## Instructions
Multiple Feature Forecaster - Cut Line Forecaster
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
NOTE: Inspiration for the change on making this spreadsheet support multiple features in the same week or sprint goes to Tyler Motherwell. Tyler can be contacted here tyler.motherwell@agilebydesign.com and I (and you) owe him a beer sometime. soon.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count (or size) range estimates and either estimated team throughput (or velocity) or historical team throughput (or velocity) samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood results as the number of simulated trials that finished on or before a given date. Given your desired scenario order, it shows what features will likely end by the target date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. The most likely date has only a 50% chance of being achieved because the velocity or throughput is a historical average. That's the odds of a coin-coss. This method allows you to choose the amount of schedule risk you wish to sign-up for. 85% is a typical middle ground used in the industry, but you can go higher odds or lower odds as you decide.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is it's better than intuition alone and better than simple regression models.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). You can also use velocity if you wish; make sure you also enter the feature sizes in points in that case. You have to be consistent.
For more probabilistic forecasting resources: FocusedObjective.com Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Go to my training workshop and consulting website
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. Use care.

## More Like This
Contact ME
Email: troy.magennis@focusedobjective.com
Twitter: @t_magennis
LinkedIn: https://www.linkedin.com/in/troymagennis
Schedule a call: https://freebusy.io/data/data
FocusedObjective.com - Forecasting and Metrics Consulting and Training
Online Calculators
Here is a set of online articles that help understand the mathematics behind Agile. We add to these all the time and would like to hear ideas you have for more.
Introduction to Monte Carlo Simulation and Forecasting
How much improvement do I get by adding more teams or people?
Story Point Velocity or Throughput Forecasting - Does it matter?
Understanding Optimal Batch Size
How Does Utilization Impact Lead-time of Work?
Impact of Multiple Team Dependencies in Software Development
MORE - Agile data notebooks and calculator articles...
Forecasting and Metric Spreadsheets
To be honest, you probably know us because of our spreadsheet tools. Thats OK, but now consider training :)
Multiple Feature Cut Line Forecaster: I want to forecast multiple features at once
Team Dashboard: I want to quickly create an team dashboard
Skill and Capability Survey and Matrix: I want to quickly survey teams to understand skill constraints
Time Series Forecasting for Demand
MORE - A lot more on our GitHub repo ....
I recently launced a SaaS application to track and manage Blockers and Dependencies between teams. It is FREE to use at a team level (just invite your team members and have a consolidated view of all impediments and the causes of those impediments).
See: BlockedApp.com for all the details (click anywhere in this box to open)
Once you have flow and blockers under control at a team level, invite other teams and other organizations to start fixing those flow problems (and we then gladly accept your credit-card for monthly subscription based on # teams).
Features at a glance -
- Capture Blockers and the causes of those blockers for YOUR team, these are always sorted by Urgency and Age to make sure the right "Blockers" pop to the top.
- See what teams are blocked by YOUR team
- Email and Slack notifications (if turned on) on new blockers to the right teams and channels
- Analytics (charts of course, it is me you know) on"Blockers in Progress" "Team vs Team Matrix" "Leading Causes" and "Lost Days" charts
- Full bi-directional integration with JIRA (if configured)
Want help? Go to my training workshop and consulting website

## Forecast
Feature Cut Line Forecaster and Explorer
1. Start Date | 2021-01-01 |  | 2. Target Date | 2021-03-01 |  | 3. Likelihood | 85% |  | 8. Month Throughput Adjustment (increase or decrease throughput by multiplying)
4. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [8 empty] | Month |  | Multiplier | Why? (add a comment with the assumptions)
[9 empty] | January | 1 | 1
| Low guess |  | 1 |  | Highest guess |  | 2 |  | February | 2 | 1
[9 empty] | March | 3 | 1
5. Throughput (or velocity). How many completed stories per week or sprint do you estimate low and high bounds? | [8 empty] | April | 4 | 1
[9 empty] | May | 5 | 1
Throughput/velocity data or estimate is per |  |  |  | Week | 7 | days |  |  | June | 6 | 1
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [8 empty] | July | 7 | 1
Use historical data OR enter a low and high estimate below. | [5 empty] | Choose here: | Estimate |  | August | 8 | 1
[9 empty] | September | 9 | 1
[9 empty] | October | 10 | 1
| Worst case |  | 5 |  | Best case |  | 8 |  | November | 11 | 1
[9 empty] | December | 12 | 1
Team focus on THIS work |  |  | 100% (only this work) |  |  |  | 100%
6. Enter the features and story count (or point) estimates here… | [6 empty] | Start date: 01/01/2021
Start Order | Feature (or Epic) Name (just for reference) |  |  | Story Count (or points) Low Guess | Story Count (or points) High Guess | Scope complexity (how well understood is this scope) | Complete by Week | Forecast Completion Date (85% CI) | Legend
1 | Feature 1 |  |  | 5 | 10 |  | 3 | 2021-01-22 | 1 | Forecast on or before the target date
2 | Feature 2 |  |  | 8 | 15 |  | 6 | 2021-02-12 | 2 | Forecast misses target date by one Week or less
3 | Feature 3 |  |  | 15 | 25 |  | 12 | 2021-03-26 | 3 | Forecast misses target date by MORE than one Week
4 | Feature 4 |  |  | 20 | 30 |  | 19 | 2021-05-14
5 | Feature 5 |  |  | 10 | 40 |  | 27 | 2021-07-09
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
We do unit testing using the excel built-in scenario manager. There is a limitation in excel that these can only work on one worksheet, so for the moment, the tests are here in this sheet!
Unit tests | Current scenario |  | None
Expected | Actual | Result | Valid scenario | Steps
Open the scenario manager - (Data-What If-Scenario Manager)
"Show" the 3 x Reset* Scenarios
2015-01-08 | 2021-01-22 |  | 1 | Confirm pass
2015-01-15 | 2021-02-12 |  | 1 | Confirm pass
2015-01-22 | 2021-03-26 |  | 1 | Confirm pass
2015-01-29 | 2021-05-14 |  | 1 | Confirm pass
2015-02-05 | 2021-07-09 |  | 1 | Confirm pass
2015-02-12 |  |  | 1 | Confirm pass
2015-02-19 |  |  | 1 | Confirm pass
2015-02-26 |  |  | 1 | Confirm pass
2015-03-05 |  |  | 1 | Confirm pass
2015-03-12 |  |  | 1 | Confirm pass
"Show" the Reverse Order scenario
2015-03-12 | 2021-01-22 |  | 2 | Confirm pass
2015-03-05 | 2021-02-12 |  | 2 | Confirm pass
2015-02-26 | 2021-03-26 |  | 2 | Confirm pass
2015-02-19 | 2021-05-14 |  | 2 | Confirm pass
2015-02-12 | 2021-07-09 |  | 2 | Confirm pass
2015-02-05 |  |  | 2 | Confirm pass
2015-01-29 |  |  | 2 | Confirm pass
2015-01-22 |  |  | 2 | Confirm pass
2015-01-15 |  |  | 2 | Confirm pass
2015-01-08 |  |  | 2 | Confirm pass
"Show" Start Date Scenario
2015-03-13 | 2021-01-22 |  | 3 | Confirm pass
2015-01-16 |  |  | 4 | "Show" Splitting Scenario and should pass
2015-01-30 |  |  | 5 | "Show" ThroughputUnit Scenario and should pass
2015-01-16 |  |  | 6 | "Show" Throughput Estimate Scenario and should pass
7
8
9
10
Why add an adjustment? You might know in advance that the team is forming, growing, or going to be at a conference (just saying)…
0.5 means team expected to perform at half the estimated rate. 2.0 means the team will perform twice as good as the estimated rate. Leave at 1.0 if you are unsure of what to do here.
The start order value is provided as a convenient way to explore the options of feature delivery order. Look for feature delivery orders that maximize delivery given the target deadline.
Only edit orange input cells like this one!

## Historical Samples
Enter Samples Below
3
5
4
7
| Total Count |  | 4
| Data |  | 4 | 3 | 7 | 5 | 5
| Estimate |  | 6 | 7 | 6 | 7 | 6
| Samples Or Data |  | 7 | 8 | 7 | 8 | 7
Transportable data formats
| CSV | 3,5,4,7
| SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="4" average="4.75" median="4.5">3,5,4,7</sip>
| Distribution | <distribution name="dist" shape="fromSamples">3,5,4,7</distribution>
Instructions.
If you have team historic throughput or velocity samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random samples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software

## Settings and Calculations
Duration name | days
Week | 7
Sprint (2 week) | 14
Sprint (3 week) | 21
Sprint (4 week) | 28
Complexity | Low Multiplier | High Multiplier
Clear and understood | 1 | 1
Somewhat understood | 1 | 1.5
Not really understood yet | 1.5 | 2
Very unclear or understood | 1.75 | 3
Focus | Adjustment
100% (only this work) | 1
75% (mostly this work) | 0.75
50% (half this work) | 0.5
25% (some of this work) | 0.25
Settings
Date format | mm/dd/yyyy
Low guess message | Low guess must be <= highest guess. Decrease low, or increase high.
High guess message | Highest guess must be >= low guess.
This section allows scenario ordering, and removes logic from individual monte carlo sheets. Best NOT to touch this :)
order | low | high | low adj | high adj | intervals | date
1 | 5 | 10 | 1 | 1 | 3 | 2021-01-22
2 | 8 | 15 | 1 | 1 | 6 | 2021-02-12
3 | 15 | 25 | 1 | 1 | 12 | 2021-03-26
4 | 20 | 30 | 1 | 1 | 19 | 2021-05-14
5 | 10 | 40 | 1 | 1 | 27 | 2021-07-09
6 | 0 | 0 | 1 | 1
7 | 0 | 0 | 1 | 1
8 | 0 | 0 | 1 | 1
9 | 0 | 0 | 1 | 1
10 | 0 | 0 | 1 | 1
11 | 0 | 0 | 1 | 1
12 | 0 | 0 | 1 | 1
13 | 0 | 0 | 1 | 1
14 | 0 | 0 | 1 | 1
15 | 0 | 0 | 1 | 1
16 | 0 | 0 | 1 | 1
17 | 0 | 0 | 1 | 1
18 | 0 | 0 | 1 | 1
19 | 0 | 0 | 1 | 1
20 | 0 | 0 | 1 | 1
Formulas:
date = IF([intervals]<>"",StartDate+(DaysPerThroughputUnit*[intervals]),"")
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.
What is this table?
Sometimes we estimate the size of work without a chance to really understand it yet. Use this complexity table to adjust the scope to account for this uncertainty. The low and high multipliers adjust the estimated scope values.

## Monte Carlo (hidden)
Trial | StorySplitRateMultiplier | Goal 1 | Goal 2 | Goal 3 | Goal 4 | Goal 5 | Goal 6 | Goal 7 | Goal 8 | Goal 9 | Goal 10 | Goal 11 | Goal 12 | Goal 13 | Goal 14 | Goal 15 | Goal 16 | Goal 17 | Goal 18 | Goal 19 | Goal 20 | Result 1 | Result 2 | Result 3 | Result 4 | Result 5 | Result 6 | Result 7 | Result 8 | Result 9 | Result 10 | Result 11 | Result 12 | Result 13 | Result 14 | Result 15 | Result 16 | Result 17 | Result 18 | Result 19 | Result 20 | End week 1 | End week 2 | End week 3 | End week 4 | End week 5 | End week 6 | End week 7 | End week 8 | End week 9 | End week 10 | End week 11 | End week 12 | End week 13 | End week 14 | End week 15 | End week 16 | End week 17 | End week 18 | End week 19 | End week 20 | End week 21 | End week 22 | End week 23 | End week 24 | End week 25 | End week 26 | End week 27 | End week 28 | End week 29 | End week 30 | End week 31 | End week 32 | End week 33 | End week 34 | End week 35 | End week 36 | End week 37 | End week 38 | End week 39 | End week 40 | End week 41 | End week 42 | End week 43 | End week 44 | End week 45 | End week 46 | End week 47 | End week 48 | End week 49 | End week 50 | End week 51 | End week 52 | End week 53 | End week 54 | End week 55 | End week 56 | End week 57 | End week 58 | End week 59 | End week 60 | End week 61 | End week 62 | End week 63 | End week 64 | End week 65 | End week 66 | End week 67 | End week 68 | End week 69 | End week 70 | End week 71 | End week 72 | End week 73 | End week 74 | End week 75 | End week 76 | End week 77 | End week 78 | End week 79 | End week 80 | End week 81 | End week 82 | End week 83 | End week 84 | End week 85 | End week 86 | End week 87 | End week 88 | End week 89 | End week 90 | End week 91 | End week 92 | End week 93 | End week 94 | End week 95 | End week 96 | End week 97 | End week 98 | End week 99 | End week 100 | End week 101 | End week 102 | End week 103 | End week 104
 | time axis 2021-01-08 to 2022-12-30
1 | 1.4349 | 8 | 29 | 58 | 97 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 5 | 9 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 12 | 17 | 25 | 33 | 39 | 47 | 53 | 58 | 63 | 69 | 74 | 79 | 87 | 92 | 97 | 102 | 109 | 117 | 123 | 130 | 137 | 144 | 150 | 158 | 166 | 173 | 178 | 185 | 191 | 197 | 203 | 211 | 219 | 225 | 233 | 241 | 247 | 254 | 262 | 268 | 274 | 281 | 287 | 294 | 301 | 306 | 312 | 317 | 323 | 329 | 336 | 342 | 350 | 357 | 362 | 368 | 375 | 382 | 389 | 397 | 405 | 411 | 419 | 426 | 434 | 441 | 449 | 456 | 461 | 468 | 475 | 482 | 490 | 497 | 504 | 510 | 515 | 520 | 526 | 531 | 539 | 544 | 552 | 560 | 566 | 572 | 579 | 585 | 591 | 599 | 605 | 613 | 619 | 626 | 634 | 640 | 648 | 656 | 662 | 668 | 674 | 680 | 688
2 | 1.7893 | 13 | 30 | 73 | 116 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 3 | 5 | 12 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 12 | 17 | 24 | 30 | 35 | 41 | 46 | 54 | 62 | 69 | 74 | 80 | 88 | 94 | 101 | 109 | 114 | 119 | 126 | 134 | 141 | 147 | 153 | 161 | 167 | 175 | 181 | 186 | 191 | 198 | 203 | 210 | 216 | 224 | 229 | 234 | 239 | 247 | 255 | 263 | 269 | 274 | 281 | 289 | 295 | 303 | 311 | 317 | 323 | 328 | 335 | 341 | 349 | 357 | 365 | 371 | 376 | 384 | 390 | 395 | 403 | 410 | 415 | 420 | 425 | 432 | 440 | 445 | 450 | 456 | 464 | 471 | 477 | 483 | 491 | 496 | 503 | 511 | 517 | 523 | 531 | 539 | 544 | 550 | 556 | 564 | 569 | 576 | 583 | 589 | 597 | 602 | 609 | 616 | 624 | 631 | 639 | 644 | 651 | 657 | 665 | 672 | 680
3 | 1.9004 | 14 | 41 | 89 | 147 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 2 | 6 | 14 | 23 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 8 | 15 | 23 | 29 | 37 | 43 | 51 | 57 | 63 | 68 | 75 | 80 | 88 | 93 | 100 | 106 | 114 | 120 | 128 | 133 | 139 | 144 | 150 | 155 | 162 | 169 | 177 | 182 | 189 | 195 | 201 | 206 | 212 | 220 | 225 | 231 | 236 | 243 | 249 | 256 | 262 | 269 | 275 | 281 | 289 | 296 | 301 | 307 | 314 | 322 | 328 | 335 | 343 | 351 | 356 | 363 | 369 | 377 | 384 | 389 | 396 | 403 | 409 | 415 | 422 | 429 | 437 | 444 | 450 | 455 | 461 | 466 | 471 | 478 | 483 | 491 | 497 | 505 | 510 | 517 | 523 | 528 | 533 | 539 | 545 | 550 | 557 | 565 | 570 | 577 | 583 | 591 | 599 | 604 | 611 | 619 | 626 | 634 | 640 | 646 | 653 | 661 | 669 | 676
4 | 1.6558 | 9 | 34 | 69 | 104 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 2 | 6 | 12 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 11 | 18 | 23 | 29 | 37 | 45 | 50 | 56 | 61 | 68 | 74 | 80 | 88 | 94 | 102 | 107 | 112 | 119 | 124 | 132 | 140 | 145 | 153 | 160 | 167 | 172 | 178 | 183 | 189 | 197 | 202 | 210 | 218 | 224 | 231 | 238 | 244 | 250 | 258 | 265 | 270 | 277 | 284 | 291 | 298 | 306 | 311 | 318 | 323 | 329 | 337 | 345 | 353 | 360 | 366 | 372 | 378 | 384 | 391 | 399 | 404 | 410 | 417 | 422 | 430 | 436 | 442 | 449 | 455 | 462 | 469 | 476 | 484 | 490 | 495 | 503 | 508 | 515 | 521 | 527 | 535 | 540 | 545 | 553 | 560 | 565 | 573 | 578 | 585 | 592 | 600 | 606 | 611 | 618 | 624 | 631 | 639 | 644 | 650 | 657 | 662 | 670 | 675
5 | 1.6183 | 10 | 35 | 63 | 104 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 2 | 6 | 10 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 12 | 19 | 25 | 32 | 39 | 44 | 50 | 57 | 64 | 71 | 78 | 84 | 90 | 97 | 104 | 111 | 116 | 122 | 128 | 136 | 143 | 151 | 158 | 164 | 169 | 176 | 181 | 186 | 193 | 198 | 204 | 210 | 215 | 222 | 228 | 234 | 240 | 246 | 253 | 259 | 267 | 274 | 282 | 290 | 298 | 304 | 312 | 317 | 324 | 331 | 337 | 342 | 347 | 355 | 361 | 366 | 372 | 380 | 387 | 392 | 400 | 407 | 415 | 423 | 431 | 436 | 444 | 449 | 454 | 460 | 467 | 474 | 480 | 485 | 491 | 499 | 506 | 512 | 519 | 527 | 535 | 540 | 548 | 555 | 562 | 567 | 572 | 578 | 585 | 592 | 600 | 607 | 615 | 621 | 627 | 634 | 639 | 646 | 654 | 660 | 667 | 674 | 679
6 | 1.3919 | 9 | 26 | 52 | 85 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 2 | 4 | 8 | 13 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 15 | 23 | 30 | 35 | 41 | 49 | 54 | 60 | 65 | 70 | 78 | 86 | 93 | 98 | 103 | 110 | 115 | 122 | 129 | 135 | 142 | 148 | 154 | 160 | 166 | 174 | 181 | 186 | 194 | 200 | 207 | 215 | 222 | 227 | 232 | 238 | 243 | 248 | 255 | 261 | 269 | 276 | 281 | 288 | 295 | 300 | 305 | 313 | 320 | 328 | 334 | 342 | 348 | 353 | 360 | 365 | 371 | 378 | 385 | 393 | 398 | 406 | 414 | 422 | 430 | 435 | 440 | 446 | 452 | 459 | 464 | 471 | 476 | 483 | 488 | 494 | 502 | 507 | 514 | 520 | 526 | 532 | 540 | 545 | 553 | 559 | 564 | 569 | 576 | 584 | 592 | 597 | 604 | 609 | 614 | 622 | 627 | 635 | 643 | 648 | 654 | 659 | 665
7 | 1.0377 | 11 | 23 | 40 | 66 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 2 | 4 | 7 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 13 | 18 | 24 | 30 | 35 | 42 | 50 | 57 | 64 | 72 | 78 | 83 | 90 | 96 | 101 | 108 | 115 | 120 | 128 | 135 | 141 | 148 | 155 | 161 | 167 | 174 | 182 | 188 | 193 | 200 | 205 | 212 | 220 | 228 | 233 | 240 | 246 | 254 | 262 | 269 | 276 | 282 | 288 | 295 | 302 | 308 | 314 | 322 | 327 | 335 | 341 | 348 | 355 | 362 | 368 | 376 | 384 | 389 | 394 | 399 | 407 | 414 | 419 | 425 | 431 | 436 | 443 | 448 | 455 | 461 | 469 | 476 | 484 | 491 | 496 | 503 | 510 | 516 | 521 | 527 | 532 | 539 | 544 | 552 | 557 | 565 | 571 | 576 | 581 | 587 | 594 | 601 | 606 | 611 | 617 | 625 | 630 | 635 | 643 | 648 | 654 | 660 | 667
8 | 1.7189 | 16 | 32 | 63 | 106 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 3 | 6 | 11 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 11 | 18 | 23 | 28 | 33 | 41 | 49 | 54 | 61 | 67 | 75 | 80 | 85 | 92 | 100 | 105 | 110 | 117 | 124 | 129 | 136 | 142 | 148 | 156 | 161 | 166 | 172 | 177 | 185 | 192 | 199 | 207 | 213 | 220 | 226 | 233 | 240 | 245 | 251 | 257 | 262 | 267 | 275 | 283 | 288 | 296 | 303 | 309 | 314 | 322 | 330 | 336 | 344 | 351 | 356 | 363 | 371 | 376 | 383 | 391 | 397 | 403 | 409 | 414 | 420 | 427 | 433 | 441 | 449 | 457 | 465 | 470 | 478 | 484 | 491 | 496 | 503 | 511 | 517 | 523 | 528 | 536 | 541 | 548 | 556 | 563 | 568 | 573 | 581 | 586 | 593 | 601 | 606 | 612 | 617 | 622 | 630 | 638 | 644 | 651 | 657 | 665 | 671
9 | 1.7856 | 11 | 35 | 80 | 125 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 2 | 6 | 13 | 20 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 11 | 19 | 25 | 30 | 38 | 46 | 51 | 56 | 62 | 70 | 77 | 85 | 92 | 100 | 105 | 110 | 118 | 123 | 131 | 139 | 146 | 153 | 159 | 167 | 175 | 180 | 186 | 192 | 197 | 205 | 211 | 217 | 224 | 232 | 240 | 245 | 251 | 259 | 266 | 273 | 280 | 285 | 290 | 297 | 302 | 308 | 314 | 319 | 327 | 333 | 341 | 349 | 354 | 362 | 370 | 377 | 382 | 389 | 397 | 403 | 411 | 416 | 422 | 429 | 434 | 441 | 449 | 455 | 462 | 468 | 473 | 479 | 484 | 491 | 496 | 503 | 509 | 517 | 523 | 530 | 537 | 543 | 550 | 555 | 560 | 566 | 571 | 576 | 582 | 588 | 593 | 598 | 604 | 610 | 615 | 621 | 626 | 631 | 636 | 641 | 649 | 655 | 661
10 | 1.2155 | 11 | 25 | 56 | 84 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 2 | 4 | 9 | 13 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 15 | 23 | 28 | 34 | 39 | 44 | 51 | 59 | 67 | 73 | 79 | 85 | 92 | 98 | 103 | 111 | 118 | 126 | 133 | 141 | 148 | 154 | 159 | 167 | 173 | 181 | 188 | 193 | 201 | 208 | 215 | 220 | 225 | 232 | 238 | 245 | 251 | 258 | 265 | 273 | 281 | 287 | 293 | 300 | 307 | 314 | 320 | 326 | 332 | 339 | 346 | 353 | 361 | 366 | 372 | 380 | 388 | 395 | 401 | 408 | 414 | 419 | 424 | 432 | 437 | 442 | 450 | 458 | 466 | 471 | 477 | 485 | 492 | 500 | 505 | 513 | 521 | 528 | 535 | 540 | 545 | 553 | 559 | 565 | 571 | 577 | 585 | 593 | 599 | 606 | 612 | 618 | 624 | 630 | 637 | 643 | 648 | 656 | 661 | 668 | 673 | 681 | 689
11 | 1.6665 | 17 | 34 | 59 | 98 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 3 | 6 | 10 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 15 | 22 | 27 | 32 | 40 | 45 | 52 | 57 | 64 | 72 | 80 | 88 | 94 | 100 | 106 | 113 | 118 | 123 | 130 | 137 | 145 | 152 | 157 | 164 | 172 | 178 | 185 | 190 | 198 | 206 | 213 | 219 | 224 | 229 | 234 | 239 | 245 | 252 | 259 | 264 | 270 | 275 | 282 | 287 | 294 | 300 | 306 | 311 | 318 | 323 | 328 | 335 | 343 | 350 | 356 | 363 | 370 | 377 | 384 | 391 | 399 | 404 | 411 | 419 | 426 | 431 | 437 | 444 | 451 | 457 | 463 | 470 | 477 | 485 | 492 | 498 | 505 | 510 | 517 | 522 | 529 | 534 | 540 | 548 | 556 | 563 | 570 | 578 | 586 | 593 | 601 | 608 | 615 | 620 | 625 | 630 | 637 | 644 | 651 | 657 | 663 | 671 | 677
12 | 1.8143 | 13 | 37 | 83 | 122 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 2 | 6 | 14 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 8 | 16 | 21 | 27 | 33 | 38 | 45 | 51 | 58 | 63 | 68 | 75 | 80 | 88 | 93 | 99 | 107 | 115 | 120 | 128 | 134 | 140 | 147 | 152 | 157 | 165 | 171 | 178 | 183 | 188 | 193 | 200 | 207 | 214 | 222 | 229 | 234 | 241 | 249 | 254 | 259 | 266 | 274 | 282 | 290 | 295 | 300 | 308 | 315 | 323 | 329 | 334 | 340 | 345 | 350 | 358 | 366 | 372 | 377 | 384 | 392 | 398 | 405 | 413 | 419 | 426 | 432 | 440 | 446 | 454 | 462 | 470 | 475 | 481 | 489 | 496 | 503 | 510 | 517 | 525 | 530 | 537 | 545 | 553 | 559 | 566 | 571 | 577 | 582 | 588 | 596 | 602 | 608 | 613 | 618 | 625 | 631 | 636 | 641 | 646 | 654 | 659 | 665 | 671
13 | 1.1882 | 9 | 23 | 46 | 81 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 4 | 7 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 15 | 20 | 27 | 33 | 40 | 47 | 55 | 62 | 69 | 75 | 82 | 89 | 96 | 102 | 109 | 114 | 121 | 128 | 135 | 142 | 149 | 155 | 163 | 168 | 176 | 184 | 191 | 198 | 206 | 212 | 217 | 223 | 228 | 234 | 240 | 247 | 254 | 260 | 266 | 273 | 279 | 286 | 292 | 298 | 306 | 311 | 317 | 323 | 328 | 334 | 339 | 346 | 352 | 359 | 365 | 370 | 377 | 383 | 389 | 395 | 401 | 407 | 414 | 422 | 427 | 432 | 438 | 443 | 448 | 454 | 459 | 465 | 470 | 475 | 482 | 489 | 495 | 503 | 508 | 516 | 522 | 527 | 533 | 539 | 545 | 550 | 556 | 563 | 568 | 574 | 580 | 586 | 593 | 600 | 607 | 612 | 620 | 626 | 634 | 640 | 647 | 653 | 658
14 | 1.2062 | 13 | 26 | 49 | 80 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 2 | 4 | 8 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 14 | 21 | 29 | 35 | 40 | 46 | 51 | 56 | 62 | 67 | 72 | 79 | 85 | 93 | 99 | 104 | 111 | 118 | 125 | 130 | 136 | 141 | 149 | 156 | 161 | 168 | 175 | 181 | 187 | 194 | 201 | 207 | 215 | 221 | 229 | 235 | 243 | 250 | 256 | 264 | 271 | 279 | 286 | 291 | 297 | 302 | 307 | 314 | 319 | 327 | 333 | 341 | 348 | 355 | 361 | 366 | 374 | 379 | 384 | 390 | 396 | 402 | 408 | 414 | 420 | 427 | 434 | 442 | 448 | 453 | 460 | 465 | 472 | 477 | 485 | 492 | 499 | 504 | 510 | 515 | 522 | 527 | 534 | 541 | 548 | 553 | 559 | 567 | 572 | 577 | 583 | 590 | 597 | 604 | 611 | 617 | 624 | 632 | 639 | 644 | 651 | 658 | 666
15 | 1.6552 | 15 | 34 | 64 | 114 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 3 | 6 | 10 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 13 | 19 | 24 | 30 | 37 | 44 | 51 | 59 | 67 | 74 | 81 | 88 | 93 | 100 | 108 | 114 | 119 | 124 | 131 | 136 | 143 | 151 | 156 | 162 | 168 | 173 | 181 | 188 | 193 | 200 | 206 | 211 | 218 | 223 | 228 | 235 | 241 | 246 | 254 | 259 | 265 | 271 | 279 | 284 | 290 | 298 | 303 | 311 | 319 | 327 | 335 | 340 | 346 | 354 | 359 | 364 | 370 | 378 | 384 | 390 | 395 | 400 | 405 | 411 | 416 | 423 | 429 | 434 | 439 | 444 | 451 | 458 | 464 | 469 | 476 | 482 | 489 | 497 | 505 | 512 | 520 | 526 | 532 | 537 | 544 | 551 | 559 | 566 | 574 | 579 | 587 | 594 | 600 | 606 | 612 | 620 | 628 | 633 | 640 | 645 | 651 | 658 | 665
16 | 1.1828 | 6 | 22 | 43 | 71 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 1 | 4 | 8 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 6 | 14 | 19 | 25 | 31 | 36 | 41 | 49 | 57 | 65 | 70 | 78 | 84 | 91 | 96 | 104 | 111 | 116 | 124 | 131 | 136 | 143 | 151 | 157 | 162 | 168 | 173 | 178 | 185 | 193 | 201 | 207 | 215 | 220 | 228 | 236 | 242 | 248 | 255 | 260 | 268 | 275 | 281 | 289 | 294 | 299 | 304 | 309 | 314 | 322 | 327 | 333 | 340 | 348 | 355 | 363 | 369 | 375 | 382 | 387 | 395 | 400 | 407 | 412 | 418 | 423 | 431 | 437 | 442 | 448 | 455 | 463 | 469 | 477 | 482 | 487 | 492 | 497 | 503 | 510 | 517 | 525 | 533 | 540 | 548 | 554 | 561 | 567 | 574 | 579 | 586 | 591 | 596 | 601 | 607 | 614 | 620 | 626 | 633 | 638 | 644 | 650 | 657 | 662
17 | 1.3052 | 14 | 25 | 57 | 93 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 2 | 4 | 10 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 14 | 20 | 26 | 33 | 38 | 45 | 50 | 55 | 61 | 67 | 72 | 77 | 83 | 89 | 97 | 103 | 108 | 116 | 122 | 130 | 136 | 143 | 148 | 153 | 161 | 166 | 172 | 179 | 185 | 192 | 200 | 208 | 213 | 219 | 225 | 233 | 241 | 246 | 254 | 259 | 267 | 275 | 281 | 288 | 295 | 303 | 310 | 315 | 322 | 327 | 333 | 339 | 347 | 354 | 360 | 368 | 373 | 380 | 387 | 394 | 399 | 404 | 409 | 417 | 423 | 430 | 436 | 443 | 451 | 456 | 463 | 468 | 473 | 481 | 488 | 496 | 503 | 509 | 517 | 524 | 529 | 536 | 541 | 548 | 556 | 564 | 572 | 578 | 585 | 590 | 597 | 602 | 608 | 613 | 621 | 628 | 635 | 641 | 646 | 652 | 658 | 665 | 670
18 | 1.8795 | 14 | 30 | 76 | 123 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 2 | 5 | 11 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 16 | 24 | 29 | 35 | 40 | 48 | 55 | 62 | 70 | 76 | 83 | 91 | 97 | 105 | 110 | 115 | 122 | 128 | 135 | 143 | 149 | 157 | 164 | 172 | 180 | 186 | 193 | 201 | 208 | 216 | 224 | 232 | 238 | 243 | 248 | 255 | 262 | 269 | 276 | 284 | 292 | 299 | 304 | 312 | 318 | 324 | 331 | 339 | 345 | 352 | 360 | 367 | 373 | 379 | 387 | 395 | 401 | 406 | 411 | 419 | 425 | 430 | 435 | 441 | 446 | 453 | 459 | 465 | 473 | 481 | 487 | 492 | 499 | 506 | 513 | 519 | 527 | 533 | 539 | 546 | 551 | 559 | 566 | 571 | 578 | 583 | 588 | 593 | 598 | 603 | 608 | 616 | 622 | 630 | 636 | 641 | 647 | 654 | 659 | 667 | 672 | 678 | 683
19 | 1.6667 | 12 | 34 | 68 | 108 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 2 | 5 | 10 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 16 | 24 | 31 | 37 | 44 | 51 | 58 | 63 | 70 | 76 | 81 | 89 | 97 | 103 | 109 | 116 | 123 | 129 | 134 | 142 | 149 | 157 | 165 | 171 | 176 | 183 | 188 | 196 | 201 | 206 | 211 | 218 | 225 | 231 | 237 | 245 | 252 | 260 | 266 | 273 | 280 | 286 | 294 | 300 | 307 | 312 | 319 | 327 | 333 | 341 | 349 | 357 | 362 | 368 | 376 | 381 | 388 | 395 | 400 | 406 | 411 | 418 | 426 | 431 | 436 | 442 | 448 | 454 | 460 | 467 | 475 | 481 | 488 | 495 | 503 | 510 | 517 | 522 | 529 | 536 | 544 | 551 | 556 | 562 | 570 | 575 | 582 | 590 | 595 | 601 | 608 | 616 | 621 | 626 | 631 | 638 | 643 | 649 | 654 | 660 | 668 | 676 | 683
20 | 1.1462 | 11 | 24 | 44 | 72 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 4 | 8 | 11 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 11 | 19 | 25 | 31 | 37 | 43 | 51 | 59 | 66 | 72 | 79 | 84 | 89 | 96 | 101 | 109 | 114 | 121 | 126 | 132 | 139 | 146 | 151 | 159 | 165 | 172 | 180 | 187 | 195 | 202 | 209 | 216 | 222 | 230 | 236 | 241 | 247 | 255 | 260 | 265 | 273 | 279 | 287 | 294 | 299 | 304 | 309 | 315 | 321 | 326 | 333 | 340 | 348 | 355 | 361 | 366 | 373 | 381 | 388 | 396 | 401 | 408 | 413 | 418 | 423 | 430 | 435 | 440 | 447 | 455 | 463 | 469 | 476 | 483 | 491 | 498 | 503 | 511 | 519 | 525 | 533 | 541 | 546 | 551 | 557 | 564 | 569 | 575 | 581 | 589 | 594 | 600 | 607 | 612 | 619 | 625 | 631 | 639 | 647 | 652 | 659 | 665 | 673
21 | 1.5923 | 8 | 28 | 54 | 90 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 1 | 5 | 8 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 13 | 19 | 26 | 32 | 40 | 48 | 55 | 62 | 68 | 75 | 83 | 89 | 97 | 104 | 112 | 118 | 124 | 129 | 135 | 142 | 147 | 153 | 160 | 166 | 173 | 178 | 183 | 189 | 194 | 202 | 209 | 215 | 221 | 226 | 231 | 237 | 245 | 253 | 260 | 268 | 274 | 281 | 287 | 295 | 303 | 309 | 317 | 324 | 331 | 338 | 345 | 350 | 358 | 363 | 370 | 376 | 382 | 389 | 396 | 404 | 411 | 419 | 426 | 434 | 442 | 450 | 458 | 463 | 468 | 476 | 482 | 488 | 495 | 502 | 507 | 512 | 520 | 525 | 532 | 538 | 543 | 550 | 555 | 563 | 569 | 575 | 581 | 587 | 595 | 602 | 609 | 614 | 619 | 627 | 635 | 640 | 646 | 651 | 658 | 664 | 670 | 676 | 681
22 | 1.4234 | 12 | 34 | 64 | 97 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 6 | 10 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 12 | 18 | 24 | 32 | 40 | 46 | 54 | 60 | 68 | 75 | 81 | 88 | 96 | 103 | 111 | 119 | 125 | 130 | 136 | 144 | 151 | 159 | 167 | 174 | 182 | 189 | 195 | 201 | 208 | 215 | 223 | 228 | 234 | 240 | 245 | 251 | 257 | 264 | 272 | 280 | 286 | 294 | 301 | 308 | 315 | 320 | 325 | 333 | 339 | 346 | 351 | 357 | 365 | 371 | 378 | 386 | 393 | 400 | 408 | 413 | 420 | 427 | 434 | 440 | 446 | 454 | 460 | 466 | 473 | 479 | 485 | 490 | 497 | 505 | 513 | 519 | 524 | 532 | 540 | 547 | 553 | 561 | 568 | 573 | 581 | 588 | 594 | 599 | 605 | 613 | 618 | 623 | 628 | 634 | 641 | 648 | 655 | 661 | 669 | 674 | 679 | 686 | 693
23 | 1.751 | 13 | 31 | 72 | 120 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 3 | 6 | 13 | 20 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 12 | 18 | 24 | 29 | 37 | 42 | 47 | 54 | 59 | 64 | 69 | 77 | 85 | 93 | 98 | 104 | 112 | 118 | 124 | 132 | 140 | 145 | 153 | 158 | 166 | 173 | 178 | 186 | 193 | 201 | 207 | 213 | 221 | 229 | 236 | 244 | 251 | 257 | 262 | 270 | 275 | 283 | 291 | 296 | 302 | 309 | 315 | 322 | 330 | 338 | 344 | 350 | 358 | 363 | 370 | 376 | 384 | 390 | 395 | 400 | 406 | 414 | 420 | 426 | 433 | 440 | 447 | 455 | 462 | 467 | 474 | 482 | 488 | 496 | 504 | 509 | 515 | 522 | 527 | 534 | 542 | 547 | 553 | 558 | 566 | 573 | 580 | 586 | 594 | 599 | 605 | 611 | 616 | 623 | 628 | 633 | 640 | 646 | 653 | 660 | 668 | 673 | 680
24 | 1.9876 | 18 | 38 | 68 | 124 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 3 | 6 | 11 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 16 | 21 | 28 | 34 | 42 | 47 | 53 | 58 | 64 | 72 | 77 | 84 | 90 | 98 | 106 | 114 | 119 | 127 | 133 | 138 | 146 | 154 | 161 | 166 | 174 | 179 | 187 | 192 | 198 | 203 | 208 | 216 | 223 | 229 | 234 | 240 | 245 | 250 | 257 | 264 | 272 | 279 | 286 | 291 | 296 | 302 | 307 | 313 | 321 | 327 | 333 | 338 | 345 | 353 | 361 | 368 | 373 | 379 | 384 | 391 | 397 | 402 | 410 | 417 | 425 | 433 | 438 | 446 | 452 | 459 | 465 | 472 | 480 | 487 | 492 | 500 | 507 | 512 | 518 | 524 | 529 | 534 | 540 | 547 | 554 | 559 | 567 | 572 | 578 | 584 | 589 | 594 | 599 | 606 | 612 | 619 | 625 | 630 | 635 | 642 | 648 | 654 | 662
25 | 1.0411 | 10 | 21 | 39 | 67 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 2 | 3 | 6 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 16 | 23 | 30 | 38 | 45 | 52 | 58 | 66 | 74 | 80 | 88 | 93 | 98 | 104 | 112 | 120 | 126 | 131 | 139 | 144 | 150 | 156 | 164 | 169 | 177 | 182 | 188 | 193 | 199 | 205 | 211 | 218 | 226 | 233 | 240 | 245 | 253 | 261 | 269 | 277 | 283 | 291 | 297 | 305 | 311 | 318 | 325 | 333 | 339 | 345 | 352 | 360 | 368 | 374 | 381 | 389 | 394 | 401 | 408 | 415 | 422 | 430 | 437 | 445 | 452 | 459 | 466 | 472 | 478 | 485 | 492 | 498 | 503 | 510 | 517 | 524 | 530 | 538 | 546 | 551 | 557 | 562 | 568 | 576 | 582 | 588 | 595 | 602 | 609 | 617 | 624 | 632 | 637 | 645 | 652 | 660 | 665 | 670 | 678 | 685 | 691 | 699 | 705
26 | 1.1542 | 9 | 19 | 40 | 73 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 2 | 3 | 7 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 15 | 20 | 27 | 33 | 38 | 43 | 48 | 55 | 62 | 68 | 74 | 80 | 87 | 93 | 100 | 107 | 113 | 119 | 127 | 134 | 139 | 147 | 154 | 159 | 167 | 174 | 179 | 185 | 192 | 198 | 203 | 208 | 213 | 218 | 226 | 232 | 240 | 245 | 250 | 258 | 264 | 269 | 277 | 282 | 290 | 298 | 303 | 308 | 315 | 320 | 326 | 332 | 338 | 344 | 349 | 356 | 363 | 370 | 378 | 385 | 391 | 399 | 406 | 411 | 419 | 425 | 430 | 438 | 445 | 453 | 458 | 466 | 471 | 479 | 484 | 491 | 496 | 502 | 507 | 514 | 519 | 525 | 533 | 539 | 547 | 552 | 558 | 566 | 574 | 579 | 586 | 591 | 598 | 605 | 612 | 620 | 627 | 635 | 640 | 646 | 653 | 660 | 667
27 | 1.0225 | 10 | 20 | 38 | 63 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 2 | 4 | 7 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 13 | 19 | 26 | 31 | 37 | 42 | 49 | 55 | 62 | 67 | 73 | 80 | 87 | 93 | 98 | 105 | 110 | 116 | 124 | 132 | 137 | 143 | 149 | 157 | 165 | 171 | 177 | 182 | 189 | 196 | 204 | 209 | 217 | 222 | 227 | 232 | 240 | 247 | 255 | 260 | 267 | 275 | 280 | 285 | 292 | 299 | 304 | 312 | 317 | 325 | 332 | 340 | 346 | 351 | 357 | 364 | 371 | 379 | 387 | 393 | 401 | 407 | 415 | 420 | 425 | 432 | 437 | 444 | 452 | 458 | 465 | 471 | 476 | 484 | 489 | 495 | 501 | 507 | 514 | 520 | 525 | 530 | 538 | 546 | 552 | 558 | 563 | 571 | 579 | 586 | 594 | 601 | 606 | 614 | 622 | 628 | 635 | 643 | 651 | 658 | 666 | 671 | 678
28 | 1.8605 | 10 | 27 | 74 | 121 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 2 | 5 | 12 | 19 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 13 | 19 | 25 | 31 | 39 | 47 | 54 | 60 | 65 | 73 | 79 | 85 | 91 | 99 | 105 | 110 | 118 | 123 | 130 | 137 | 144 | 149 | 155 | 161 | 166 | 174 | 182 | 187 | 195 | 201 | 207 | 212 | 217 | 223 | 231 | 239 | 244 | 251 | 259 | 267 | 275 | 280 | 287 | 294 | 301 | 307 | 312 | 318 | 323 | 330 | 337 | 344 | 350 | 355 | 361 | 366 | 374 | 382 | 389 | 396 | 404 | 412 | 418 | 426 | 434 | 441 | 448 | 456 | 462 | 470 | 478 | 485 | 492 | 497 | 504 | 512 | 517 | 524 | 532 | 539 | 544 | 549 | 555 | 563 | 569 | 575 | 583 | 589 | 596 | 602 | 609 | 615 | 620 | 628 | 635 | 640 | 647 | 652 | 657 | 665 | 671 | 676 | 684
29 | 1.1111 | 12 | 21 | 40 | 67 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 2 | 3 | 6 | 9 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 16 | 24 | 32 | 38 | 46 | 52 | 59 | 67 | 74 | 79 | 84 | 89 | 95 | 102 | 109 | 116 | 123 | 128 | 136 | 142 | 150 | 157 | 165 | 173 | 181 | 186 | 191 | 199 | 206 | 212 | 217 | 222 | 230 | 238 | 244 | 249 | 255 | 261 | 269 | 276 | 282 | 288 | 293 | 301 | 308 | 315 | 322 | 327 | 334 | 340 | 348 | 354 | 360 | 365 | 370 | 376 | 383 | 388 | 394 | 402 | 410 | 415 | 423 | 431 | 437 | 442 | 449 | 457 | 463 | 468 | 474 | 482 | 489 | 496 | 503 | 508 | 516 | 521 | 528 | 535 | 541 | 547 | 555 | 560 | 566 | 573 | 581 | 588 | 595 | 600 | 608 | 615 | 623 | 630 | 636 | 642 | 650 | 656 | 664 | 671 | 676 | 684 | 689
30 | 1.8749 | 12 | 29 | 61 | 118 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 2 | 5 | 10 | 19 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 8 | 13 | 21 | 27 | 35 | 40 | 47 | 52 | 58 | 65 | 70 | 77 | 83 | 91 | 96 | 103 | 109 | 116 | 121 | 128 | 135 | 142 | 149 | 155 | 163 | 169 | 177 | 182 | 187 | 192 | 200 | 208 | 215 | 221 | 228 | 235 | 243 | 248 | 254 | 261 | 267 | 273 | 281 | 288 | 295 | 303 | 310 | 316 | 323 | 331 | 337 | 343 | 351 | 357 | 365 | 371 | 378 | 385 | 392 | 397 | 405 | 413 | 419 | 427 | 435 | 443 | 450 | 456 | 464 | 471 | 477 | 482 | 489 | 496 | 501 | 509 | 514 | 520 | 528 | 533 | 538 | 544 | 551 | 556 | 563 | 569 | 574 | 580 | 588 | 595 | 600 | 608 | 613 | 621 | 629 | 636 | 644 | 650 | 655 | 663 | 668 | 673 | 680 | 685
31 | 1.9315 | 20 | 42 | 87 | 142 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 4 | 7 | 14 | 23 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 13 | 19 | 25 | 30 | 35 | 43 | 51 | 59 | 67 | 73 | 79 | 84 | 90 | 97 | 102 | 109 | 116 | 123 | 128 | 136 | 141 | 147 | 152 | 159 | 165 | 170 | 175 | 182 | 188 | 193 | 198 | 203 | 209 | 215 | 223 | 230 | 237 | 243 | 249 | 256 | 263 | 269 | 277 | 282 | 290 | 295 | 301 | 309 | 316 | 323 | 330 | 335 | 343 | 348 | 354 | 362 | 369 | 375 | 380 | 385 | 392 | 399 | 407 | 415 | 422 | 429 | 436 | 443 | 450 | 456 | 462 | 468 | 474 | 482 | 490 | 495 | 501 | 509 | 516 | 522 | 530 | 535 | 540 | 545 | 553 | 559 | 566 | 572 | 580 | 586 | 594 | 599 | 605 | 613 | 620 | 628 | 634 | 642 | 650 | 657 | 664 | 669 | 676
32 | 1.8643 | 10 | 31 | 74 | 116 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 2 | 5 | 12 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 14 | 21 | 27 | 35 | 40 | 47 | 53 | 58 | 64 | 70 | 77 | 85 | 92 | 99 | 106 | 111 | 117 | 122 | 128 | 134 | 139 | 147 | 153 | 160 | 166 | 171 | 176 | 183 | 190 | 197 | 205 | 211 | 218 | 224 | 229 | 235 | 241 | 248 | 256 | 263 | 271 | 278 | 283 | 290 | 295 | 301 | 309 | 315 | 321 | 327 | 333 | 339 | 345 | 352 | 357 | 365 | 371 | 377 | 382 | 389 | 395 | 403 | 408 | 415 | 420 | 427 | 433 | 438 | 444 | 452 | 457 | 464 | 469 | 476 | 484 | 491 | 496 | 501 | 506 | 512 | 520 | 526 | 531 | 538 | 545 | 551 | 558 | 565 | 573 | 581 | 589 | 594 | 601 | 608 | 614 | 621 | 626 | 633 | 639 | 645 | 650 | 655 | 660
33 | 1.1216 | 6 | 20 | 41 | 65 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 1 | 4 | 7 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 11 | 18 | 26 | 32 | 40 | 47 | 53 | 60 | 68 | 74 | 80 | 85 | 92 | 98 | 105 | 113 | 121 | 129 | 137 | 143 | 151 | 156 | 163 | 169 | 177 | 185 | 193 | 200 | 205 | 211 | 219 | 224 | 231 | 239 | 244 | 250 | 258 | 265 | 273 | 278 | 286 | 294 | 301 | 306 | 314 | 321 | 326 | 334 | 339 | 345 | 351 | 359 | 367 | 374 | 380 | 385 | 392 | 399 | 405 | 411 | 419 | 425 | 432 | 439 | 447 | 452 | 460 | 467 | 473 | 480 | 487 | 494 | 501 | 508 | 513 | 520 | 525 | 530 | 535 | 540 | 547 | 554 | 562 | 570 | 575 | 583 | 589 | 595 | 601 | 606 | 611 | 618 | 625 | 633 | 641 | 647 | 652 | 658 | 665 | 673 | 681 | 686 | 692
34 | 1.5389 | 16 | 30 | 66 | 99 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 3 | 6 | 11 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 12 | 18 | 24 | 29 | 35 | 41 | 48 | 56 | 63 | 68 | 76 | 82 | 89 | 97 | 102 | 107 | 113 | 120 | 125 | 133 | 140 | 145 | 150 | 158 | 165 | 173 | 178 | 183 | 189 | 194 | 201 | 208 | 215 | 222 | 229 | 235 | 243 | 250 | 258 | 266 | 271 | 276 | 281 | 288 | 295 | 301 | 306 | 312 | 317 | 322 | 328 | 333 | 340 | 345 | 352 | 359 | 364 | 372 | 378 | 383 | 390 | 396 | 401 | 406 | 413 | 418 | 425 | 430 | 438 | 445 | 451 | 458 | 465 | 471 | 477 | 482 | 489 | 494 | 501 | 506 | 511 | 519 | 525 | 530 | 536 | 544 | 550 | 555 | 560 | 568 | 576 | 584 | 592 | 598 | 604 | 610 | 618 | 626 | 633 | 641 | 649 | 656 | 664
35 | 1.8315 | 17 | 39 | 74 | 120 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 3 | 6 | 12 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 12 | 18 | 24 | 31 | 39 | 46 | 53 | 58 | 63 | 69 | 77 | 85 | 93 | 98 | 103 | 109 | 114 | 122 | 130 | 138 | 144 | 151 | 158 | 163 | 168 | 174 | 180 | 187 | 193 | 200 | 206 | 211 | 218 | 223 | 228 | 234 | 240 | 248 | 254 | 259 | 264 | 272 | 280 | 286 | 291 | 298 | 306 | 311 | 319 | 327 | 332 | 338 | 344 | 352 | 357 | 364 | 369 | 374 | 379 | 384 | 391 | 396 | 402 | 409 | 414 | 421 | 429 | 436 | 442 | 449 | 456 | 464 | 469 | 475 | 480 | 487 | 492 | 499 | 507 | 515 | 520 | 525 | 533 | 538 | 544 | 550 | 555 | 560 | 568 | 575 | 582 | 587 | 595 | 600 | 606 | 614 | 620 | 625 | 632 | 638 | 644 | 649 | 656
36 | 1.9516 | 16 | 46 | 78 | 121 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 3 | 7 | 12 | 19 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 15 | 20 | 26 | 33 | 41 | 46 | 52 | 59 | 67 | 75 | 81 | 86 | 94 | 100 | 105 | 112 | 117 | 125 | 133 | 141 | 146 | 153 | 159 | 164 | 172 | 177 | 185 | 191 | 198 | 205 | 213 | 220 | 228 | 235 | 240 | 247 | 252 | 260 | 267 | 272 | 280 | 285 | 290 | 297 | 303 | 309 | 317 | 322 | 329 | 337 | 344 | 350 | 356 | 362 | 367 | 374 | 382 | 389 | 394 | 401 | 408 | 414 | 420 | 428 | 433 | 438 | 445 | 450 | 455 | 462 | 467 | 475 | 480 | 487 | 494 | 500 | 506 | 513 | 521 | 528 | 535 | 540 | 547 | 553 | 559 | 564 | 572 | 577 | 582 | 590 | 597 | 605 | 612 | 618 | 623 | 629 | 635 | 642 | 649 | 654 | 662 | 668 | 674
37 | 1.7995 | 15 | 37 | 70 | 112 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 3 | 6 | 11 | 18 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 6 | 13 | 18 | 24 | 30 | 38 | 46 | 53 | 60 | 66 | 73 | 78 | 86 | 91 | 96 | 102 | 108 | 114 | 122 | 129 | 137 | 144 | 149 | 155 | 163 | 168 | 174 | 179 | 187 | 194 | 202 | 207 | 213 | 218 | 225 | 231 | 236 | 241 | 247 | 253 | 260 | 266 | 272 | 278 | 284 | 291 | 299 | 305 | 310 | 316 | 321 | 327 | 335 | 340 | 347 | 353 | 358 | 366 | 372 | 378 | 385 | 393 | 399 | 405 | 411 | 418 | 424 | 430 | 438 | 446 | 451 | 459 | 466 | 473 | 480 | 488 | 496 | 503 | 509 | 514 | 522 | 530 | 536 | 544 | 550 | 557 | 562 | 570 | 576 | 584 | 589 | 595 | 600 | 606 | 612 | 620 | 627 | 635 | 642 | 649 | 654 | 662 | 670 | 676
38 | 1.5036 | 11 | 34 | 57 | 94 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 3 | 6 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 10 | 18 | 23 | 30 | 38 | 46 | 54 | 59 | 65 | 71 | 76 | 84 | 92 | 100 | 106 | 111 | 119 | 125 | 130 | 136 | 144 | 151 | 157 | 163 | 168 | 173 | 179 | 185 | 191 | 197 | 202 | 210 | 217 | 225 | 233 | 239 | 244 | 250 | 256 | 262 | 270 | 276 | 282 | 290 | 297 | 304 | 309 | 314 | 322 | 330 | 336 | 342 | 350 | 357 | 365 | 372 | 378 | 384 | 392 | 399 | 406 | 412 | 420 | 426 | 433 | 439 | 447 | 452 | 460 | 466 | 472 | 478 | 483 | 490 | 497 | 505 | 511 | 519 | 524 | 531 | 538 | 546 | 553 | 560 | 568 | 574 | 580 | 588 | 596 | 601 | 608 | 615 | 623 | 630 | 637 | 642 | 650 | 655 | 661 | 669 | 676 | 681 | 688
39 | 1.689 | 17 | 36 | 77 | 116 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 3 | 6 | 11 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 11 | 19 | 27 | 35 | 41 | 48 | 56 | 63 | 71 | 78 | 85 | 93 | 99 | 106 | 113 | 121 | 128 | 136 | 141 | 147 | 155 | 162 | 170 | 178 | 186 | 194 | 202 | 210 | 218 | 223 | 228 | 233 | 240 | 247 | 255 | 261 | 267 | 273 | 279 | 285 | 291 | 299 | 305 | 312 | 319 | 324 | 331 | 338 | 343 | 348 | 354 | 359 | 367 | 374 | 379 | 385 | 392 | 399 | 404 | 411 | 418 | 423 | 430 | 438 | 443 | 449 | 457 | 463 | 471 | 478 | 486 | 491 | 496 | 504 | 510 | 518 | 525 | 533 | 540 | 547 | 553 | 561 | 566 | 571 | 576 | 582 | 587 | 595 | 600 | 606 | 611 | 619 | 625 | 631 | 639 | 647 | 655 | 661 | 669 | 674 | 681 | 688 | 696
40 | 1.5688 | 15 | 37 | 64 | 112 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 3 | 6 | 10 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 5 | 13 | 21 | 27 | 34 | 39 | 47 | 54 | 59 | 64 | 70 | 78 | 86 | 91 | 98 | 105 | 112 | 120 | 128 | 133 | 138 | 145 | 152 | 159 | 166 | 174 | 180 | 186 | 191 | 197 | 204 | 210 | 216 | 221 | 229 | 236 | 242 | 249 | 256 | 262 | 267 | 272 | 280 | 288 | 296 | 304 | 309 | 314 | 319 | 325 | 331 | 338 | 344 | 349 | 356 | 364 | 369 | 377 | 384 | 392 | 397 | 405 | 411 | 417 | 423 | 429 | 436 | 442 | 448 | 455 | 460 | 465 | 472 | 479 | 485 | 493 | 501 | 508 | 515 | 521 | 526 | 531 | 539 | 545 | 552 | 559 | 564 | 572 | 580 | 585 | 593 | 599 | 607 | 612 | 619 | 625 | 630 | 635 | 643 | 649 | 657 | 665 | 673 | 679
41 | 1.4141 | 8 | 23 | 49 | 79 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 1 | 4 | 8 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 15 | 20 | 26 | 33 | 41 | 47 | 54 | 59 | 67 | 74 | 80 | 86 | 92 | 97 | 105 | 111 | 116 | 123 | 129 | 137 | 144 | 151 | 156 | 163 | 171 | 177 | 185 | 190 | 198 | 206 | 212 | 219 | 227 | 233 | 238 | 243 | 250 | 258 | 263 | 268 | 274 | 281 | 286 | 292 | 300 | 306 | 314 | 322 | 330 | 338 | 344 | 350 | 357 | 363 | 371 | 378 | 385 | 393 | 398 | 403 | 409 | 414 | 422 | 427 | 435 | 443 | 449 | 455 | 461 | 466 | 472 | 477 | 484 | 489 | 495 | 503 | 508 | 514 | 520 | 526 | 533 | 538 | 543 | 548 | 555 | 562 | 570 | 575 | 581 | 589 | 596 | 604 | 612 | 620 | 625 | 633 | 638 | 645 | 653 | 661 | 666 | 674 | 681
42 | 1.3958 | 10 | 30 | 53 | 83 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 2 | 5 | 8 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8 | 16 | 24 | 29 | 34 | 41 | 48 | 56 | 64 | 70 | 76 | 81 | 88 | 94 | 100 | 107 | 113 | 118 | 125 | 132 | 140 | 146 | 154 | 162 | 168 | 173 | 180 | 188 | 195 | 202 | 208 | 215 | 221 | 227 | 235 | 242 | 250 | 257 | 265 | 273 | 280 | 286 | 291 | 299 | 304 | 311 | 319 | 327 | 334 | 339 | 344 | 350 | 355 | 361 | 367 | 372 | 379 | 386 | 391 | 398 | 404 | 409 | 414 | 421 | 427 | 433 | 439 | 444 | 449 | 456 | 462 | 467 | 474 | 480 | 486 | 492 | 498 | 503 | 508 | 516 | 521 | 529 | 537 | 542 | 547 | 554 | 562 | 570 | 578 | 586 | 591 | 599 | 604 | 609 | 617 | 623 | 631 | 636 | 641 | 646 | 652 | 659 | 664 | 669
43 | 1.239 | 7 | 24 | 54 | 90 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 5 | 9 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 10 | 15 | 22 | 28 | 36 | 43 | 49 | 55 | 60 | 67 | 75 | 81 | 89 | 96 | 104 | 109 | 114 | 121 | 128 | 135 | 143 | 151 | 159 | 165 | 173 | 181 | 189 | 195 | 201 | 208 | 213 | 218 | 224 | 230 | 235 | 243 | 251 | 256 | 262 | 268 | 276 | 282 | 290 | 297 | 305 | 310 | 316 | 321 | 328 | 335 | 340 | 348 | 356 | 361 | 366 | 371 | 378 | 383 | 389 | 395 | 401 | 406 | 413 | 421 | 426 | 431 | 436 | 442 | 449 | 457 | 462 | 468 | 475 | 481 | 488 | 494 | 500 | 507 | 512 | 517 | 524 | 529 | 534 | 539 | 546 | 553 | 558 | 563 | 571 | 576 | 581 | 587 | 592 | 598 | 604 | 610 | 616 | 621 | 629 | 636 | 642 | 650 | 658
44 | 1.0779 | 6 | 15 | 41 | 68 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 2 | 3 | 7 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 10 | 18 | 23 | 29 | 37 | 43 | 48 | 53 | 59 | 67 | 75 | 82 | 87 | 93 | 101 | 106 | 113 | 119 | 126 | 131 | 136 | 143 | 148 | 156 | 164 | 169 | 175 | 181 | 189 | 194 | 200 | 208 | 214 | 221 | 226 | 233 | 238 | 244 | 251 | 257 | 263 | 270 | 277 | 283 | 290 | 295 | 302 | 310 | 316 | 324 | 329 | 335 | 343 | 348 | 355 | 360 | 368 | 374 | 381 | 389 | 396 | 402 | 408 | 413 | 420 | 427 | 432 | 440 | 448 | 453 | 459 | 466 | 474 | 481 | 487 | 494 | 502 | 508 | 515 | 523 | 531 | 538 | 544 | 552 | 557 | 565 | 572 | 577 | 583 | 590 | 595 | 600 | 607 | 614 | 619 | 624 | 632 | 638 | 646 | 653 | 660 | 666 | 671
45 | 1.6912 | 17 | 36 | 72 | 115 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 3 | 5 | 11 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 13 | 21 | 28 | 36 | 44 | 51 | 57 | 65 | 71 | 76 | 81 | 89 | 96 | 103 | 111 | 118 | 123 | 129 | 134 | 141 | 149 | 157 | 164 | 169 | 177 | 184 | 192 | 197 | 205 | 210 | 216 | 223 | 230 | 236 | 243 | 248 | 253 | 261 | 266 | 272 | 277 | 284 | 289 | 297 | 302 | 310 | 317 | 325 | 333 | 339 | 344 | 352 | 358 | 366 | 372 | 377 | 383 | 391 | 398 | 403 | 408 | 415 | 420 | 427 | 434 | 442 | 447 | 452 | 458 | 463 | 468 | 474 | 482 | 490 | 497 | 503 | 509 | 515 | 522 | 529 | 537 | 543 | 548 | 555 | 563 | 570 | 575 | 580 | 586 | 591 | 596 | 601 | 609 | 617 | 625 | 630 | 637 | 643 | 649 | 654 | 659 | 666 | 672
46 | 1.1616 | 9 | 19 | 49 | 84 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 2 | 4 | 9 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 6 | 11 | 16 | 21 | 29 | 36 | 42 | 48 | 53 | 61 | 68 | 74 | 81 | 87 | 94 | 102 | 107 | 112 | 120 | 128 | 133 | 141 | 148 | 155 | 162 | 168 | 174 | 182 | 188 | 194 | 202 | 209 | 214 | 222 | 229 | 236 | 244 | 250 | 257 | 265 | 272 | 277 | 285 | 293 | 301 | 309 | 317 | 324 | 330 | 338 | 346 | 352 | 359 | 364 | 372 | 379 | 386 | 391 | 396 | 403 | 410 | 415 | 422 | 427 | 432 | 439 | 446 | 454 | 460 | 467 | 475 | 480 | 485 | 491 | 496 | 501 | 509 | 517 | 525 | 531 | 538 | 543 | 548 | 554 | 561 | 568 | 575 | 582 | 588 | 594 | 601 | 606 | 611 | 616 | 624 | 630 | 636 | 644 | 649 | 655 | 663 | 669 | 676 | 682
47 | 1.0998 | 10 | 27 | 54 | 80 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 2 | 4 | 9 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 12 | 20 | 27 | 34 | 41 | 47 | 53 | 58 | 63 | 69 | 74 | 79 | 86 | 92 | 98 | 105 | 111 | 116 | 121 | 129 | 136 | 144 | 150 | 158 | 166 | 172 | 177 | 182 | 187 | 192 | 197 | 203 | 209 | 216 | 223 | 229 | 235 | 241 | 248 | 256 | 261 | 266 | 274 | 279 | 287 | 294 | 302 | 308 | 314 | 320 | 326 | 332 | 339 | 344 | 351 | 359 | 364 | 371 | 378 | 385 | 391 | 396 | 402 | 409 | 414 | 419 | 427 | 433 | 439 | 447 | 454 | 459 | 467 | 474 | 479 | 484 | 490 | 498 | 504 | 512 | 517 | 523 | 530 | 536 | 541 | 548 | 556 | 561 | 569 | 574 | 581 | 588 | 596 | 603 | 610 | 616 | 624 | 630 | 638 | 645 | 651 | 658 | 666
48 | 1.3432 | 10 | 31 | 58 | 85 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 5 | 8 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 15 | 23 | 30 | 36 | 42 | 50 | 58 | 64 | 70 | 78 | 83 | 91 | 96 | 102 | 110 | 117 | 123 | 129 | 134 | 140 | 148 | 154 | 162 | 170 | 175 | 183 | 189 | 194 | 201 | 208 | 216 | 221 | 228 | 236 | 244 | 249 | 254 | 260 | 268 | 276 | 284 | 291 | 299 | 307 | 312 | 317 | 322 | 330 | 337 | 343 | 348 | 356 | 361 | 368 | 374 | 380 | 385 | 390 | 397 | 403 | 408 | 416 | 422 | 430 | 436 | 444 | 450 | 457 | 464 | 470 | 475 | 482 | 488 | 494 | 501 | 509 | 517 | 524 | 530 | 538 | 546 | 554 | 562 | 568 | 576 | 583 | 589 | 596 | 601 | 609 | 614 | 622 | 628 | 633 | 641 | 649 | 657 | 665 | 671 | 676 | 684 | 691 | 697
49 | 1.6033 | 13 | 30 | 55 | 104 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 2 | 5 | 9 | 15 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 14 | 22 | 28 | 36 | 42 | 47 | 53 | 61 | 69 | 76 | 84 | 92 | 100 | 105 | 110 | 115 | 120 | 128 | 136 | 143 | 151 | 158 | 164 | 169 | 177 | 182 | 190 | 197 | 205 | 212 | 219 | 224 | 232 | 240 | 246 | 253 | 260 | 268 | 273 | 281 | 289 | 294 | 300 | 306 | 312 | 320 | 328 | 334 | 340 | 345 | 353 | 361 | 369 | 374 | 379 | 386 | 394 | 400 | 405 | 411 | 417 | 423 | 429 | 437 | 444 | 452 | 460 | 467 | 472 | 478 | 485 | 492 | 497 | 504 | 512 | 519 | 525 | 533 | 540 | 545 | 552 | 557 | 563 | 570 | 575 | 581 | 589 | 594 | 601 | 607 | 613 | 619 | 625 | 631 | 637 | 642 | 648 | 655 | 660 | 665 | 670 | 678 | 683
50 | 1.1194 | 11 | 27 | 45 | 75 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 2 | 4 | 7 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 16 | 24 | 31 | 36 | 41 | 46 | 53 | 59 | 64 | 70 | 77 | 85 | 91 | 99 | 105 | 113 | 121 | 127 | 133 | 140 | 145 | 152 | 157 | 162 | 170 | 176 | 181 | 187 | 195 | 200 | 206 | 211 | 218 | 226 | 234 | 242 | 247 | 252 | 259 | 266 | 273 | 281 | 287 | 294 | 300 | 306 | 313 | 321 | 326 | 331 | 337 | 344 | 351 | 357 | 362 | 368 | 375 | 381 | 386 | 394 | 401 | 408 | 416 | 422 | 430 | 436 | 444 | 451 | 457 | 465 | 473 | 481 | 489 | 497 | 505 | 512 | 520 | 526 | 531 | 537 | 542 | 548 | 553 | 558 | 565 | 573 | 581 | 587 | 592 | 600 | 608 | 613 | 621 | 626 | 634 | 639 | 646 | 652 | 658 | 663 | 671 | 677 | 685
51 | 1.8042 | 19 | 34 | 76 | 114 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 3 | 5 | 11 | 17 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 15 | 22 | 27 | 34 | 41 | 48 | 56 | 62 | 68 | 76 | 84 | 90 | 97 | 103 | 110 | 116 | 121 | 129 | 134 | 140 | 147 | 153 | 159 | 164 | 169 | 177 | 185 | 190 | 196 | 204 | 212 | 220 | 228 | 234 | 242 | 248 | 254 | 260 | 268 | 276 | 282 | 289 | 294 | 299 | 305 | 311 | 318 | 324 | 331 | 338 | 345 | 353 | 361 | 368 | 374 | 381 | 387 | 395 | 403 | 409 | 414 | 421 | 426 | 431 | 436 | 441 | 446 | 453 | 460 | 467 | 475 | 480 | 485 | 491 | 498 | 504 | 509 | 515 | 521 | 527 | 533 | 541 | 549 | 557 | 565 | 572 | 578 | 584 | 592 | 597 | 602 | 607 | 613 | 619 | 624 | 631 | 638 | 645 | 652 | 658 | 666 | 671 | 679
52 | 1.466 | 14 | 31 | 61 | 101 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 3 | 6 | 10 | 17 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 10 | 16 | 23 | 29 | 34 | 42 | 49 | 57 | 62 | 68 | 74 | 81 | 87 | 94 | 99 | 107 | 112 | 118 | 123 | 130 | 136 | 143 | 149 | 156 | 164 | 171 | 178 | 186 | 193 | 201 | 207 | 212 | 219 | 225 | 230 | 237 | 242 | 248 | 256 | 262 | 270 | 276 | 284 | 290 | 296 | 304 | 312 | 318 | 324 | 331 | 338 | 346 | 352 | 358 | 363 | 368 | 373 | 380 | 388 | 393 | 401 | 407 | 412 | 418 | 426 | 433 | 438 | 446 | 451 | 457 | 463 | 471 | 478 | 485 | 491 | 497 | 503 | 510 | 515 | 522 | 529 | 536 | 544 | 549 | 556 | 563 | 570 | 577 | 582 | 587 | 595 | 603 | 611 | 617 | 623 | 631 | 639 | 644 | 652 | 660 | 667 | 672 | 679
53 | 1.5962 | 8 | 23 | 49 | 91 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 2 | 4 | 7 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 14 | 19 | 27 | 33 | 41 | 49 | 57 | 62 | 68 | 74 | 79 | 84 | 92 | 99 | 104 | 111 | 119 | 125 | 132 | 140 | 148 | 154 | 159 | 166 | 173 | 178 | 185 | 191 | 197 | 202 | 207 | 212 | 219 | 226 | 232 | 237 | 243 | 249 | 255 | 260 | 268 | 275 | 280 | 286 | 294 | 300 | 305 | 313 | 321 | 327 | 333 | 338 | 346 | 352 | 360 | 366 | 374 | 381 | 389 | 395 | 401 | 406 | 412 | 420 | 425 | 430 | 435 | 441 | 448 | 454 | 459 | 464 | 470 | 477 | 484 | 489 | 494 | 500 | 508 | 515 | 523 | 530 | 536 | 543 | 548 | 554 | 561 | 567 | 575 | 583 | 589 | 596 | 601 | 608 | 616 | 623 | 629 | 634 | 642 | 648 | 654 | 662 | 668
54 | 1.4931 | 14 | 37 | 70 | 112 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 3 | 6 | 12 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 10 | 18 | 26 | 33 | 38 | 44 | 51 | 56 | 64 | 69 | 74 | 80 | 87 | 93 | 99 | 105 | 111 | 118 | 125 | 131 | 136 | 142 | 150 | 157 | 164 | 171 | 178 | 183 | 190 | 196 | 202 | 207 | 215 | 222 | 227 | 233 | 241 | 246 | 252 | 259 | 266 | 274 | 280 | 288 | 296 | 301 | 307 | 315 | 323 | 329 | 336 | 343 | 348 | 353 | 359 | 365 | 372 | 377 | 383 | 388 | 393 | 398 | 406 | 411 | 419 | 424 | 429 | 436 | 441 | 446 | 452 | 460 | 465 | 472 | 480 | 485 | 492 | 499 | 506 | 511 | 518 | 524 | 532 | 538 | 546 | 552 | 560 | 567 | 574 | 582 | 587 | 595 | 603 | 611 | 616 | 623 | 630 | 637 | 644 | 651 | 658 | 664 | 669
55 | 1.475 | 9 | 32 | 56 | 101 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 6 | 10 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 11 | 17 | 22 | 27 | 34 | 42 | 48 | 54 | 59 | 65 | 73 | 78 | 86 | 93 | 98 | 106 | 111 | 119 | 127 | 135 | 141 | 147 | 154 | 160 | 166 | 172 | 178 | 186 | 191 | 196 | 204 | 211 | 217 | 222 | 230 | 237 | 243 | 251 | 256 | 261 | 269 | 275 | 283 | 291 | 297 | 303 | 309 | 314 | 319 | 324 | 332 | 337 | 345 | 353 | 361 | 367 | 375 | 380 | 387 | 393 | 400 | 408 | 415 | 422 | 427 | 435 | 442 | 448 | 453 | 458 | 465 | 473 | 481 | 488 | 495 | 501 | 506 | 513 | 519 | 524 | 529 | 535 | 540 | 545 | 551 | 558 | 565 | 572 | 578 | 585 | 592 | 597 | 605 | 610 | 617 | 625 | 633 | 641 | 646 | 651 | 657 | 664 | 669
56 | 1.058 | 11 | 23 | 47 | 77 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 2 | 4 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 12 | 18 | 25 | 32 | 37 | 45 | 51 | 57 | 62 | 67 | 74 | 82 | 90 | 95 | 101 | 106 | 111 | 118 | 124 | 132 | 140 | 145 | 151 | 159 | 166 | 172 | 178 | 185 | 191 | 197 | 202 | 207 | 215 | 223 | 231 | 239 | 246 | 254 | 262 | 270 | 276 | 281 | 288 | 293 | 299 | 306 | 311 | 319 | 327 | 333 | 339 | 346 | 352 | 357 | 364 | 372 | 377 | 384 | 391 | 398 | 404 | 410 | 415 | 423 | 430 | 437 | 442 | 449 | 454 | 459 | 466 | 471 | 479 | 484 | 491 | 498 | 503 | 510 | 516 | 522 | 530 | 537 | 544 | 549 | 557 | 563 | 569 | 577 | 582 | 590 | 596 | 603 | 608 | 616 | 621 | 629 | 637 | 643 | 648 | 655 | 663 | 669 | 674
57 | 1.854 | 13 | 38 | 83 | 132 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 3 | 7 | 13 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 11 | 18 | 24 | 31 | 37 | 45 | 50 | 58 | 66 | 73 | 80 | 85 | 93 | 101 | 106 | 113 | 118 | 126 | 133 | 141 | 148 | 154 | 159 | 165 | 173 | 178 | 184 | 190 | 198 | 203 | 209 | 216 | 222 | 229 | 235 | 240 | 245 | 251 | 259 | 265 | 270 | 276 | 281 | 288 | 293 | 300 | 306 | 312 | 318 | 323 | 331 | 337 | 343 | 350 | 355 | 361 | 369 | 375 | 381 | 387 | 394 | 399 | 405 | 413 | 418 | 423 | 428 | 434 | 439 | 445 | 453 | 461 | 469 | 474 | 481 | 489 | 495 | 503 | 511 | 519 | 524 | 531 | 536 | 544 | 551 | 556 | 564 | 572 | 577 | 585 | 592 | 598 | 605 | 611 | 616 | 621 | 628 | 634 | 639 | 647 | 655 | 661 | 668
58 | 1.0907 | 8 | 20 | 41 | 68 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1 | 3 | 6 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 15 | 20 | 27 | 34 | 41 | 48 | 56 | 62 | 67 | 72 | 80 | 86 | 91 | 97 | 105 | 111 | 116 | 122 | 128 | 134 | 139 | 144 | 151 | 157 | 162 | 170 | 177 | 184 | 192 | 198 | 204 | 211 | 218 | 223 | 230 | 238 | 245 | 252 | 259 | 266 | 273 | 279 | 286 | 292 | 297 | 303 | 311 | 316 | 321 | 326 | 332 | 338 | 343 | 351 | 356 | 362 | 370 | 377 | 385 | 393 | 399 | 407 | 414 | 422 | 429 | 435 | 442 | 450 | 456 | 462 | 467 | 475 | 480 | 485 | 491 | 499 | 506 | 511 | 519 | 525 | 532 | 538 | 546 | 553 | 559 | 564 | 569 | 574 | 581 | 587 | 594 | 601 | 607 | 612 | 617 | 623 | 628 | 633 | 638 | 646 | 653 | 661 | 669
59 | 1.8144 | 17 | 45 | 84 | 121 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 3 | 7 | 13 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 14 | 21 | 28 | 35 | 43 | 50 | 57 | 63 | 69 | 76 | 81 | 86 | 93 | 99 | 107 | 114 | 122 | 130 | 135 | 142 | 147 | 154 | 160 | 166 | 172 | 179 | 186 | 193 | 200 | 208 | 213 | 221 | 227 | 233 | 238 | 246 | 251 | 258 | 263 | 269 | 277 | 282 | 289 | 294 | 302 | 309 | 317 | 322 | 329 | 337 | 343 | 349 | 356 | 363 | 371 | 378 | 383 | 389 | 397 | 403 | 410 | 415 | 423 | 430 | 438 | 446 | 454 | 461 | 466 | 471 | 479 | 487 | 495 | 501 | 506 | 513 | 521 | 529 | 534 | 541 | 548 | 554 | 561 | 568 | 575 | 580 | 585 | 591 | 596 | 604 | 612 | 618 | 623 | 629 | 637 | 645 | 652 | 658 | 664 | 670 | 678 | 685 | 690
60 | 1.6082 | 9 | 26 | 59 | 100 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 2 | 4 | 10 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 7 | 14 | 19 | 27 | 32 | 38 | 46 | 51 | 56 | 61 | 69 | 77 | 85 | 90 | 95 | 100 | 106 | 113 | 121 | 127 | 132 | 137 | 142 | 148 | 153 | 161 | 169 | 175 | 181 | 188 | 196 | 204 | 210 | 215 | 220 | 226 | 232 | 238 | 245 | 250 | 257 | 264 | 271 | 276 | 281 | 287 | 295 | 301 | 309 | 315 | 320 | 326 | 332 | 340 | 348 | 355 | 360 | 367 | 375 | 382 | 390 | 398 | 404 | 412 | 418 | 423 | 431 | 438 | 444 | 449 | 457 | 463 | 468 | 473 | 480 | 486 | 491 | 497 | 505 | 511 | 516 | 523 | 531 | 536 | 544 | 551 | 556 | 562 | 569 | 574 | 579 | 584 | 592 | 597 | 603 | 609 | 615 | 622 | 630 | 636 | 643 | 648 | 654 | 662
61 | 1.4574 | 9 | 31 | 53 | 88 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 2 | 6 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 13 | 18 | 24 | 30 | 36 | 41 | 48 | 55 | 62 | 70 | 76 | 82 | 88 | 95 | 100 | 106 | 114 | 120 | 128 | 136 | 141 | 147 | 155 | 163 | 170 | 176 | 183 | 188 | 193 | 200 | 206 | 212 | 218 | 223 | 229 | 234 | 239 | 244 | 252 | 259 | 266 | 273 | 279 | 284 | 292 | 298 | 306 | 314 | 319 | 325 | 331 | 337 | 344 | 352 | 359 | 366 | 371 | 377 | 385 | 393 | 399 | 406 | 411 | 417 | 424 | 432 | 440 | 448 | 453 | 461 | 467 | 475 | 480 | 485 | 491 | 498 | 506 | 511 | 519 | 524 | 529 | 536 | 543 | 548 | 554 | 560 | 565 | 573 | 579 | 585 | 590 | 597 | 604 | 609 | 614 | 621 | 627 | 635 | 643 | 650 | 655 | 662 | 669
62 | 1.221 | 13 | 32 | 63 | 99 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 3 | 5 | 10 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 12 | 20 | 26 | 34 | 41 | 46 | 52 | 59 | 64 | 69 | 74 | 81 | 87 | 95 | 101 | 108 | 113 | 121 | 129 | 136 | 141 | 149 | 156 | 163 | 168 | 174 | 180 | 186 | 192 | 200 | 205 | 211 | 218 | 223 | 228 | 234 | 242 | 248 | 255 | 262 | 268 | 275 | 281 | 287 | 295 | 301 | 308 | 315 | 322 | 327 | 335 | 341 | 347 | 352 | 360 | 365 | 373 | 381 | 386 | 394 | 400 | 406 | 414 | 422 | 427 | 432 | 440 | 445 | 450 | 458 | 464 | 469 | 476 | 484 | 490 | 497 | 503 | 511 | 518 | 524 | 532 | 538 | 543 | 550 | 557 | 564 | 571 | 579 | 586 | 593 | 599 | 605 | 612 | 617 | 623 | 630 | 637 | 643 | 651 | 659 | 665 | 671 | 678
63 | 1.8872 | 14 | 37 | 68 | 118 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 3 | 6 | 11 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 12 | 19 | 26 | 31 | 38 | 43 | 49 | 54 | 61 | 68 | 74 | 81 | 88 | 96 | 104 | 110 | 116 | 124 | 131 | 139 | 145 | 151 | 158 | 166 | 171 | 179 | 185 | 192 | 199 | 204 | 209 | 214 | 222 | 229 | 235 | 241 | 247 | 254 | 261 | 269 | 274 | 281 | 287 | 292 | 297 | 305 | 311 | 318 | 324 | 332 | 339 | 345 | 351 | 357 | 362 | 369 | 376 | 384 | 391 | 399 | 404 | 409 | 417 | 424 | 430 | 437 | 444 | 449 | 456 | 463 | 471 | 476 | 482 | 489 | 494 | 502 | 510 | 517 | 522 | 529 | 534 | 540 | 548 | 553 | 560 | 567 | 573 | 579 | 584 | 592 | 600 | 605 | 612 | 619 | 624 | 630 | 637 | 643 | 649 | 655 | 662 | 668 | 676
64 | 1.348 | 11 | 26 | 51 | 78 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 2 | 4 | 8 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 12 | 20 | 28 | 33 | 38 | 46 | 52 | 58 | 66 | 72 | 80 | 86 | 94 | 102 | 109 | 116 | 123 | 128 | 133 | 140 | 147 | 154 | 160 | 167 | 174 | 180 | 186 | 193 | 198 | 206 | 214 | 220 | 225 | 231 | 236 | 241 | 247 | 255 | 260 | 268 | 275 | 281 | 289 | 295 | 303 | 310 | 317 | 324 | 332 | 338 | 346 | 353 | 358 | 365 | 372 | 380 | 388 | 393 | 399 | 406 | 411 | 417 | 424 | 432 | 439 | 445 | 453 | 460 | 465 | 473 | 480 | 486 | 493 | 499 | 505 | 511 | 516 | 521 | 527 | 534 | 539 | 544 | 551 | 557 | 562 | 569 | 576 | 581 | 588 | 595 | 602 | 607 | 615 | 623 | 630 | 635 | 643 | 651 | 659 | 664 | 671 | 679 | 686
65 | 1.1954 | 12 | 29 | 57 | 83 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 4 | 8 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 14 | 21 | 29 | 36 | 43 | 50 | 58 | 64 | 70 | 77 | 85 | 91 | 99 | 104 | 110 | 117 | 123 | 129 | 136 | 141 | 147 | 153 | 159 | 165 | 172 | 180 | 187 | 193 | 201 | 207 | 213 | 221 | 228 | 234 | 240 | 248 | 254 | 261 | 268 | 276 | 284 | 292 | 297 | 305 | 312 | 320 | 327 | 332 | 338 | 346 | 352 | 357 | 365 | 372 | 379 | 387 | 395 | 402 | 407 | 415 | 423 | 429 | 435 | 443 | 451 | 457 | 462 | 469 | 475 | 480 | 486 | 494 | 499 | 507 | 514 | 521 | 526 | 532 | 538 | 544 | 551 | 557 | 565 | 571 | 577 | 583 | 588 | 595 | 603 | 610 | 616 | 622 | 629 | 637 | 644 | 652 | 657 | 662 | 670 | 678 | 683 | 691 | 698
66 | 1.9267 | 18 | 40 | 75 | 114 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 3 | 7 | 12 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 13 | 19 | 25 | 31 | 38 | 45 | 51 | 59 | 65 | 73 | 78 | 85 | 92 | 99 | 106 | 113 | 119 | 125 | 133 | 140 | 145 | 152 | 159 | 164 | 170 | 176 | 181 | 188 | 194 | 201 | 208 | 215 | 222 | 230 | 238 | 243 | 248 | 255 | 263 | 270 | 278 | 286 | 293 | 301 | 308 | 313 | 319 | 325 | 331 | 337 | 342 | 347 | 355 | 363 | 370 | 376 | 384 | 390 | 398 | 404 | 412 | 417 | 425 | 430 | 437 | 442 | 450 | 458 | 463 | 470 | 478 | 483 | 488 | 494 | 501 | 507 | 514 | 519 | 524 | 531 | 538 | 546 | 552 | 560 | 568 | 576 | 582 | 589 | 596 | 604 | 612 | 617 | 622 | 629 | 636 | 642 | 647 | 654 | 659 | 664 | 672 | 680 | 688
67 | 1.4576 | 12 | 33 | 68 | 98 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 2 | 5 | 11 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 13 | 21 | 29 | 36 | 41 | 46 | 54 | 61 | 66 | 74 | 81 | 86 | 94 | 101 | 109 | 117 | 124 | 131 | 139 | 145 | 150 | 156 | 164 | 171 | 179 | 184 | 189 | 194 | 200 | 205 | 211 | 218 | 224 | 229 | 237 | 245 | 251 | 258 | 263 | 268 | 276 | 284 | 291 | 296 | 301 | 309 | 316 | 324 | 330 | 336 | 343 | 350 | 355 | 361 | 367 | 374 | 381 | 388 | 393 | 401 | 409 | 415 | 420 | 426 | 431 | 437 | 444 | 449 | 457 | 462 | 470 | 475 | 483 | 491 | 497 | 505 | 510 | 517 | 525 | 533 | 538 | 545 | 552 | 559 | 564 | 571 | 577 | 585 | 590 | 597 | 604 | 611 | 618 | 626 | 631 | 636 | 642 | 650 | 656 | 664 | 670 | 677 | 684
68 | 1.2379 | 12 | 27 | 46 | 80 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 2 | 4 | 7 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 14 | 19 | 27 | 35 | 43 | 48 | 54 | 59 | 66 | 73 | 80 | 85 | 93 | 100 | 107 | 112 | 118 | 125 | 130 | 136 | 142 | 148 | 155 | 161 | 168 | 176 | 182 | 187 | 195 | 200 | 208 | 215 | 223 | 228 | 236 | 241 | 246 | 252 | 257 | 263 | 271 | 279 | 286 | 294 | 300 | 308 | 313 | 320 | 326 | 334 | 340 | 345 | 350 | 356 | 364 | 370 | 378 | 383 | 390 | 395 | 401 | 409 | 415 | 422 | 427 | 433 | 440 | 447 | 454 | 462 | 470 | 475 | 482 | 489 | 497 | 503 | 510 | 517 | 522 | 527 | 533 | 538 | 545 | 553 | 558 | 566 | 571 | 578 | 584 | 589 | 596 | 601 | 608 | 613 | 620 | 625 | 633 | 638 | 646 | 651 | 658 | 665 | 670
69 | 1.8218 | 15 | 32 | 73 | 114 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 3 | 6 | 13 | 19 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 5 | 10 | 16 | 24 | 29 | 36 | 44 | 51 | 57 | 62 | 67 | 72 | 77 | 82 | 90 | 98 | 106 | 112 | 117 | 125 | 132 | 139 | 144 | 150 | 158 | 163 | 168 | 176 | 183 | 189 | 197 | 204 | 209 | 216 | 223 | 230 | 237 | 245 | 250 | 258 | 266 | 272 | 277 | 285 | 290 | 297 | 304 | 311 | 316 | 322 | 328 | 336 | 342 | 349 | 355 | 363 | 368 | 376 | 384 | 391 | 398 | 405 | 411 | 418 | 423 | 430 | 436 | 442 | 449 | 457 | 462 | 470 | 475 | 483 | 491 | 499 | 504 | 512 | 520 | 528 | 534 | 542 | 550 | 558 | 564 | 570 | 578 | 583 | 590 | 597 | 602 | 609 | 614 | 620 | 628 | 635 | 641 | 647 | 655 | 661 | 669 | 674 | 681 | 686
70 | 1.6582 | 15 | 30 | 69 | 116 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 3 | 5 | 11 | 18 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 13 | 21 | 29 | 37 | 44 | 49 | 55 | 61 | 68 | 75 | 80 | 86 | 92 | 97 | 104 | 112 | 118 | 126 | 132 | 138 | 144 | 149 | 154 | 161 | 168 | 173 | 181 | 188 | 194 | 199 | 207 | 214 | 219 | 225 | 230 | 235 | 240 | 246 | 251 | 256 | 264 | 272 | 277 | 285 | 293 | 300 | 307 | 314 | 320 | 325 | 332 | 340 | 347 | 353 | 360 | 366 | 372 | 378 | 385 | 390 | 396 | 403 | 410 | 415 | 420 | 427 | 435 | 442 | 450 | 458 | 465 | 470 | 476 | 482 | 488 | 494 | 502 | 507 | 514 | 519 | 527 | 534 | 540 | 546 | 554 | 560 | 567 | 574 | 582 | 590 | 598 | 604 | 612 | 617 | 622 | 629 | 634 | 640 | 647 | 652 | 659 | 665 | 670
71 | 1.9664 | 20 | 48 | 88 | 144 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 4 | 7 | 13 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 7 | 13 | 19 | 25 | 33 | 41 | 49 | 56 | 63 | 71 | 79 | 84 | 92 | 99 | 107 | 114 | 120 | 127 | 134 | 140 | 145 | 151 | 157 | 164 | 171 | 176 | 182 | 188 | 196 | 204 | 210 | 218 | 223 | 230 | 238 | 244 | 249 | 254 | 262 | 269 | 275 | 281 | 287 | 292 | 300 | 308 | 315 | 322 | 329 | 336 | 344 | 349 | 357 | 363 | 368 | 376 | 384 | 390 | 395 | 401 | 408 | 415 | 422 | 428 | 435 | 442 | 447 | 453 | 460 | 466 | 471 | 477 | 484 | 491 | 496 | 502 | 508 | 515 | 521 | 528 | 534 | 539 | 545 | 551 | 557 | 565 | 570 | 578 | 585 | 593 | 598 | 606 | 614 | 620 | 627 | 632 | 637 | 642 | 648 | 654 | 661 | 666 | 673 | 681
72 | 1.5376 | 8 | 30 | 69 | 116 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 2 | 5 | 11 | 18 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 12 | 20 | 25 | 33 | 38 | 46 | 51 | 58 | 64 | 71 | 77 | 83 | 91 | 97 | 102 | 109 | 116 | 122 | 127 | 132 | 137 | 144 | 151 | 158 | 164 | 169 | 175 | 181 | 187 | 194 | 199 | 204 | 210 | 217 | 222 | 227 | 234 | 239 | 246 | 252 | 258 | 263 | 271 | 279 | 286 | 293 | 299 | 306 | 314 | 322 | 328 | 333 | 340 | 345 | 350 | 356 | 361 | 369 | 377 | 383 | 391 | 399 | 405 | 411 | 419 | 424 | 430 | 437 | 443 | 450 | 457 | 464 | 471 | 477 | 482 | 487 | 495 | 501 | 507 | 513 | 519 | 527 | 532 | 537 | 545 | 552 | 560 | 568 | 575 | 580 | 585 | 593 | 601 | 607 | 612 | 617 | 623 | 628 | 634 | 642 | 647 | 654 | 660
73 | 1.4804 | 12 | 33 | 66 | 96 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 2 | 5 | 10 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 15 | 22 | 27 | 34 | 40 | 47 | 52 | 59 | 67 | 72 | 79 | 84 | 92 | 97 | 104 | 112 | 120 | 126 | 131 | 138 | 144 | 151 | 158 | 166 | 172 | 180 | 185 | 190 | 197 | 204 | 211 | 216 | 222 | 228 | 235 | 240 | 246 | 251 | 256 | 264 | 272 | 280 | 286 | 291 | 298 | 306 | 314 | 321 | 328 | 335 | 340 | 345 | 350 | 357 | 365 | 371 | 378 | 386 | 392 | 399 | 407 | 415 | 421 | 428 | 435 | 441 | 449 | 455 | 462 | 470 | 478 | 486 | 491 | 496 | 502 | 507 | 514 | 520 | 526 | 531 | 538 | 543 | 549 | 557 | 563 | 570 | 575 | 581 | 586 | 591 | 597 | 602 | 609 | 614 | 622 | 627 | 635 | 643 | 649 | 654 | 659 | 666 | 673
74 | 1.4108 | 8 | 30 | 54 | 97 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 1 | 5 | 9 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 15 | 20 | 28 | 35 | 40 | 46 | 53 | 61 | 69 | 77 | 82 | 90 | 96 | 104 | 109 | 117 | 125 | 131 | 137 | 145 | 151 | 156 | 161 | 167 | 174 | 180 | 187 | 195 | 200 | 206 | 214 | 219 | 227 | 235 | 241 | 246 | 252 | 258 | 265 | 270 | 277 | 285 | 291 | 296 | 301 | 309 | 314 | 321 | 327 | 334 | 340 | 346 | 352 | 358 | 363 | 370 | 375 | 382 | 390 | 395 | 401 | 406 | 414 | 419 | 425 | 431 | 436 | 443 | 450 | 457 | 465 | 471 | 476 | 484 | 491 | 496 | 503 | 510 | 516 | 522 | 527 | 535 | 542 | 548 | 553 | 559 | 566 | 572 | 579 | 586 | 594 | 602 | 610 | 616 | 622 | 630 | 635 | 642 | 647 | 655 | 662 | 669 | 674
75 | 1.9236 | 20 | 38 | 75 | 131 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 4 | 7 | 12 | 21 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 6 | 12 | 19 | 26 | 32 | 37 | 43 | 50 | 55 | 63 | 71 | 77 | 82 | 88 | 93 | 99 | 107 | 112 | 118 | 124 | 131 | 138 | 146 | 154 | 161 | 169 | 177 | 185 | 192 | 199 | 207 | 214 | 222 | 228 | 233 | 241 | 246 | 253 | 259 | 264 | 270 | 276 | 282 | 289 | 296 | 304 | 312 | 317 | 324 | 332 | 338 | 343 | 351 | 356 | 362 | 368 | 374 | 380 | 386 | 394 | 402 | 407 | 415 | 420 | 426 | 433 | 439 | 446 | 453 | 461 | 468 | 476 | 481 | 489 | 494 | 502 | 508 | 515 | 520 | 525 | 531 | 539 | 545 | 551 | 557 | 565 | 572 | 577 | 582 | 588 | 594 | 599 | 605 | 612 | 620 | 625 | 631 | 639 | 645 | 652 | 659 | 664 | 670 | 676
76 | 1.43 | 13 | 35 | 64 | 99 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 6 | 11 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 13 | 21 | 26 | 31 | 39 | 44 | 51 | 57 | 62 | 68 | 75 | 82 | 87 | 95 | 102 | 107 | 112 | 120 | 126 | 132 | 138 | 146 | 153 | 160 | 167 | 175 | 182 | 187 | 193 | 198 | 204 | 211 | 216 | 222 | 228 | 235 | 241 | 246 | 254 | 262 | 268 | 273 | 279 | 284 | 292 | 297 | 304 | 309 | 314 | 320 | 326 | 332 | 338 | 346 | 354 | 362 | 368 | 376 | 383 | 391 | 399 | 405 | 413 | 420 | 428 | 435 | 443 | 451 | 459 | 465 | 471 | 478 | 483 | 491 | 496 | 502 | 507 | 513 | 521 | 527 | 533 | 540 | 548 | 555 | 562 | 569 | 574 | 580 | 586 | 593 | 600 | 605 | 613 | 621 | 626 | 632 | 640 | 648 | 654 | 659 | 667 | 673 | 679
77 | 1.7765 | 11 | 33 | 74 | 117 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 3 | 6 | 12 | 19 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 10 | 15 | 21 | 29 | 34 | 42 | 49 | 57 | 63 | 70 | 75 | 82 | 89 | 94 | 101 | 106 | 114 | 120 | 128 | 135 | 140 | 145 | 152 | 159 | 164 | 169 | 177 | 182 | 187 | 194 | 201 | 209 | 214 | 219 | 227 | 235 | 241 | 247 | 252 | 257 | 264 | 272 | 277 | 284 | 290 | 298 | 306 | 314 | 321 | 328 | 336 | 341 | 349 | 357 | 365 | 372 | 379 | 384 | 390 | 396 | 401 | 407 | 415 | 420 | 427 | 435 | 442 | 449 | 456 | 461 | 467 | 473 | 481 | 488 | 494 | 501 | 506 | 512 | 519 | 527 | 532 | 537 | 543 | 549 | 554 | 559 | 566 | 571 | 577 | 582 | 589 | 597 | 602 | 609 | 614 | 621 | 627 | 632 | 640 | 648 | 655 | 663 | 669
78 | 1.8202 | 11 | 26 | 68 | 105 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 2 | 5 | 11 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 6 | 14 | 19 | 24 | 29 | 35 | 40 | 46 | 54 | 62 | 68 | 76 | 82 | 90 | 96 | 104 | 112 | 117 | 125 | 130 | 136 | 144 | 149 | 155 | 163 | 169 | 175 | 182 | 189 | 196 | 203 | 211 | 217 | 225 | 231 | 237 | 242 | 250 | 256 | 263 | 270 | 276 | 282 | 289 | 297 | 304 | 311 | 317 | 324 | 330 | 336 | 341 | 348 | 355 | 362 | 369 | 375 | 383 | 389 | 394 | 399 | 406 | 413 | 418 | 426 | 434 | 440 | 447 | 455 | 460 | 467 | 473 | 481 | 486 | 491 | 499 | 506 | 514 | 521 | 526 | 534 | 540 | 548 | 553 | 560 | 568 | 576 | 584 | 592 | 597 | 605 | 611 | 616 | 621 | 628 | 633 | 638 | 643 | 651 | 659 | 666 | 672 | 680 | 686
79 | 1.6776 | 12 | 29 | 71 | 108 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 3 | 5 | 11 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 11 | 18 | 26 | 32 | 38 | 46 | 53 | 61 | 66 | 73 | 80 | 87 | 94 | 99 | 106 | 111 | 117 | 122 | 128 | 135 | 143 | 151 | 157 | 163 | 169 | 174 | 181 | 188 | 195 | 200 | 208 | 216 | 224 | 230 | 235 | 243 | 248 | 254 | 262 | 268 | 274 | 282 | 288 | 295 | 303 | 308 | 316 | 321 | 326 | 331 | 339 | 346 | 353 | 360 | 365 | 370 | 376 | 382 | 387 | 394 | 399 | 406 | 414 | 422 | 427 | 432 | 439 | 444 | 449 | 454 | 462 | 467 | 475 | 481 | 486 | 492 | 500 | 508 | 514 | 522 | 527 | 535 | 541 | 548 | 553 | 561 | 568 | 574 | 582 | 589 | 594 | 599 | 604 | 612 | 619 | 625 | 633 | 641 | 647 | 655 | 661 | 666 | 673
80 | 1.1345 | 7 | 23 | 43 | 68 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 2 | 4 | 7 | 10 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 14 | 20 | 26 | 33 | 39 | 46 | 54 | 62 | 68 | 75 | 80 | 86 | 93 | 99 | 106 | 112 | 118 | 125 | 133 | 138 | 146 | 153 | 161 | 168 | 174 | 180 | 186 | 194 | 201 | 207 | 213 | 219 | 226 | 232 | 239 | 247 | 252 | 257 | 262 | 268 | 273 | 278 | 284 | 289 | 297 | 303 | 311 | 317 | 323 | 330 | 336 | 344 | 350 | 358 | 365 | 370 | 377 | 385 | 392 | 398 | 405 | 412 | 419 | 424 | 429 | 436 | 444 | 452 | 460 | 465 | 470 | 477 | 483 | 491 | 499 | 504 | 511 | 517 | 525 | 532 | 540 | 546 | 553 | 559 | 565 | 573 | 578 | 584 | 591 | 597 | 604 | 609 | 615 | 620 | 625 | 632 | 639 | 644 | 649 | 654 | 659 | 665 | 672
81 | 1.6495 | 12 | 34 | 76 | 126 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 2 | 5 | 12 | 19 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 16 | 24 | 30 | 36 | 42 | 49 | 56 | 62 | 68 | 74 | 79 | 85 | 92 | 97 | 104 | 111 | 118 | 126 | 132 | 140 | 147 | 153 | 160 | 166 | 172 | 177 | 183 | 190 | 196 | 201 | 207 | 213 | 221 | 228 | 236 | 242 | 247 | 252 | 258 | 264 | 271 | 276 | 284 | 292 | 297 | 302 | 307 | 313 | 318 | 326 | 331 | 339 | 346 | 354 | 360 | 367 | 375 | 381 | 388 | 394 | 400 | 407 | 413 | 421 | 427 | 433 | 438 | 446 | 452 | 457 | 465 | 472 | 480 | 488 | 495 | 502 | 509 | 516 | 521 | 528 | 536 | 541 | 547 | 553 | 559 | 567 | 574 | 581 | 586 | 591 | 599 | 604 | 611 | 617 | 622 | 628 | 633 | 639 | 644 | 652 | 660 | 668 | 676
82 | 1.1843 | 11 | 27 | 57 | 87 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 5 | 9 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 11 | 17 | 25 | 32 | 40 | 48 | 54 | 59 | 64 | 72 | 79 | 86 | 93 | 98 | 104 | 110 | 116 | 121 | 127 | 132 | 140 | 146 | 151 | 156 | 161 | 169 | 174 | 179 | 187 | 194 | 199 | 205 | 213 | 219 | 226 | 234 | 241 | 246 | 254 | 259 | 267 | 272 | 280 | 286 | 294 | 299 | 306 | 312 | 320 | 326 | 332 | 339 | 347 | 354 | 361 | 369 | 374 | 379 | 385 | 391 | 398 | 406 | 414 | 420 | 428 | 434 | 439 | 445 | 453 | 460 | 465 | 473 | 480 | 487 | 495 | 500 | 505 | 510 | 515 | 520 | 526 | 532 | 537 | 542 | 549 | 556 | 563 | 568 | 574 | 582 | 589 | 597 | 605 | 613 | 619 | 626 | 633 | 641 | 649 | 655 | 663 | 670 | 675
83 | 1.1879 | 9 | 20 | 42 | 67 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 3 | 8 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 7 | 13 | 20 | 26 | 31 | 36 | 41 | 48 | 53 | 60 | 67 | 73 | 79 | 86 | 92 | 100 | 107 | 114 | 122 | 128 | 133 | 140 | 145 | 150 | 157 | 164 | 169 | 177 | 182 | 187 | 192 | 197 | 202 | 210 | 216 | 224 | 232 | 237 | 242 | 248 | 256 | 263 | 269 | 276 | 284 | 290 | 295 | 301 | 307 | 312 | 319 | 327 | 335 | 343 | 351 | 357 | 362 | 369 | 377 | 383 | 388 | 394 | 400 | 405 | 412 | 419 | 426 | 434 | 440 | 445 | 452 | 458 | 464 | 469 | 476 | 482 | 490 | 498 | 503 | 511 | 519 | 527 | 533 | 539 | 544 | 551 | 559 | 564 | 572 | 577 | 585 | 592 | 600 | 606 | 612 | 620 | 628 | 634 | 641 | 646 | 654 | 660 | 665 | 671
84 | 1.159 | 12 | 23 | 46 | 70 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 4 | 7 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 13 | 21 | 27 | 35 | 41 | 48 | 56 | 62 | 69 | 76 | 84 | 92 | 98 | 104 | 111 | 117 | 123 | 129 | 135 | 141 | 147 | 154 | 159 | 167 | 174 | 181 | 189 | 196 | 202 | 209 | 214 | 220 | 225 | 233 | 238 | 244 | 250 | 258 | 266 | 272 | 278 | 284 | 292 | 300 | 308 | 316 | 324 | 332 | 340 | 346 | 353 | 361 | 368 | 374 | 379 | 387 | 392 | 400 | 406 | 412 | 420 | 427 | 432 | 439 | 444 | 451 | 459 | 464 | 469 | 476 | 482 | 488 | 494 | 499 | 506 | 511 | 516 | 521 | 527 | 534 | 542 | 548 | 556 | 562 | 569 | 574 | 582 | 590 | 596 | 604 | 611 | 616 | 622 | 627 | 635 | 641 | 646 | 653 | 658 | 664 | 671 | 678 | 684
85 | 1.5732 | 12 | 35 | 59 | 94 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 2 | 6 | 10 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 15 | 23 | 28 | 34 | 40 | 46 | 53 | 58 | 66 | 73 | 80 | 88 | 95 | 100 | 107 | 114 | 122 | 130 | 137 | 145 | 151 | 159 | 166 | 174 | 181 | 186 | 194 | 200 | 205 | 211 | 218 | 224 | 229 | 235 | 240 | 246 | 253 | 260 | 268 | 275 | 282 | 287 | 292 | 299 | 304 | 312 | 317 | 324 | 329 | 337 | 345 | 351 | 357 | 365 | 370 | 377 | 382 | 387 | 393 | 400 | 405 | 412 | 417 | 423 | 430 | 438 | 446 | 453 | 459 | 466 | 472 | 480 | 486 | 492 | 497 | 505 | 511 | 518 | 526 | 534 | 540 | 545 | 550 | 555 | 563 | 570 | 577 | 582 | 589 | 594 | 599 | 604 | 611 | 619 | 624 | 629 | 637 | 645 | 650 | 658 | 666 | 673 | 681
86 | 1.9781 | 12 | 34 | 82 | 140 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 3 | 6 | 14 | 22 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 11 | 17 | 23 | 28 | 36 | 43 | 48 | 54 | 61 | 66 | 73 | 81 | 88 | 94 | 101 | 108 | 115 | 120 | 126 | 134 | 141 | 149 | 155 | 161 | 169 | 177 | 183 | 188 | 195 | 203 | 211 | 218 | 223 | 231 | 238 | 246 | 252 | 258 | 265 | 270 | 277 | 284 | 291 | 298 | 306 | 313 | 319 | 327 | 333 | 339 | 344 | 349 | 354 | 360 | 367 | 374 | 381 | 387 | 393 | 399 | 405 | 413 | 421 | 428 | 435 | 440 | 446 | 454 | 461 | 467 | 472 | 479 | 484 | 492 | 498 | 504 | 512 | 519 | 524 | 530 | 538 | 545 | 551 | 556 | 563 | 571 | 577 | 585 | 591 | 599 | 607 | 615 | 622 | 630 | 638 | 646 | 653 | 658 | 665 | 672 | 680 | 687 | 693
87 | 1.3301 | 10 | 29 | 60 | 100 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 2 | 5 | 10 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 14 | 19 | 27 | 32 | 37 | 43 | 50 | 55 | 61 | 69 | 75 | 80 | 87 | 92 | 100 | 107 | 112 | 117 | 122 | 128 | 133 | 139 | 144 | 149 | 157 | 165 | 170 | 178 | 185 | 191 | 199 | 206 | 214 | 222 | 228 | 233 | 238 | 245 | 251 | 259 | 265 | 273 | 280 | 285 | 292 | 299 | 307 | 315 | 321 | 329 | 337 | 344 | 351 | 358 | 363 | 371 | 376 | 382 | 387 | 392 | 398 | 406 | 412 | 420 | 427 | 435 | 440 | 447 | 452 | 457 | 464 | 469 | 475 | 480 | 486 | 492 | 500 | 508 | 516 | 521 | 527 | 533 | 538 | 545 | 553 | 561 | 566 | 571 | 576 | 582 | 590 | 597 | 603 | 609 | 616 | 624 | 632 | 639 | 644 | 650 | 658 | 664 | 672
88 | 1.8019 | 10 | 34 | 71 | 113 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 2 | 6 | 11 | 18 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 10 | 17 | 25 | 33 | 39 | 47 | 53 | 61 | 66 | 74 | 79 | 87 | 92 | 100 | 105 | 110 | 118 | 123 | 128 | 133 | 138 | 144 | 151 | 159 | 167 | 173 | 180 | 187 | 192 | 200 | 208 | 213 | 219 | 224 | 229 | 234 | 240 | 245 | 252 | 257 | 263 | 268 | 273 | 280 | 287 | 294 | 302 | 307 | 315 | 323 | 328 | 335 | 340 | 346 | 353 | 360 | 368 | 373 | 379 | 384 | 392 | 399 | 404 | 411 | 417 | 424 | 429 | 436 | 441 | 449 | 456 | 462 | 467 | 474 | 481 | 488 | 495 | 501 | 506 | 514 | 522 | 530 | 537 | 545 | 551 | 559 | 564 | 570 | 575 | 581 | 589 | 595 | 602 | 610 | 616 | 623 | 631 | 637 | 642 | 649 | 655 | 661 | 668
89 | 1.662 | 17 | 34 | 76 | 120 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 3 | 6 | 14 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 14 | 21 | 26 | 32 | 37 | 42 | 47 | 52 | 57 | 64 | 69 | 75 | 81 | 87 | 93 | 100 | 105 | 112 | 120 | 126 | 132 | 137 | 142 | 150 | 158 | 164 | 172 | 180 | 185 | 191 | 196 | 202 | 209 | 214 | 222 | 227 | 235 | 241 | 247 | 255 | 263 | 269 | 276 | 283 | 290 | 297 | 305 | 311 | 319 | 324 | 332 | 339 | 345 | 353 | 358 | 365 | 372 | 380 | 387 | 395 | 400 | 408 | 413 | 420 | 427 | 434 | 439 | 446 | 453 | 460 | 467 | 473 | 481 | 487 | 495 | 501 | 508 | 514 | 522 | 527 | 535 | 542 | 548 | 555 | 561 | 568 | 576 | 583 | 591 | 596 | 604 | 609 | 614 | 621 | 628 | 633 | 641 | 647 | 653 | 660 | 667 | 672 | 679
90 | 1.7162 | 16 | 37 | 75 | 112 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 3 | 6 | 12 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 7 | 12 | 19 | 26 | 31 | 39 | 47 | 54 | 59 | 65 | 72 | 77 | 85 | 93 | 98 | 106 | 112 | 119 | 127 | 134 | 139 | 146 | 152 | 157 | 165 | 170 | 175 | 180 | 188 | 195 | 202 | 207 | 213 | 221 | 229 | 237 | 244 | 249 | 255 | 263 | 271 | 278 | 283 | 289 | 297 | 303 | 310 | 316 | 322 | 329 | 334 | 342 | 348 | 355 | 361 | 366 | 374 | 379 | 387 | 394 | 399 | 407 | 415 | 421 | 427 | 433 | 438 | 444 | 449 | 455 | 462 | 469 | 476 | 484 | 489 | 494 | 499 | 507 | 513 | 519 | 525 | 531 | 536 | 542 | 547 | 555 | 561 | 568 | 575 | 581 | 586 | 594 | 599 | 604 | 612 | 617 | 622 | 628 | 634 | 640 | 645 | 653 | 658 | 664
91 | 1.5006 | 8 | 31 | 56 | 87 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 1 | 5 | 9 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 15 | 22 | 28 | 33 | 39 | 46 | 53 | 61 | 67 | 74 | 81 | 87 | 94 | 99 | 106 | 112 | 117 | 122 | 130 | 135 | 142 | 150 | 156 | 163 | 168 | 173 | 181 | 189 | 194 | 200 | 206 | 212 | 217 | 223 | 230 | 235 | 243 | 249 | 257 | 265 | 272 | 280 | 287 | 294 | 299 | 307 | 315 | 322 | 328 | 333 | 340 | 347 | 352 | 359 | 365 | 371 | 378 | 383 | 388 | 394 | 402 | 410 | 416 | 424 | 432 | 438 | 443 | 450 | 457 | 463 | 470 | 478 | 486 | 491 | 498 | 505 | 510 | 517 | 523 | 531 | 538 | 546 | 554 | 562 | 569 | 576 | 584 | 590 | 597 | 605 | 611 | 617 | 622 | 628 | 633 | 640 | 647 | 653 | 661 | 667 | 672 | 680 | 685
92 | 1.3285 | 14 | 32 | 63 | 103 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 3 | 6 | 10 | 16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 7 | 13 | 21 | 26 | 31 | 39 | 45 | 52 | 57 | 63 | 71 | 78 | 84 | 91 | 99 | 106 | 113 | 120 | 128 | 133 | 139 | 146 | 151 | 156 | 161 | 167 | 175 | 183 | 190 | 196 | 202 | 210 | 215 | 220 | 227 | 232 | 237 | 244 | 250 | 255 | 261 | 267 | 272 | 278 | 284 | 290 | 295 | 303 | 308 | 315 | 321 | 328 | 333 | 339 | 344 | 352 | 359 | 366 | 373 | 378 | 384 | 392 | 399 | 406 | 412 | 417 | 422 | 429 | 436 | 443 | 450 | 457 | 464 | 470 | 476 | 482 | 490 | 497 | 503 | 509 | 515 | 523 | 531 | 539 | 547 | 554 | 559 | 567 | 572 | 579 | 587 | 595 | 601 | 608 | 615 | 622 | 627 | 634 | 641 | 649 | 654 | 660 | 668 | 674
93 | 1.5888 | 8 | 26 | 57 | 96 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 2 | 5 | 10 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 10 | 15 | 22 | 27 | 33 | 38 | 45 | 51 | 58 | 63 | 71 | 76 | 84 | 90 | 96 | 102 | 109 | 117 | 122 | 130 | 138 | 144 | 152 | 157 | 164 | 170 | 178 | 185 | 192 | 198 | 206 | 213 | 220 | 227 | 234 | 239 | 247 | 254 | 262 | 268 | 275 | 280 | 285 | 293 | 299 | 304 | 311 | 318 | 324 | 329 | 337 | 344 | 349 | 356 | 362 | 368 | 376 | 382 | 389 | 397 | 402 | 407 | 413 | 421 | 428 | 435 | 441 | 448 | 455 | 460 | 467 | 475 | 481 | 486 | 491 | 499 | 505 | 513 | 521 | 528 | 534 | 542 | 549 | 554 | 559 | 564 | 572 | 579 | 587 | 595 | 602 | 610 | 615 | 621 | 626 | 632 | 637 | 644 | 649 | 657 | 664 | 670 | 677
94 | 1.4289 | 11 | 24 | 50 | 86 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 4 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 13 | 19 | 24 | 30 | 35 | 40 | 48 | 56 | 61 | 67 | 74 | 82 | 88 | 94 | 99 | 104 | 110 | 118 | 125 | 131 | 138 | 145 | 151 | 157 | 162 | 168 | 175 | 183 | 190 | 198 | 206 | 211 | 218 | 225 | 230 | 235 | 242 | 247 | 252 | 257 | 262 | 267 | 274 | 282 | 288 | 296 | 304 | 311 | 316 | 322 | 329 | 337 | 344 | 352 | 360 | 367 | 375 | 382 | 390 | 396 | 404 | 409 | 415 | 422 | 429 | 434 | 441 | 449 | 457 | 465 | 470 | 478 | 486 | 494 | 502 | 509 | 515 | 521 | 526 | 532 | 538 | 543 | 549 | 555 | 562 | 569 | 575 | 581 | 587 | 595 | 602 | 607 | 612 | 619 | 627 | 632 | 637 | 642 | 649 | 654 | 660 | 668 | 674
95 | 1.0467 | 10 | 21 | 38 | 59 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 2 | 4 | 6 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 7 | 12 | 20 | 28 | 33 | 38 | 45 | 53 | 59 | 64 | 69 | 76 | 81 | 87 | 93 | 98 | 104 | 112 | 119 | 124 | 130 | 136 | 141 | 146 | 153 | 160 | 166 | 174 | 180 | 185 | 190 | 195 | 202 | 209 | 214 | 219 | 225 | 230 | 236 | 241 | 248 | 254 | 260 | 265 | 270 | 275 | 282 | 290 | 295 | 302 | 310 | 317 | 322 | 330 | 338 | 344 | 350 | 357 | 364 | 372 | 379 | 387 | 394 | 401 | 408 | 416 | 423 | 428 | 435 | 441 | 448 | 454 | 461 | 467 | 475 | 480 | 486 | 494 | 499 | 506 | 514 | 520 | 527 | 532 | 540 | 545 | 550 | 555 | 560 | 568 | 575 | 583 | 589 | 596 | 601 | 609 | 616 | 623 | 630 | 638 | 645 | 651 | 657 | 662
96 | 1.4947 | 9 | 30 | 65 | 107 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 2 | 5 | 11 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 14 | 20 | 28 | 33 | 40 | 46 | 51 | 58 | 63 | 68 | 73 | 80 | 87 | 94 | 100 | 108 | 116 | 124 | 129 | 136 | 142 | 149 | 157 | 163 | 171 | 178 | 186 | 192 | 197 | 202 | 209 | 215 | 221 | 228 | 234 | 242 | 250 | 256 | 261 | 267 | 275 | 283 | 291 | 297 | 304 | 311 | 318 | 325 | 330 | 336 | 344 | 349 | 354 | 361 | 366 | 371 | 377 | 385 | 393 | 398 | 404 | 411 | 418 | 425 | 433 | 441 | 446 | 451 | 456 | 463 | 469 | 477 | 485 | 491 | 496 | 501 | 508 | 515 | 521 | 529 | 536 | 543 | 549 | 557 | 563 | 568 | 576 | 584 | 590 | 597 | 605 | 610 | 618 | 626 | 632 | 638 | 645 | 652 | 658 | 663 | 669 | 677 | 682
97 | 1.6616 | 17 | 39 | 76 | 125 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 3 | 7 | 13 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 6 | 12 | 17 | 24 | 29 | 35 | 41 | 46 | 51 | 58 | 63 | 69 | 77 | 83 | 88 | 94 | 99 | 105 | 111 | 117 | 124 | 131 | 139 | 145 | 153 | 159 | 166 | 173 | 179 | 186 | 193 | 201 | 206 | 213 | 219 | 227 | 234 | 241 | 249 | 255 | 263 | 268 | 273 | 281 | 288 | 296 | 304 | 311 | 317 | 323 | 331 | 336 | 341 | 347 | 354 | 361 | 368 | 374 | 380 | 385 | 390 | 398 | 404 | 411 | 419 | 427 | 432 | 439 | 445 | 452 | 460 | 465 | 470 | 477 | 483 | 490 | 496 | 503 | 509 | 516 | 521 | 527 | 533 | 540 | 546 | 552 | 560 | 568 | 574 | 579 | 586 | 593 | 600 | 606 | 611 | 616 | 623 | 628 | 634 | 641 | 648 | 656 | 661 | 668
98 | 1.7106 | 14 | 37 | 79 | 124 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 3 | 7 | 13 | 21 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 12 | 20 | 25 | 30 | 36 | 42 | 49 | 55 | 62 | 69 | 74 | 80 | 87 | 93 | 98 | 104 | 111 | 117 | 123 | 128 | 134 | 139 | 145 | 151 | 157 | 165 | 170 | 176 | 183 | 188 | 193 | 199 | 204 | 212 | 220 | 227 | 234 | 242 | 250 | 257 | 265 | 273 | 281 | 289 | 294 | 300 | 308 | 315 | 320 | 325 | 333 | 339 | 344 | 350 | 355 | 363 | 368 | 373 | 381 | 388 | 395 | 401 | 407 | 413 | 418 | 423 | 429 | 436 | 444 | 451 | 456 | 461 | 469 | 475 | 482 | 489 | 497 | 504 | 509 | 514 | 520 | 527 | 533 | 538 | 543 | 551 | 557 | 564 | 569 | 576 | 581 | 586 | 593 | 600 | 606 | 613 | 620 | 628 | 633 | 640 | 645 | 653 | 658
99 | 1.5165 | 8 | 25 | 51 | 86 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 2 | 4 | 8 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 13 | 21 | 28 | 35 | 41 | 46 | 54 | 62 | 68 | 73 | 79 | 87 | 92 | 100 | 106 | 112 | 118 | 124 | 131 | 138 | 144 | 149 | 157 | 162 | 167 | 172 | 177 | 185 | 191 | 199 | 206 | 213 | 218 | 225 | 231 | 238 | 244 | 250 | 257 | 263 | 268 | 276 | 282 | 290 | 298 | 305 | 310 | 316 | 324 | 332 | 340 | 345 | 353 | 360 | 365 | 372 | 380 | 388 | 395 | 401 | 408 | 414 | 419 | 424 | 430 | 435 | 443 | 451 | 458 | 465 | 472 | 479 | 485 | 491 | 499 | 505 | 512 | 518 | 526 | 531 | 539 | 545 | 553 | 560 | 568 | 574 | 580 | 585 | 591 | 599 | 605 | 612 | 620 | 627 | 633 | 640 | 646 | 651 | 657 | 664 | 672 | 679 | 687
100 | 1.899 | 18 | 45 | 82 | 130 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 4 | 8 | 13 | 20 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 5 | 11 | 17 | 22 | 28 | 36 | 44 | 52 | 58 | 63 | 70 | 75 | 83 | 89 | 97 | 104 | 109 | 116 | 123 | 131 | 138 | 143 | 149 | 155 | 162 | 169 | 175 | 180 | 187 | 192 | 199 | 204 | 209 | 214 | 221 | 227 | 232 | 240 | 245 | 252 | 257 | 263 | 270 | 275 | 280 | 285 | 291 | 297 | 305 | 310 | 318 | 326 | 334 | 342 | 348 | 356 | 364 | 371 | 377 | 385 | 390 | 395 | 402 | 407 | 414 | 419 | 427 | 435 | 441 | 447 | 454 | 459 | 466 | 474 | 481 | 488 | 496 | 501 | 506 | 511 | 519 | 526 | 533 | 539 | 544 | 552 | 559 | 567 | 573 | 578 | 584 | 592 | 597 | 603 | 610 | 618 | 626 | 631 | 637 | 644 | 651 | 659 | 666 | 673
101 | 1.5995 | 12 | 30 | 61 | 93 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 5 | 10 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 13 | 20 | 28 | 33 | 41 | 47 | 52 | 60 | 65 | 70 | 78 | 84 | 91 | 99 | 107 | 114 | 121 | 128 | 136 | 141 | 149 | 156 | 163 | 169 | 176 | 181 | 188 | 193 | 201 | 206 | 211 | 217 | 223 | 229 | 237 | 243 | 248 | 255 | 262 | 267 | 275 | 280 | 285 | 293 | 299 | 304 | 310 | 315 | 323 | 328 | 336 | 344 | 349 | 355 | 362 | 368 | 376 | 381 | 386 | 394 | 399 | 405 | 413 | 418 | 423 | 428 | 434 | 439 | 444 | 452 | 458 | 463 | 471 | 479 | 484 | 491 | 496 | 503 | 508 | 514 | 519 | 527 | 535 | 542 | 548 | 553 | 560 | 567 | 574 | 581 | 587 | 592 | 599 | 604 | 612 | 620 | 626 | 631 | 638 | 645 | 653 | 660 | 667
102 | 1.1275 | 11 | 24 | 52 | 75 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 2 | 4 | 9 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 14 | 20 | 27 | 32 | 40 | 46 | 51 | 58 | 66 | 74 | 81 | 88 | 96 | 104 | 110 | 115 | 123 | 128 | 135 | 141 | 149 | 156 | 162 | 167 | 172 | 180 | 188 | 195 | 201 | 209 | 215 | 220 | 225 | 230 | 236 | 243 | 251 | 259 | 267 | 273 | 279 | 285 | 292 | 297 | 303 | 310 | 317 | 325 | 333 | 338 | 343 | 348 | 353 | 358 | 364 | 371 | 379 | 385 | 392 | 400 | 407 | 412 | 419 | 426 | 434 | 442 | 447 | 453 | 461 | 466 | 471 | 477 | 484 | 492 | 499 | 505 | 513 | 518 | 525 | 530 | 536 | 542 | 550 | 555 | 561 | 567 | 573 | 580 | 588 | 595 | 602 | 610 | 617 | 624 | 631 | 637 | 645 | 650 | 656 | 663 | 671 | 678 | 686
103 | 1.1318 | 8 | 23 | 43 | 70 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 2 | 4 | 6 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 6 | 14 | 22 | 29 | 35 | 43 | 51 | 59 | 67 | 74 | 79 | 84 | 89 | 96 | 104 | 109 | 115 | 120 | 128 | 133 | 140 | 148 | 155 | 162 | 168 | 176 | 184 | 189 | 197 | 205 | 210 | 215 | 222 | 228 | 235 | 241 | 247 | 253 | 259 | 265 | 271 | 278 | 283 | 290 | 296 | 301 | 309 | 314 | 322 | 327 | 334 | 340 | 346 | 352 | 357 | 365 | 373 | 380 | 386 | 394 | 400 | 406 | 412 | 418 | 426 | 431 | 439 | 447 | 454 | 459 | 466 | 474 | 481 | 487 | 492 | 497 | 505 | 512 | 518 | 523 | 529 | 536 | 542 | 549 | 555 | 563 | 568 | 574 | 580 | 587 | 593 | 600 | 608 | 616 | 623 | 628 | 633 | 638 | 646 | 651 | 658 | 663 | 668 | 673
104 | 1.3267 | 10 | 22 | 50 | 89 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 3 | 8 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 14 | 22 | 29 | 37 | 43 | 49 | 54 | 62 | 70 | 78 | 86 | 94 | 102 | 109 | 114 | 120 | 125 | 130 | 137 | 142 | 149 | 157 | 162 | 169 | 177 | 185 | 190 | 198 | 203 | 208 | 216 | 223 | 228 | 235 | 242 | 249 | 256 | 261 | 268 | 273 | 281 | 288 | 294 | 299 | 304 | 311 | 319 | 325 | 331 | 336 | 344 | 349 | 357 | 363 | 369 | 376 | 382 | 389 | 394 | 400 | 405 | 410 | 418 | 425 | 432 | 440 | 446 | 452 | 457 | 463 | 468 | 474 | 482 | 490 | 496 | 504 | 511 | 518 | 524 | 530 | 535 | 541 | 546 | 552 | 557 | 564 | 572 | 578 | 583 | 590 | 598 | 604 | 612 | 620 | 628 | 636 | 643 | 650 | 655 | 660 | 665 | 672 | 678
105 | 1.1195 | 6 | 17 | 38 | 63 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 1 | 3 | 6 | 11 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 15 | 21 | 27 | 33 | 38 | 44 | 51 | 56 | 62 | 69 | 77 | 83 | 88 | 93 | 101 | 108 | 114 | 120 | 126 | 134 | 139 | 144 | 149 | 155 | 162 | 168 | 174 | 179 | 185 | 191 | 198 | 203 | 209 | 215 | 222 | 230 | 235 | 241 | 246 | 253 | 260 | 265 | 273 | 278 | 283 | 290 | 296 | 303 | 311 | 316 | 323 | 330 | 338 | 346 | 353 | 360 | 365 | 370 | 375 | 381 | 389 | 395 | 402 | 408 | 414 | 419 | 427 | 435 | 442 | 447 | 452 | 458 | 465 | 473 | 479 | 484 | 491 | 498 | 504 | 512 | 517 | 524 | 532 | 538 | 544 | 552 | 559 | 566 | 571 | 579 | 586 | 593 | 601 | 608 | 615 | 622 | 627 | 633 | 641 | 648 | 655 | 662 | 670
106 | 1.5075 | 16 | 30 | 59 | 94 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 3 | 5 | 10 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 14 | 22 | 28 | 33 | 38 | 43 | 50 | 55 | 62 | 70 | 78 | 85 | 90 | 97 | 102 | 110 | 118 | 123 | 128 | 133 | 139 | 147 | 153 | 159 | 166 | 173 | 181 | 189 | 195 | 202 | 210 | 215 | 222 | 227 | 235 | 243 | 249 | 255 | 262 | 269 | 275 | 280 | 285 | 290 | 295 | 300 | 307 | 313 | 319 | 326 | 333 | 340 | 348 | 356 | 361 | 367 | 373 | 378 | 384 | 390 | 397 | 403 | 409 | 414 | 422 | 429 | 436 | 443 | 450 | 456 | 461 | 468 | 474 | 481 | 487 | 494 | 499 | 504 | 512 | 520 | 528 | 535 | 543 | 549 | 554 | 562 | 570 | 577 | 583 | 589 | 594 | 602 | 608 | 614 | 619 | 625 | 632 | 640 | 645 | 652 | 659 | 666 | 672
107 | 1.2859 | 11 | 22 | 42 | 71 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 3 | 6 | 11 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 16 | 23 | 30 | 35 | 43 | 48 | 53 | 61 | 66 | 74 | 79 | 84 | 91 | 98 | 104 | 111 | 116 | 121 | 126 | 131 | 139 | 146 | 154 | 162 | 170 | 178 | 186 | 194 | 201 | 207 | 215 | 222 | 230 | 235 | 240 | 245 | 252 | 258 | 265 | 270 | 275 | 283 | 290 | 296 | 304 | 309 | 314 | 321 | 328 | 335 | 342 | 347 | 355 | 361 | 366 | 371 | 378 | 385 | 393 | 400 | 405 | 410 | 416 | 421 | 426 | 431 | 438 | 444 | 451 | 457 | 462 | 467 | 472 | 477 | 485 | 492 | 500 | 508 | 515 | 523 | 530 | 537 | 544 | 551 | 558 | 566 | 572 | 577 | 582 | 589 | 595 | 603 | 611 | 618 | 624 | 632 | 639 | 644 | 650 | 658 | 664 | 672 | 679
108 | 1.8699 | 15 | 30 | 64 | 102 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 3 | 5 | 10 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 11 | 18 | 24 | 32 | 38 | 44 | 52 | 58 | 66 | 72 | 78 | 85 | 93 | 99 | 106 | 111 | 119 | 126 | 134 | 140 | 146 | 154 | 160 | 167 | 174 | 182 | 188 | 193 | 201 | 209 | 215 | 221 | 227 | 233 | 241 | 247 | 255 | 261 | 267 | 273 | 279 | 284 | 292 | 298 | 305 | 312 | 319 | 324 | 332 | 337 | 344 | 352 | 357 | 362 | 370 | 377 | 385 | 392 | 398 | 406 | 411 | 418 | 423 | 431 | 439 | 445 | 450 | 458 | 463 | 469 | 477 | 485 | 492 | 497 | 504 | 512 | 520 | 527 | 535 | 542 | 548 | 555 | 561 | 569 | 574 | 582 | 590 | 595 | 603 | 611 | 616 | 624 | 632 | 637 | 644 | 649 | 657 | 662 | 670 | 678 | 684 | 689 | 694
109 | 1.3413 | 7 | 28 | 58 | 91 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 1 | 4 | 9 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 16 | 24 | 29 | 37 | 42 | 47 | 52 | 58 | 63 | 69 | 76 | 83 | 91 | 96 | 103 | 111 | 119 | 124 | 132 | 138 | 143 | 151 | 156 | 162 | 167 | 175 | 180 | 186 | 191 | 199 | 206 | 212 | 217 | 222 | 228 | 235 | 243 | 250 | 258 | 266 | 274 | 279 | 287 | 293 | 300 | 306 | 313 | 321 | 326 | 333 | 339 | 344 | 350 | 355 | 360 | 367 | 374 | 382 | 387 | 392 | 399 | 407 | 414 | 420 | 427 | 434 | 439 | 446 | 451 | 459 | 466 | 472 | 480 | 488 | 494 | 501 | 507 | 514 | 520 | 528 | 536 | 543 | 550 | 556 | 561 | 568 | 576 | 581 | 586 | 591 | 597 | 605 | 610 | 615 | 623 | 631 | 637 | 642 | 648 | 653 | 658 | 664 | 672
110 | 1.0912 | 7 | 22 | 45 | 68 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 2 | 4 | 7 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 6 | 14 | 21 | 27 | 35 | 43 | 48 | 54 | 61 | 66 | 73 | 80 | 88 | 96 | 103 | 110 | 115 | 120 | 127 | 135 | 143 | 148 | 155 | 160 | 167 | 175 | 180 | 186 | 192 | 197 | 202 | 208 | 213 | 220 | 227 | 235 | 241 | 249 | 256 | 261 | 267 | 272 | 277 | 285 | 292 | 298 | 306 | 312 | 320 | 325 | 330 | 337 | 345 | 353 | 361 | 366 | 373 | 378 | 385 | 390 | 396 | 402 | 408 | 413 | 421 | 429 | 436 | 441 | 447 | 452 | 457 | 464 | 471 | 478 | 485 | 492 | 497 | 504 | 509 | 517 | 524 | 531 | 538 | 543 | 551 | 559 | 564 | 572 | 578 | 583 | 590 | 596 | 603 | 609 | 615 | 621 | 629 | 637 | 643 | 651 | 657 | 665 | 671 | 676
111 | 1.0802 | 9 | 20 | 37 | 70 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 3 | 6 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 6 | 13 | 20 | 27 | 34 | 42 | 49 | 55 | 61 | 67 | 73 | 81 | 86 | 91 | 96 | 101 | 109 | 117 | 122 | 129 | 135 | 141 | 148 | 154 | 159 | 167 | 174 | 180 | 185 | 191 | 199 | 207 | 213 | 220 | 228 | 236 | 244 | 250 | 256 | 264 | 270 | 276 | 283 | 288 | 294 | 300 | 305 | 312 | 319 | 325 | 330 | 336 | 344 | 349 | 355 | 363 | 371 | 377 | 382 | 389 | 394 | 401 | 408 | 413 | 418 | 423 | 431 | 439 | 445 | 452 | 460 | 467 | 472 | 477 | 485 | 492 | 498 | 506 | 511 | 516 | 524 | 529 | 534 | 539 | 546 | 552 | 560 | 567 | 573 | 578 | 583 | 589 | 594 | 599 | 604 | 610 | 618 | 623 | 631 | 639 | 647 | 654 | 662 | 669
112 | 1.6246 | 17 | 30 | 56 | 97 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 3 | 5 | 9 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 15 | 21 | 26 | 32 | 38 | 46 | 54 | 62 | 67 | 72 | 79 | 85 | 90 | 96 | 103 | 108 | 116 | 121 | 129 | 137 | 143 | 151 | 157 | 163 | 168 | 173 | 178 | 184 | 191 | 199 | 207 | 213 | 221 | 229 | 234 | 242 | 249 | 254 | 260 | 267 | 273 | 278 | 285 | 292 | 300 | 307 | 312 | 317 | 325 | 330 | 337 | 344 | 352 | 357 | 363 | 368 | 376 | 384 | 389 | 396 | 401 | 407 | 412 | 418 | 425 | 431 | 436 | 444 | 451 | 456 | 461 | 466 | 473 | 480 | 485 | 490 | 496 | 502 | 507 | 513 | 519 | 527 | 532 | 538 | 546 | 554 | 559 | 565 | 573 | 581 | 586 | 591 | 596 | 603 | 611 | 618 | 625 | 633 | 641 | 647 | 652 | 659 | 665
113 | 1.4282 | 10 | 22 | 58 | 97 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 2 | 4 | 10 | 15 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 12 | 20 | 25 | 30 | 35 | 43 | 50 | 55 | 62 | 69 | 75 | 82 | 90 | 98 | 105 | 113 | 119 | 124 | 131 | 137 | 143 | 150 | 158 | 165 | 172 | 179 | 186 | 191 | 196 | 201 | 207 | 212 | 219 | 226 | 231 | 237 | 242 | 248 | 255 | 263 | 271 | 277 | 282 | 290 | 297 | 303 | 311 | 316 | 322 | 327 | 333 | 340 | 348 | 356 | 362 | 367 | 374 | 382 | 388 | 396 | 401 | 406 | 411 | 419 | 424 | 432 | 439 | 447 | 455 | 461 | 469 | 474 | 480 | 485 | 493 | 498 | 503 | 510 | 518 | 526 | 531 | 536 | 541 | 547 | 553 | 560 | 568 | 576 | 582 | 589 | 597 | 603 | 610 | 615 | 620 | 628 | 633 | 639 | 647 | 653 | 660 | 668 | 674
114 | 1.4709 | 12 | 33 | 60 | 100 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 2 | 5 | 10 | 16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 13 | 20 | 27 | 35 | 42 | 47 | 52 | 58 | 63 | 70 | 77 | 83 | 89 | 94 | 100 | 105 | 113 | 121 | 129 | 134 | 141 | 149 | 154 | 161 | 169 | 176 | 181 | 188 | 196 | 203 | 211 | 217 | 225 | 232 | 238 | 243 | 248 | 256 | 262 | 269 | 276 | 283 | 290 | 298 | 306 | 312 | 319 | 325 | 332 | 339 | 344 | 350 | 356 | 361 | 368 | 376 | 382 | 387 | 395 | 400 | 408 | 415 | 420 | 426 | 432 | 440 | 446 | 453 | 459 | 464 | 470 | 478 | 485 | 493 | 500 | 508 | 515 | 523 | 528 | 533 | 538 | 544 | 550 | 556 | 561 | 567 | 573 | 579 | 587 | 595 | 601 | 607 | 613 | 621 | 627 | 632 | 640 | 647 | 653 | 660 | 667 | 674 | 679
115 | 1.8879 | 10 | 29 | 60 | 102 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 2 | 5 | 9 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 14 | 20 | 27 | 32 | 39 | 47 | 54 | 62 | 67 | 73 | 78 | 84 | 92 | 99 | 106 | 113 | 119 | 124 | 132 | 137 | 145 | 152 | 157 | 163 | 169 | 174 | 182 | 188 | 196 | 201 | 206 | 214 | 220 | 227 | 233 | 239 | 246 | 254 | 259 | 265 | 272 | 278 | 285 | 293 | 298 | 305 | 312 | 320 | 325 | 333 | 341 | 349 | 357 | 363 | 369 | 375 | 380 | 388 | 396 | 401 | 406 | 412 | 419 | 424 | 432 | 438 | 444 | 449 | 455 | 461 | 467 | 472 | 477 | 484 | 491 | 496 | 504 | 511 | 519 | 526 | 534 | 542 | 550 | 555 | 560 | 568 | 575 | 580 | 587 | 594 | 600 | 608 | 614 | 622 | 629 | 635 | 642 | 650 | 656 | 664 | 670 | 678 | 684
116 | 1.5684 | 15 | 31 | 63 | 109 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 3 | 5 | 10 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 13 | 18 | 26 | 31 | 38 | 44 | 51 | 58 | 66 | 73 | 81 | 87 | 92 | 97 | 102 | 107 | 115 | 120 | 127 | 133 | 140 | 145 | 152 | 158 | 165 | 173 | 179 | 187 | 193 | 198 | 203 | 208 | 214 | 221 | 226 | 231 | 236 | 243 | 249 | 254 | 262 | 268 | 276 | 283 | 291 | 297 | 303 | 308 | 314 | 322 | 328 | 334 | 342 | 350 | 355 | 363 | 368 | 373 | 378 | 383 | 391 | 398 | 405 | 412 | 417 | 424 | 430 | 436 | 443 | 448 | 454 | 461 | 467 | 472 | 477 | 485 | 493 | 499 | 505 | 511 | 518 | 525 | 530 | 535 | 540 | 546 | 553 | 560 | 566 | 571 | 579 | 587 | 595 | 601 | 608 | 613 | 620 | 625 | 632 | 637 | 643 | 650 | 657
117 | 1.5331 | 8 | 21 | 60 | 103 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 1 | 3 | 9 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 16 | 22 | 29 | 34 | 42 | 50 | 57 | 65 | 71 | 76 | 82 | 90 | 97 | 102 | 107 | 115 | 123 | 129 | 134 | 139 | 145 | 153 | 158 | 163 | 170 | 177 | 182 | 189 | 194 | 200 | 207 | 213 | 219 | 224 | 229 | 234 | 239 | 244 | 251 | 259 | 267 | 275 | 282 | 287 | 293 | 299 | 307 | 315 | 320 | 326 | 333 | 341 | 349 | 354 | 360 | 368 | 376 | 383 | 389 | 396 | 402 | 410 | 415 | 420 | 427 | 432 | 439 | 445 | 453 | 461 | 468 | 473 | 481 | 489 | 496 | 504 | 512 | 519 | 524 | 530 | 535 | 543 | 549 | 557 | 565 | 570 | 577 | 584 | 589 | 596 | 601 | 609 | 615 | 622 | 628 | 634 | 639 | 644 | 650 | 656 | 662 | 668 | 676
118 | 1.9734 | 16 | 36 | 86 | 140 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 3 | 6 | 13 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 14 | 20 | 27 | 34 | 42 | 50 | 56 | 62 | 70 | 77 | 82 | 89 | 95 | 103 | 111 | 119 | 127 | 133 | 141 | 148 | 155 | 162 | 170 | 176 | 184 | 190 | 197 | 202 | 209 | 214 | 221 | 228 | 235 | 242 | 247 | 253 | 258 | 264 | 269 | 274 | 280 | 288 | 293 | 301 | 308 | 316 | 322 | 327 | 332 | 337 | 344 | 350 | 356 | 363 | 371 | 376 | 384 | 390 | 395 | 401 | 408 | 413 | 420 | 427 | 433 | 440 | 445 | 452 | 458 | 465 | 472 | 478 | 485 | 491 | 499 | 505 | 511 | 516 | 523 | 531 | 538 | 544 | 552 | 558 | 563 | 569 | 574 | 582 | 589 | 596 | 601 | 607 | 612 | 619 | 627 | 632 | 637 | 642 | 649 | 654 | 659 | 664 | 669
119 | 1.7594 | 11 | 31 | 70 | 118 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 2 | 5 | 11 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 14 | 21 | 26 | 34 | 42 | 47 | 53 | 61 | 69 | 76 | 84 | 90 | 96 | 103 | 111 | 116 | 121 | 129 | 136 | 143 | 151 | 156 | 163 | 168 | 175 | 183 | 189 | 195 | 203 | 210 | 215 | 222 | 228 | 236 | 243 | 250 | 257 | 262 | 269 | 277 | 285 | 293 | 299 | 306 | 312 | 320 | 327 | 333 | 338 | 345 | 350 | 356 | 361 | 367 | 375 | 381 | 389 | 395 | 403 | 408 | 415 | 423 | 429 | 436 | 441 | 448 | 455 | 463 | 469 | 474 | 481 | 486 | 493 | 501 | 506 | 514 | 521 | 527 | 532 | 537 | 543 | 551 | 556 | 563 | 571 | 577 | 583 | 589 | 597 | 602 | 608 | 613 | 620 | 625 | 630 | 637 | 643 | 648 | 655 | 663 | 669 | 675 | 681
120 | 1.0647 | 10 | 22 | 48 | 71 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 2 | 4 | 9 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 5 | 10 | 18 | 24 | 30 | 36 | 41 | 47 | 52 | 58 | 63 | 71 | 77 | 84 | 91 | 96 | 103 | 111 | 119 | 125 | 133 | 138 | 143 | 148 | 153 | 160 | 167 | 172 | 178 | 186 | 192 | 199 | 204 | 211 | 216 | 221 | 227 | 234 | 240 | 245 | 252 | 258 | 263 | 268 | 275 | 280 | 287 | 294 | 299 | 304 | 309 | 316 | 323 | 328 | 334 | 341 | 347 | 354 | 361 | 369 | 376 | 384 | 391 | 396 | 401 | 408 | 416 | 422 | 430 | 436 | 444 | 450 | 455 | 461 | 467 | 474 | 479 | 484 | 492 | 500 | 508 | 513 | 519 | 527 | 534 | 542 | 550 | 557 | 564 | 572 | 578 | 583 | 588 | 596 | 604 | 611 | 618 | 623 | 629 | 636 | 643 | 651 | 658 | 666
121 | 1.6 | 13 | 36 | 73 | 112 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 2 | 6 | 11 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 16 | 22 | 27 | 32 | 39 | 45 | 53 | 60 | 67 | 75 | 82 | 88 | 93 | 100 | 107 | 114 | 122 | 130 | 137 | 144 | 152 | 157 | 163 | 170 | 175 | 183 | 191 | 198 | 204 | 209 | 215 | 222 | 230 | 235 | 240 | 245 | 250 | 256 | 261 | 267 | 275 | 280 | 285 | 291 | 296 | 304 | 312 | 317 | 322 | 330 | 338 | 343 | 348 | 353 | 359 | 366 | 372 | 379 | 384 | 391 | 399 | 407 | 412 | 419 | 426 | 432 | 438 | 443 | 450 | 455 | 462 | 470 | 476 | 482 | 490 | 495 | 500 | 505 | 510 | 516 | 521 | 529 | 534 | 540 | 547 | 553 | 559 | 564 | 571 | 576 | 582 | 587 | 593 | 599 | 607 | 615 | 620 | 628 | 636 | 644 | 650 | 655 | 662
122 | 1.9352 | 12 | 36 | 77 | 132 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 2 | 7 | 13 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 7 | 13 | 19 | 24 | 29 | 34 | 41 | 49 | 55 | 61 | 68 | 75 | 81 | 88 | 93 | 101 | 107 | 114 | 120 | 128 | 133 | 138 | 144 | 151 | 157 | 163 | 168 | 176 | 184 | 192 | 199 | 206 | 211 | 217 | 223 | 230 | 238 | 243 | 251 | 257 | 262 | 270 | 276 | 281 | 288 | 295 | 301 | 308 | 313 | 319 | 325 | 331 | 338 | 345 | 351 | 357 | 362 | 370 | 376 | 383 | 390 | 397 | 403 | 410 | 416 | 422 | 428 | 433 | 438 | 446 | 452 | 458 | 465 | 472 | 479 | 487 | 492 | 497 | 502 | 507 | 514 | 522 | 527 | 533 | 541 | 546 | 552 | 560 | 565 | 570 | 575 | 583 | 588 | 593 | 600 | 607 | 612 | 619 | 624 | 629 | 634 | 639 | 644 | 649
123 | 1.3477 | 13 | 26 | 47 | 87 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 3 | 5 | 8 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 12 | 19 | 24 | 29 | 37 | 42 | 49 | 54 | 61 | 68 | 73 | 79 | 87 | 95 | 101 | 109 | 115 | 122 | 129 | 137 | 144 | 152 | 157 | 162 | 167 | 173 | 178 | 184 | 192 | 198 | 203 | 211 | 219 | 225 | 232 | 237 | 244 | 249 | 254 | 260 | 267 | 273 | 281 | 288 | 295 | 302 | 310 | 316 | 323 | 330 | 338 | 345 | 350 | 357 | 364 | 372 | 377 | 383 | 389 | 396 | 403 | 408 | 414 | 422 | 428 | 435 | 443 | 448 | 454 | 459 | 464 | 470 | 478 | 486 | 491 | 497 | 503 | 509 | 517 | 522 | 528 | 536 | 543 | 551 | 556 | 561 | 566 | 573 | 578 | 583 | 589 | 597 | 605 | 613 | 619 | 627 | 632 | 639 | 645 | 653 | 658 | 663 | 668
124 | 1.3162 | 14 | 34 | 62 | 95 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 3 | 6 | 11 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 11 | 17 | 25 | 30 | 36 | 43 | 49 | 55 | 60 | 67 | 73 | 81 | 86 | 92 | 99 | 105 | 110 | 118 | 124 | 131 | 138 | 146 | 152 | 157 | 165 | 171 | 177 | 184 | 191 | 196 | 202 | 210 | 217 | 223 | 228 | 235 | 241 | 247 | 252 | 260 | 265 | 273 | 281 | 286 | 294 | 301 | 309 | 315 | 322 | 327 | 332 | 340 | 345 | 353 | 361 | 368 | 374 | 382 | 388 | 394 | 401 | 408 | 416 | 423 | 431 | 436 | 443 | 450 | 456 | 462 | 470 | 475 | 483 | 488 | 494 | 502 | 509 | 514 | 521 | 529 | 536 | 544 | 550 | 556 | 564 | 572 | 577 | 583 | 589 | 594 | 599 | 604 | 609 | 616 | 622 | 629 | 636 | 642 | 648 | 654 | 659 | 664 | 670
125 | 1.939 | 20 | 48 | 83 | 138 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 201 | 4 | 8 | 13 | 22 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 7 | 12 | 18 | 26 | 31 | 38 | 46 | 54 | 60 | 67 | 72 | 79 | 84 | 89 | 95 | 101 | 107 | 114 | 122 | 129 | 137 | 145 | 152 | 160 | 167 | 175 | 182 | 190 | 197 | 204 | 210 | 216 | 224 | 232 | 239 | 246 | 254 | 262 | 269 | 277 | 285 | 291 | 297 | 303 | 308 | 315 | 323 | 330 | 336 | 342 | 350 | 355 | 362 | 368 | 373 | 379 | 386 | 394 | 401 | 408 | 414 | 421 | 428 | 433 | 440 | 448 | 454 | 462 | 468 | 476 | 483 | 490 | 497 | 505 | 512 | 517 | 524 | 530 | 537 | 544 | 552 | 559 | 566 | 572 | 580 | 587 | 592 | 599 | 606 | 614 | 620 | 626 | 631 | 637 | 644 | 650 | 655 | 662 | 670 | 678 | 685 | 693 | 701 | 708
126 | 1.3697 | 13 | 27 | 48 | 85 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 2 | 5 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 14 | 19 | 24 | 31 | 37 | 44 | 52 | 58 | 66 | 74 | 81 | 89 | 94 | 100 | 106 | 112 | 118 | 125 | 133 | 141 | 147 | 155 | 163 | 170 | 177 | 182 | 189 | 194 | 202 | 208 | 213 | 218 | 224 | 231 | 236 | 241 | 248 | 253 | 259 | 266 | 273 | 280 | 285 | 293 | 298 | 306 | 314 | 319 | 325 | 331 | 339 | 344 | 351 | 356 | 361 | 368 | 373 | 379 | 387 | 393 | 398 | 404 | 411 | 417 | 422 | 427 | 434 | 442 | 449 | 457 | 462 | 470 | 477 | 485 | 493 | 501 | 506 | 512 | 518 | 524 | 531 | 537 | 545 | 552 | 557 | 563 | 568 | 576 | 582 | 589 | 596 | 604 | 611 | 618 | 626 | 632 | 640 | 648 | 655 | 662 | 670 | 678 | 685
127 | 1.5852 | 16 | 36 | 71 | 108 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 3 | 6 | 11 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 14 | 20 | 26 | 32 | 39 | 46 | 52 | 60 | 65 | 72 | 77 | 83 | 90 | 96 | 101 | 106 | 111 | 116 | 124 | 129 | 137 | 144 | 152 | 157 | 163 | 168 | 174 | 181 | 187 | 195 | 201 | 206 | 213 | 219 | 224 | 231 | 239 | 246 | 251 | 258 | 266 | 274 | 282 | 290 | 295 | 300 | 307 | 314 | 319 | 326 | 334 | 339 | 346 | 354 | 362 | 369 | 377 | 383 | 388 | 396 | 401 | 406 | 412 | 417 | 423 | 429 | 434 | 442 | 447 | 455 | 461 | 466 | 472 | 478 | 483 | 490 | 496 | 502 | 508 | 513 | 520 | 528 | 536 | 544 | 552 | 557 | 563 | 570 | 577 | 583 | 588 | 594 | 602 | 610 | 616 | 621 | 626 | 632 | 639 | 646 | 654 | 659 | 665
128 | 1.2557 | 11 | 24 | 48 | 84 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 2 | 4 | 8 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 13 | 20 | 26 | 31 | 36 | 43 | 51 | 56 | 64 | 70 | 77 | 82 | 87 | 92 | 100 | 108 | 114 | 122 | 127 | 132 | 140 | 147 | 155 | 161 | 168 | 175 | 183 | 191 | 198 | 204 | 210 | 217 | 224 | 229 | 235 | 243 | 248 | 256 | 263 | 271 | 279 | 286 | 294 | 300 | 305 | 311 | 317 | 324 | 332 | 337 | 345 | 353 | 361 | 369 | 377 | 384 | 389 | 396 | 404 | 410 | 417 | 424 | 429 | 437 | 444 | 450 | 455 | 460 | 468 | 474 | 482 | 488 | 495 | 503 | 510 | 515 | 520 | 527 | 534 | 540 | 545 | 553 | 560 | 565 | 572 | 580 | 588 | 594 | 601 | 607 | 614 | 621 | 626 | 631 | 639 | 644 | 651 | 656 | 661 | 666 | 672 | 677 | 684
129 | 1.3607 | 11 | 31 | 57 | 85 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 6 | 10 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 11 | 18 | 23 | 30 | 36 | 41 | 47 | 54 | 60 | 68 | 73 | 80 | 85 | 91 | 96 | 103 | 111 | 116 | 122 | 128 | 134 | 142 | 149 | 154 | 161 | 166 | 174 | 180 | 186 | 191 | 199 | 205 | 211 | 219 | 226 | 234 | 239 | 244 | 252 | 259 | 266 | 271 | 278 | 286 | 291 | 297 | 305 | 312 | 317 | 325 | 331 | 339 | 344 | 352 | 357 | 364 | 371 | 378 | 385 | 392 | 398 | 406 | 414 | 420 | 425 | 432 | 437 | 443 | 451 | 458 | 465 | 472 | 477 | 483 | 488 | 496 | 504 | 510 | 515 | 520 | 525 | 532 | 540 | 548 | 556 | 563 | 571 | 579 | 587 | 592 | 599 | 606 | 614 | 620 | 628 | 636 | 643 | 648 | 655 | 663 | 668 | 673 | 680
130 | 1.9167 | 12 | 37 | 80 | 119 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 2 | 6 | 13 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 12 | 17 | 24 | 32 | 37 | 44 | 51 | 56 | 64 | 70 | 76 | 82 | 89 | 96 | 103 | 110 | 118 | 124 | 130 | 138 | 143 | 150 | 157 | 164 | 171 | 176 | 184 | 191 | 196 | 204 | 210 | 216 | 223 | 229 | 237 | 244 | 252 | 259 | 266 | 271 | 279 | 285 | 292 | 297 | 305 | 313 | 319 | 326 | 334 | 340 | 346 | 351 | 358 | 363 | 370 | 376 | 384 | 392 | 397 | 405 | 410 | 415 | 423 | 428 | 435 | 443 | 450 | 458 | 465 | 470 | 475 | 480 | 486 | 491 | 497 | 504 | 512 | 517 | 525 | 533 | 539 | 547 | 555 | 560 | 568 | 575 | 581 | 588 | 595 | 600 | 606 | 611 | 618 | 623 | 628 | 633 | 638 | 644 | 650 | 657 | 662 | 669 | 674
131 | 1.3124 | 7 | 26 | 55 | 95 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 2 | 4 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 13 | 18 | 26 | 33 | 40 | 46 | 54 | 62 | 68 | 75 | 83 | 89 | 97 | 103 | 111 | 116 | 123 | 129 | 136 | 142 | 150 | 157 | 163 | 170 | 175 | 180 | 186 | 194 | 202 | 210 | 215 | 223 | 230 | 237 | 243 | 248 | 255 | 262 | 269 | 276 | 283 | 289 | 295 | 301 | 307 | 314 | 319 | 327 | 332 | 337 | 342 | 349 | 357 | 364 | 372 | 378 | 384 | 392 | 399 | 407 | 413 | 418 | 425 | 431 | 438 | 444 | 452 | 458 | 464 | 471 | 477 | 485 | 491 | 498 | 505 | 511 | 517 | 523 | 530 | 537 | 543 | 551 | 557 | 564 | 570 | 577 | 582 | 587 | 593 | 599 | 605 | 612 | 619 | 627 | 635 | 641 | 647 | 654 | 662 | 670 | 675 | 683 | 688
132 | 1.9673 | 18 | 48 | 88 | 136 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 3 | 9 | 15 | 23 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 7 | 12 | 18 | 23 | 28 | 35 | 40 | 46 | 54 | 60 | 66 | 73 | 79 | 85 | 93 | 98 | 105 | 112 | 117 | 123 | 130 | 135 | 141 | 147 | 153 | 159 | 167 | 173 | 179 | 186 | 194 | 202 | 207 | 213 | 220 | 227 | 235 | 243 | 248 | 256 | 264 | 269 | 276 | 283 | 288 | 293 | 299 | 306 | 314 | 321 | 327 | 335 | 340 | 347 | 352 | 358 | 365 | 370 | 378 | 386 | 393 | 399 | 404 | 409 | 416 | 423 | 430 | 437 | 445 | 450 | 455 | 463 | 469 | 475 | 481 | 489 | 495 | 501 | 506 | 514 | 522 | 529 | 535 | 540 | 547 | 552 | 559 | 565 | 570 | 575 | 581 | 587 | 592 | 598 | 605 | 611 | 619 | 626 | 634 | 639 | 645 | 651 | 659 | 664
133 | 1.5428 | 11 | 27 | 51 | 95 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 2 | 4 | 8 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 15 | 20 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 83 | 89 | 97 | 102 | 109 | 114 | 122 | 130 | 138 | 143 | 149 | 157 | 163 | 169 | 175 | 182 | 187 | 192 | 198 | 205 | 210 | 215 | 220 | 226 | 232 | 240 | 246 | 252 | 259 | 266 | 273 | 279 | 284 | 290 | 298 | 306 | 313 | 318 | 323 | 330 | 337 | 344 | 351 | 359 | 367 | 374 | 382 | 387 | 395 | 400 | 408 | 414 | 421 | 427 | 435 | 442 | 449 | 455 | 463 | 468 | 474 | 479 | 485 | 492 | 499 | 507 | 513 | 520 | 525 | 533 | 538 | 546 | 552 | 557 | 562 | 567 | 574 | 580 | 586 | 593 | 598 | 605 | 613 | 618 | 625 | 630 | 636 | 642 | 648 | 654 | 660 | 666 | 674
134 | 1.7169 | 18 | 44 | 84 | 133 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 4 | 8 | 15 | 22 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 10 | 16 | 24 | 29 | 36 | 42 | 48 | 53 | 60 | 67 | 72 | 78 | 83 | 89 | 96 | 101 | 108 | 116 | 123 | 128 | 134 | 142 | 149 | 155 | 163 | 168 | 173 | 180 | 187 | 195 | 202 | 208 | 216 | 221 | 227 | 235 | 241 | 248 | 253 | 258 | 263 | 269 | 276 | 281 | 289 | 296 | 302 | 309 | 314 | 322 | 327 | 333 | 339 | 347 | 355 | 363 | 370 | 375 | 380 | 386 | 393 | 399 | 406 | 411 | 416 | 424 | 430 | 438 | 446 | 453 | 458 | 466 | 471 | 479 | 487 | 494 | 502 | 508 | 513 | 518 | 526 | 531 | 536 | 541 | 548 | 553 | 559 | 567 | 574 | 581 | 586 | 594 | 600 | 608 | 615 | 623 | 631 | 636 | 642 | 648 | 655 | 660 | 666
135 | 1.6745 | 16 | 33 | 72 | 111 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 3 | 6 | 12 | 18 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 11 | 19 | 25 | 30 | 37 | 43 | 48 | 55 | 60 | 65 | 73 | 80 | 86 | 91 | 99 | 106 | 113 | 121 | 128 | 135 | 143 | 149 | 154 | 162 | 170 | 175 | 181 | 186 | 192 | 200 | 208 | 216 | 222 | 229 | 234 | 239 | 246 | 251 | 259 | 265 | 272 | 280 | 286 | 294 | 299 | 306 | 313 | 318 | 325 | 332 | 340 | 345 | 352 | 358 | 363 | 368 | 373 | 379 | 387 | 394 | 401 | 407 | 413 | 420 | 428 | 433 | 438 | 444 | 450 | 457 | 463 | 469 | 477 | 485 | 490 | 498 | 503 | 508 | 515 | 521 | 527 | 535 | 540 | 547 | 554 | 561 | 568 | 574 | 581 | 587 | 592 | 597 | 603 | 610 | 615 | 621 | 627 | 635 | 641 | 646 | 651 | 658 | 665
136 | 1.9648 | 18 | 34 | 76 | 118 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 4 | 6 | 12 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 10 | 15 | 20 | 28 | 34 | 41 | 47 | 54 | 62 | 68 | 76 | 81 | 87 | 93 | 101 | 106 | 113 | 121 | 129 | 136 | 141 | 146 | 153 | 158 | 164 | 171 | 179 | 187 | 194 | 201 | 209 | 215 | 221 | 228 | 234 | 240 | 248 | 256 | 262 | 267 | 272 | 280 | 287 | 292 | 300 | 305 | 311 | 316 | 323 | 330 | 335 | 341 | 346 | 353 | 360 | 365 | 373 | 379 | 384 | 390 | 397 | 404 | 410 | 415 | 421 | 429 | 435 | 441 | 449 | 457 | 463 | 469 | 475 | 483 | 489 | 496 | 502 | 510 | 516 | 522 | 527 | 535 | 543 | 550 | 556 | 561 | 566 | 572 | 577 | 582 | 587 | 592 | 599 | 606 | 611 | 617 | 624 | 631 | 636 | 644 | 652 | 657 | 664
137 | 1.8905 | 16 | 43 | 91 | 135 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 3 | 7 | 14 | 21 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 8 | 14 | 20 | 27 | 34 | 40 | 45 | 53 | 58 | 66 | 73 | 81 | 87 | 94 | 99 | 104 | 111 | 118 | 124 | 132 | 140 | 148 | 155 | 161 | 167 | 172 | 178 | 186 | 193 | 200 | 206 | 213 | 218 | 223 | 228 | 235 | 243 | 250 | 257 | 262 | 268 | 276 | 281 | 289 | 294 | 299 | 306 | 313 | 318 | 325 | 330 | 335 | 341 | 346 | 354 | 361 | 369 | 377 | 384 | 391 | 396 | 404 | 410 | 416 | 421 | 427 | 435 | 440 | 446 | 454 | 460 | 465 | 471 | 477 | 483 | 489 | 494 | 501 | 509 | 514 | 519 | 524 | 532 | 540 | 548 | 553 | 561 | 566 | 574 | 581 | 586 | 591 | 598 | 604 | 609 | 616 | 622 | 630 | 637 | 644 | 652 | 657 | 664 | 672
138 | 1.3496 | 9 | 24 | 53 | 91 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 2 | 4 | 9 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 7 | 12 | 20 | 27 | 35 | 41 | 47 | 52 | 58 | 63 | 68 | 74 | 79 | 87 | 94 | 99 | 106 | 111 | 116 | 123 | 130 | 135 | 140 | 146 | 152 | 160 | 165 | 171 | 177 | 182 | 187 | 195 | 202 | 208 | 216 | 223 | 229 | 236 | 241 | 247 | 253 | 260 | 267 | 273 | 281 | 289 | 297 | 304 | 311 | 316 | 323 | 330 | 335 | 342 | 350 | 356 | 361 | 369 | 376 | 384 | 392 | 397 | 403 | 411 | 416 | 423 | 430 | 435 | 442 | 447 | 454 | 460 | 468 | 474 | 480 | 486 | 493 | 499 | 505 | 512 | 520 | 526 | 533 | 538 | 546 | 554 | 559 | 565 | 573 | 580 | 586 | 591 | 596 | 602 | 609 | 615 | 623 | 631 | 636 | 641 | 647 | 654 | 662 | 670
139 | 1.2084 | 10 | 20 | 40 | 76 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 2 | 4 | 7 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 13 | 18 | 25 | 32 | 39 | 44 | 50 | 56 | 64 | 72 | 80 | 86 | 91 | 99 | 107 | 115 | 123 | 129 | 134 | 139 | 145 | 150 | 156 | 163 | 170 | 177 | 182 | 189 | 196 | 202 | 209 | 215 | 223 | 228 | 233 | 240 | 248 | 255 | 261 | 269 | 276 | 283 | 291 | 297 | 303 | 310 | 316 | 323 | 330 | 336 | 344 | 351 | 359 | 364 | 372 | 377 | 384 | 391 | 397 | 402 | 407 | 414 | 421 | 429 | 437 | 443 | 449 | 455 | 462 | 467 | 475 | 480 | 488 | 496 | 501 | 508 | 516 | 523 | 529 | 535 | 543 | 548 | 554 | 559 | 565 | 570 | 578 | 584 | 589 | 597 | 605 | 611 | 618 | 623 | 629 | 634 | 640 | 646 | 652 | 657 | 663 | 669 | 677
140 | 1.8767 | 17 | 33 | 71 | 118 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 3 | 5 | 10 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 16 | 21 | 29 | 35 | 42 | 50 | 56 | 64 | 71 | 78 | 83 | 89 | 97 | 105 | 112 | 119 | 124 | 129 | 136 | 144 | 152 | 158 | 164 | 169 | 176 | 183 | 190 | 198 | 204 | 212 | 217 | 224 | 231 | 237 | 244 | 251 | 256 | 261 | 267 | 272 | 280 | 287 | 293 | 299 | 307 | 312 | 319 | 325 | 330 | 338 | 345 | 352 | 357 | 363 | 371 | 378 | 383 | 389 | 394 | 400 | 407 | 414 | 421 | 426 | 432 | 440 | 445 | 452 | 459 | 467 | 473 | 481 | 489 | 496 | 502 | 508 | 515 | 522 | 530 | 537 | 544 | 550 | 555 | 562 | 568 | 574 | 579 | 585 | 592 | 597 | 602 | 610 | 616 | 623 | 629 | 636 | 644 | 650 | 658 | 666 | 672 | 680 | 686
141 | 1.6515 | 15 | 40 | 78 | 116 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 3 | 7 | 13 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 11 | 19 | 26 | 32 | 39 | 44 | 51 | 56 | 62 | 68 | 76 | 82 | 90 | 97 | 104 | 110 | 117 | 123 | 131 | 136 | 143 | 151 | 157 | 163 | 169 | 174 | 182 | 190 | 195 | 202 | 210 | 216 | 221 | 226 | 233 | 241 | 249 | 257 | 265 | 273 | 279 | 286 | 294 | 302 | 310 | 318 | 326 | 331 | 338 | 343 | 348 | 356 | 361 | 369 | 374 | 380 | 385 | 393 | 398 | 403 | 410 | 416 | 424 | 430 | 437 | 445 | 452 | 460 | 468 | 476 | 482 | 488 | 496 | 501 | 509 | 515 | 522 | 530 | 535 | 542 | 548 | 555 | 563 | 570 | 575 | 583 | 591 | 596 | 604 | 611 | 618 | 623 | 628 | 635 | 643 | 650 | 656 | 662 | 670 | 676 | 681 | 686 | 694
142 | 1.9675 | 16 | 42 | 88 | 148 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 3 | 7 | 14 | 21 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 5 | 12 | 18 | 25 | 30 | 37 | 44 | 52 | 59 | 64 | 71 | 79 | 87 | 95 | 103 | 110 | 118 | 126 | 133 | 140 | 148 | 155 | 162 | 168 | 173 | 181 | 186 | 191 | 199 | 206 | 214 | 221 | 227 | 234 | 242 | 247 | 254 | 262 | 269 | 275 | 280 | 288 | 296 | 303 | 308 | 316 | 324 | 330 | 335 | 342 | 348 | 355 | 362 | 367 | 375 | 382 | 387 | 394 | 402 | 410 | 415 | 422 | 430 | 435 | 443 | 450 | 456 | 463 | 471 | 476 | 481 | 488 | 493 | 500 | 505 | 511 | 518 | 523 | 531 | 539 | 547 | 553 | 559 | 564 | 571 | 578 | 583 | 591 | 596 | 604 | 610 | 617 | 622 | 630 | 636 | 643 | 648 | 654 | 659 | 665 | 670 | 676 | 682 | 689
143 | 1.1076 | 10 | 22 | 46 | 80 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 2 | 4 | 9 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 14 | 19 | 24 | 30 | 35 | 40 | 45 | 51 | 56 | 61 | 68 | 74 | 79 | 87 | 95 | 100 | 105 | 111 | 118 | 123 | 128 | 133 | 139 | 144 | 152 | 157 | 165 | 173 | 179 | 185 | 190 | 197 | 202 | 207 | 213 | 221 | 229 | 236 | 244 | 251 | 258 | 266 | 272 | 278 | 284 | 290 | 295 | 300 | 305 | 310 | 315 | 320 | 326 | 334 | 342 | 349 | 356 | 363 | 368 | 376 | 383 | 390 | 398 | 406 | 411 | 416 | 422 | 429 | 436 | 444 | 450 | 455 | 461 | 467 | 472 | 477 | 483 | 488 | 496 | 502 | 510 | 516 | 522 | 529 | 536 | 544 | 551 | 558 | 565 | 572 | 578 | 583 | 591 | 597 | 603 | 610 | 617 | 625 | 631 | 639 | 646 | 653 | 658
144 | 1.5109 | 10 | 32 | 61 | 95 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 5 | 9 | 14 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 11 | 19 | 27 | 32 | 39 | 47 | 53 | 61 | 69 | 74 | 82 | 89 | 95 | 100 | 106 | 114 | 119 | 126 | 132 | 139 | 147 | 155 | 162 | 167 | 175 | 180 | 187 | 194 | 200 | 208 | 213 | 221 | 226 | 231 | 237 | 245 | 250 | 257 | 263 | 269 | 275 | 283 | 288 | 293 | 299 | 304 | 309 | 317 | 325 | 332 | 339 | 344 | 350 | 357 | 364 | 372 | 379 | 384 | 390 | 396 | 402 | 409 | 417 | 423 | 431 | 438 | 443 | 448 | 454 | 460 | 465 | 472 | 480 | 486 | 493 | 499 | 504 | 512 | 520 | 526 | 531 | 537 | 545 | 551 | 556 | 561 | 569 | 575 | 582 | 587 | 592 | 600 | 608 | 613 | 618 | 624 | 630 | 635 | 640 | 648 | 653 | 659 | 665
145 | 1.2122 | 8 | 25 | 51 | 88 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 2 | 4 | 8 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 12 | 20 | 28 | 36 | 43 | 48 | 56 | 62 | 69 | 76 | 84 | 90 | 98 | 104 | 110 | 118 | 123 | 131 | 136 | 141 | 149 | 154 | 161 | 169 | 176 | 184 | 190 | 196 | 204 | 211 | 216 | 224 | 230 | 238 | 246 | 254 | 260 | 266 | 271 | 278 | 285 | 293 | 301 | 307 | 313 | 320 | 326 | 332 | 338 | 345 | 351 | 359 | 367 | 373 | 381 | 387 | 395 | 401 | 409 | 414 | 421 | 427 | 432 | 438 | 443 | 450 | 456 | 462 | 468 | 475 | 483 | 489 | 497 | 502 | 510 | 517 | 525 | 530 | 538 | 545 | 551 | 556 | 562 | 569 | 574 | 579 | 585 | 590 | 595 | 601 | 607 | 615 | 620 | 628 | 633 | 638 | 645 | 653 | 661 | 667 | 672 | 677 | 683
146 | 1.038 | 7 | 18 | 40 | 71 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 4 | 7 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 6 | 11 | 17 | 25 | 30 | 38 | 44 | 51 | 56 | 63 | 68 | 75 | 80 | 88 | 96 | 104 | 112 | 119 | 125 | 133 | 138 | 143 | 150 | 156 | 161 | 166 | 174 | 181 | 186 | 192 | 199 | 207 | 214 | 222 | 228 | 236 | 244 | 249 | 255 | 262 | 268 | 274 | 281 | 289 | 297 | 304 | 311 | 319 | 324 | 331 | 336 | 344 | 349 | 355 | 363 | 370 | 377 | 385 | 393 | 400 | 407 | 414 | 420 | 425 | 430 | 435 | 442 | 450 | 456 | 463 | 470 | 476 | 484 | 492 | 499 | 506 | 514 | 520 | 527 | 535 | 542 | 548 | 556 | 563 | 570 | 578 | 586 | 591 | 599 | 607 | 612 | 620 | 628 | 635 | 640 | 646 | 651 | 659 | 664 | 671 | 677 | 684 | 691 | 697
147 | 1.7442 | 13 | 31 | 65 | 113 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 2 | 5 | 10 | 17 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 15 | 23 | 29 | 34 | 41 | 47 | 55 | 63 | 71 | 78 | 83 | 89 | 95 | 100 | 108 | 113 | 120 | 127 | 132 | 139 | 146 | 151 | 157 | 164 | 169 | 174 | 179 | 187 | 193 | 200 | 208 | 213 | 218 | 225 | 233 | 241 | 247 | 254 | 259 | 267 | 273 | 281 | 288 | 294 | 301 | 307 | 312 | 317 | 323 | 328 | 334 | 340 | 347 | 353 | 360 | 367 | 374 | 381 | 387 | 394 | 399 | 406 | 412 | 417 | 424 | 430 | 437 | 442 | 447 | 454 | 462 | 470 | 475 | 482 | 490 | 495 | 501 | 509 | 517 | 524 | 532 | 537 | 545 | 551 | 558 | 565 | 573 | 580 | 586 | 592 | 597 | 605 | 613 | 619 | 626 | 632 | 640 | 645 | 650 | 658 | 666 | 673 | 681
148 | 1.2175 | 13 | 23 | 50 | 83 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 3 | 4 | 8 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 19 | 25 | 30 | 36 | 42 | 50 | 58 | 64 | 72 | 77 | 82 | 90 | 95 | 100 | 108 | 113 | 121 | 127 | 135 | 143 | 148 | 156 | 163 | 168 | 175 | 183 | 188 | 196 | 203 | 208 | 216 | 222 | 227 | 232 | 239 | 247 | 253 | 259 | 265 | 272 | 279 | 287 | 293 | 301 | 306 | 312 | 318 | 323 | 331 | 337 | 345 | 350 | 358 | 366 | 372 | 379 | 387 | 395 | 402 | 408 | 416 | 423 | 429 | 437 | 445 | 452 | 458 | 464 | 469 | 474 | 480 | 485 | 491 | 498 | 505 | 512 | 520 | 528 | 534 | 540 | 547 | 555 | 563 | 569 | 575 | 583 | 590 | 595 | 602 | 609 | 616 | 621 | 627 | 633 | 641 | 647 | 653 | 658 | 663 | 669 | 676 | 682
149 | 1.3509 | 11 | 29 | 54 | 88 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 4 | 7 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 16 | 23 | 31 | 39 | 47 | 54 | 60 | 65 | 72 | 77 | 84 | 91 | 98 | 103 | 109 | 114 | 121 | 129 | 135 | 143 | 150 | 155 | 162 | 168 | 176 | 183 | 191 | 196 | 202 | 208 | 216 | 222 | 227 | 232 | 237 | 243 | 248 | 256 | 262 | 268 | 274 | 279 | 284 | 291 | 296 | 303 | 310 | 318 | 323 | 330 | 338 | 343 | 350 | 357 | 364 | 370 | 377 | 382 | 389 | 397 | 402 | 409 | 414 | 422 | 429 | 436 | 444 | 450 | 458 | 466 | 472 | 480 | 488 | 493 | 499 | 504 | 512 | 518 | 524 | 532 | 539 | 544 | 550 | 556 | 561 | 566 | 571 | 577 | 584 | 592 | 600 | 607 | 613 | 619 | 627 | 634 | 640 | 646 | 651 | 658 | 663 | 669 | 674
150 | 1.3323 | 14 | 30 | 64 | 92 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 3 | 5 | 11 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 11 | 17 | 25 | 33 | 39 | 44 | 49 | 57 | 62 | 70 | 77 | 84 | 90 | 96 | 103 | 108 | 114 | 120 | 126 | 133 | 140 | 145 | 150 | 158 | 164 | 172 | 179 | 186 | 194 | 202 | 208 | 213 | 220 | 226 | 233 | 240 | 247 | 252 | 259 | 267 | 272 | 278 | 285 | 293 | 298 | 303 | 310 | 315 | 321 | 326 | 332 | 340 | 347 | 354 | 359 | 364 | 372 | 377 | 385 | 390 | 397 | 403 | 408 | 413 | 421 | 427 | 435 | 441 | 448 | 455 | 460 | 467 | 473 | 479 | 487 | 493 | 500 | 508 | 514 | 520 | 527 | 535 | 540 | 545 | 550 | 555 | 561 | 567 | 573 | 580 | 586 | 592 | 598 | 605 | 610 | 615 | 620 | 627 | 632 | 637 | 643 | 651 | 656
151 | 1.0432 | 6 | 16 | 33 | 56 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 1 | 3 | 5 | 9 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 6 | 13 | 20 | 25 | 33 | 40 | 46 | 52 | 59 | 65 | 73 | 79 | 85 | 92 | 99 | 105 | 111 | 117 | 122 | 129 | 135 | 143 | 148 | 155 | 161 | 168 | 173 | 178 | 185 | 191 | 198 | 203 | 209 | 214 | 222 | 229 | 235 | 242 | 249 | 256 | 262 | 270 | 276 | 282 | 290 | 295 | 300 | 307 | 312 | 319 | 325 | 331 | 336 | 343 | 350 | 355 | 363 | 369 | 376 | 383 | 390 | 397 | 402 | 409 | 414 | 421 | 427 | 435 | 443 | 451 | 459 | 466 | 474 | 481 | 489 | 496 | 501 | 506 | 513 | 519 | 525 | 532 | 537 | 544 | 550 | 556 | 562 | 569 | 574 | 582 | 588 | 596 | 601 | 606 | 612 | 618 | 625 | 633 | 641 | 648 | 655 | 660 | 667 | 674
152 | 1.7832 | 17 | 34 | 77 | 120 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 3 | 6 | 12 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 12 | 17 | 24 | 32 | 37 | 44 | 51 | 58 | 65 | 71 | 77 | 85 | 92 | 100 | 106 | 113 | 121 | 128 | 133 | 141 | 148 | 156 | 162 | 167 | 175 | 181 | 189 | 196 | 204 | 212 | 220 | 225 | 231 | 237 | 242 | 247 | 255 | 262 | 267 | 274 | 281 | 286 | 293 | 299 | 306 | 313 | 319 | 325 | 330 | 338 | 345 | 353 | 360 | 367 | 372 | 380 | 387 | 395 | 403 | 408 | 415 | 423 | 431 | 437 | 443 | 448 | 456 | 464 | 470 | 476 | 483 | 489 | 497 | 504 | 510 | 517 | 524 | 530 | 537 | 542 | 549 | 557 | 565 | 573 | 580 | 585 | 591 | 596 | 601 | 608 | 616 | 622 | 627 | 632 | 639 | 647 | 655 | 660 | 667 | 673 | 681 | 689 | 697
153 | 1.2553 | 9 | 20 | 39 | 73 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 2 | 3 | 6 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 14 | 22 | 28 | 35 | 40 | 45 | 51 | 58 | 64 | 71 | 76 | 82 | 88 | 94 | 101 | 109 | 116 | 123 | 128 | 136 | 144 | 151 | 157 | 164 | 169 | 175 | 183 | 188 | 196 | 204 | 210 | 215 | 222 | 227 | 233 | 241 | 246 | 253 | 261 | 269 | 275 | 280 | 286 | 291 | 296 | 302 | 310 | 317 | 323 | 329 | 334 | 340 | 345 | 353 | 361 | 368 | 374 | 380 | 385 | 392 | 398 | 406 | 413 | 419 | 427 | 434 | 442 | 450 | 455 | 463 | 471 | 479 | 484 | 490 | 496 | 501 | 508 | 513 | 518 | 523 | 528 | 536 | 544 | 549 | 557 | 565 | 572 | 578 | 583 | 588 | 594 | 601 | 606 | 613 | 619 | 625 | 631 | 636 | 643 | 650 | 655 | 663 | 671
154 | 1.7856 | 17 | 35 | 80 | 116 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 3 | 6 | 13 | 18 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 15 | 20 | 27 | 34 | 39 | 45 | 53 | 58 | 66 | 71 | 76 | 84 | 90 | 98 | 104 | 112 | 118 | 124 | 131 | 139 | 147 | 154 | 161 | 169 | 174 | 181 | 187 | 192 | 199 | 204 | 209 | 215 | 220 | 228 | 233 | 241 | 246 | 254 | 259 | 266 | 274 | 280 | 285 | 293 | 300 | 308 | 313 | 319 | 325 | 332 | 339 | 345 | 353 | 359 | 365 | 373 | 378 | 385 | 393 | 400 | 405 | 413 | 419 | 426 | 431 | 439 | 446 | 454 | 460 | 467 | 472 | 478 | 486 | 491 | 498 | 504 | 512 | 517 | 522 | 527 | 534 | 540 | 546 | 553 | 560 | 568 | 573 | 578 | 584 | 590 | 595 | 602 | 610 | 616 | 622 | 628 | 636 | 642 | 649 | 657 | 665 | 671 | 678
155 | 1.6641 | 10 | 32 | 59 | 94 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 2 | 5 | 10 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 12 | 20 | 25 | 32 | 39 | 46 | 51 | 58 | 65 | 72 | 78 | 83 | 91 | 96 | 104 | 111 | 118 | 124 | 130 | 136 | 141 | 149 | 154 | 162 | 170 | 177 | 185 | 193 | 199 | 205 | 213 | 220 | 225 | 233 | 238 | 244 | 249 | 254 | 261 | 267 | 275 | 283 | 291 | 297 | 305 | 311 | 319 | 327 | 334 | 342 | 350 | 357 | 365 | 371 | 376 | 384 | 389 | 396 | 403 | 411 | 417 | 422 | 427 | 433 | 438 | 446 | 453 | 458 | 464 | 470 | 477 | 483 | 488 | 496 | 501 | 509 | 515 | 522 | 530 | 538 | 543 | 549 | 556 | 563 | 570 | 578 | 584 | 591 | 597 | 602 | 609 | 614 | 620 | 628 | 635 | 643 | 648 | 656 | 661 | 669 | 676 | 682 | 690
156 | 1.3842 | 13 | 26 | 47 | 89 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 2 | 4 | 7 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 14 | 19 | 26 | 33 | 40 | 47 | 54 | 61 | 67 | 73 | 78 | 84 | 91 | 98 | 104 | 110 | 118 | 126 | 134 | 141 | 149 | 155 | 160 | 167 | 174 | 180 | 185 | 190 | 197 | 204 | 211 | 218 | 225 | 233 | 238 | 246 | 251 | 256 | 261 | 269 | 276 | 283 | 289 | 294 | 300 | 307 | 313 | 319 | 327 | 332 | 337 | 344 | 351 | 358 | 366 | 371 | 378 | 385 | 391 | 396 | 401 | 409 | 415 | 423 | 431 | 436 | 443 | 450 | 456 | 462 | 468 | 476 | 484 | 489 | 494 | 501 | 506 | 512 | 520 | 526 | 531 | 539 | 546 | 551 | 557 | 562 | 568 | 573 | 581 | 586 | 592 | 599 | 606 | 614 | 620 | 627 | 634 | 640 | 645 | 652 | 660 | 667 | 674
157 | 1.8173 | 15 | 41 | 78 | 126 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 2 | 6 | 13 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 15 | 21 | 27 | 34 | 42 | 50 | 56 | 61 | 66 | 71 | 76 | 82 | 89 | 97 | 104 | 110 | 115 | 122 | 130 | 135 | 142 | 148 | 153 | 161 | 168 | 175 | 180 | 188 | 193 | 201 | 208 | 213 | 219 | 225 | 230 | 237 | 245 | 253 | 258 | 263 | 268 | 276 | 284 | 290 | 298 | 306 | 311 | 317 | 325 | 331 | 339 | 345 | 351 | 357 | 362 | 370 | 377 | 384 | 389 | 397 | 402 | 410 | 418 | 423 | 430 | 435 | 440 | 445 | 450 | 456 | 462 | 468 | 474 | 482 | 487 | 492 | 497 | 503 | 511 | 516 | 523 | 530 | 538 | 544 | 550 | 558 | 566 | 574 | 581 | 587 | 594 | 600 | 608 | 615 | 620 | 626 | 631 | 638 | 646 | 653 | 660 | 665 | 670
158 | 1.4856 | 14 | 32 | 67 | 109 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 2 | 5 | 10 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 16 | 22 | 28 | 36 | 44 | 49 | 56 | 61 | 67 | 73 | 79 | 86 | 91 | 97 | 104 | 109 | 117 | 124 | 130 | 137 | 143 | 150 | 158 | 166 | 173 | 178 | 186 | 194 | 202 | 209 | 215 | 222 | 230 | 238 | 244 | 250 | 258 | 264 | 272 | 279 | 286 | 293 | 298 | 304 | 311 | 319 | 326 | 333 | 338 | 345 | 350 | 355 | 361 | 366 | 373 | 379 | 384 | 391 | 398 | 403 | 409 | 416 | 424 | 429 | 435 | 441 | 446 | 454 | 462 | 470 | 475 | 482 | 489 | 497 | 505 | 513 | 521 | 527 | 535 | 541 | 549 | 555 | 563 | 570 | 575 | 580 | 588 | 595 | 601 | 607 | 614 | 620 | 625 | 631 | 638 | 646 | 654 | 662 | 667 | 673 | 679 | 687 | 692
159 | 1.9255 | 16 | 36 | 67 | 108 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 3 | 7 | 11 | 17 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 5 | 12 | 17 | 22 | 27 | 35 | 43 | 50 | 55 | 63 | 71 | 79 | 87 | 94 | 101 | 106 | 114 | 122 | 128 | 133 | 141 | 147 | 153 | 159 | 167 | 174 | 180 | 186 | 191 | 199 | 206 | 213 | 219 | 225 | 232 | 238 | 246 | 254 | 260 | 266 | 273 | 281 | 289 | 296 | 301 | 308 | 316 | 322 | 327 | 335 | 342 | 349 | 354 | 361 | 367 | 373 | 380 | 386 | 391 | 396 | 403 | 408 | 414 | 420 | 428 | 435 | 441 | 448 | 456 | 463 | 471 | 476 | 481 | 487 | 494 | 500 | 507 | 515 | 520 | 528 | 534 | 539 | 547 | 554 | 561 | 567 | 574 | 580 | 586 | 594 | 599 | 607 | 615 | 621 | 626 | 632 | 638 | 644 | 650 | 655 | 660 | 668 | 676 | 681
160 | 1.4696 | 12 | 35 | 60 | 103 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 3 | 6 | 10 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 5 | 11 | 19 | 25 | 33 | 41 | 46 | 52 | 58 | 66 | 74 | 81 | 87 | 92 | 99 | 104 | 112 | 118 | 126 | 133 | 140 | 148 | 153 | 160 | 165 | 172 | 177 | 184 | 189 | 194 | 202 | 209 | 215 | 221 | 229 | 236 | 243 | 249 | 255 | 261 | 266 | 271 | 276 | 281 | 287 | 294 | 302 | 310 | 315 | 323 | 331 | 337 | 342 | 349 | 357 | 364 | 372 | 378 | 384 | 390 | 398 | 404 | 409 | 414 | 420 | 428 | 435 | 440 | 448 | 455 | 461 | 466 | 472 | 478 | 486 | 492 | 500 | 506 | 511 | 519 | 524 | 531 | 538 | 544 | 552 | 560 | 565 | 572 | 579 | 585 | 591 | 599 | 604 | 609 | 616 | 623 | 628 | 633 | 641 | 646 | 653 | 660 | 667 | 674
161 | 1.1686 | 10 | 26 | 53 | 86 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 2 | 5 | 8 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 13 | 18 | 24 | 32 | 40 | 48 | 54 | 62 | 67 | 74 | 82 | 90 | 95 | 100 | 108 | 114 | 119 | 124 | 129 | 134 | 142 | 148 | 155 | 162 | 170 | 177 | 184 | 189 | 194 | 202 | 208 | 215 | 220 | 227 | 232 | 239 | 247 | 253 | 258 | 263 | 270 | 278 | 286 | 291 | 297 | 304 | 310 | 315 | 320 | 326 | 333 | 341 | 346 | 352 | 358 | 364 | 370 | 377 | 385 | 393 | 400 | 405 | 412 | 420 | 427 | 434 | 442 | 450 | 456 | 461 | 466 | 473 | 480 | 488 | 494 | 499 | 505 | 513 | 519 | 527 | 532 | 539 | 545 | 553 | 559 | 566 | 571 | 579 | 584 | 591 | 597 | 605 | 613 | 618 | 626 | 631 | 636 | 641 | 647 | 654 | 662 | 668 | 673
162 | 1.7088 | 14 | 37 | 68 | 115 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 3 | 6 | 11 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 12 | 19 | 26 | 31 | 39 | 46 | 51 | 58 | 64 | 72 | 78 | 85 | 92 | 97 | 103 | 110 | 118 | 125 | 131 | 136 | 142 | 148 | 156 | 161 | 169 | 174 | 181 | 188 | 195 | 200 | 208 | 215 | 221 | 226 | 234 | 242 | 249 | 257 | 264 | 270 | 276 | 283 | 291 | 298 | 303 | 309 | 315 | 321 | 326 | 333 | 338 | 343 | 349 | 354 | 361 | 368 | 373 | 379 | 384 | 390 | 395 | 402 | 409 | 416 | 421 | 429 | 434 | 441 | 448 | 456 | 462 | 469 | 474 | 479 | 487 | 493 | 501 | 508 | 515 | 520 | 526 | 533 | 540 | 548 | 555 | 561 | 569 | 576 | 581 | 588 | 595 | 601 | 606 | 614 | 619 | 624 | 630 | 638 | 646 | 652 | 657 | 665 | 673
163 | 1.5659 | 16 | 37 | 69 | 110 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 3 | 6 | 11 | 17 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 6 | 11 | 19 | 26 | 33 | 38 | 43 | 50 | 58 | 63 | 71 | 78 | 84 | 90 | 98 | 105 | 110 | 118 | 126 | 131 | 139 | 147 | 153 | 161 | 169 | 175 | 181 | 189 | 196 | 201 | 208 | 214 | 219 | 224 | 231 | 236 | 243 | 250 | 257 | 264 | 272 | 277 | 282 | 287 | 293 | 298 | 304 | 310 | 315 | 323 | 331 | 337 | 345 | 350 | 357 | 363 | 371 | 379 | 387 | 395 | 403 | 409 | 416 | 424 | 431 | 438 | 446 | 454 | 459 | 467 | 475 | 483 | 489 | 494 | 501 | 507 | 512 | 518 | 525 | 530 | 536 | 543 | 551 | 557 | 563 | 570 | 575 | 581 | 586 | 592 | 599 | 606 | 614 | 620 | 628 | 634 | 642 | 649 | 657 | 662 | 668 | 676 | 684 | 689
164 | 1.4345 | 15 | 36 | 68 | 99 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 6 | 11 | 15 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 16 | 23 | 29 | 35 | 41 | 48 | 53 | 60 | 66 | 74 | 79 | 85 | 92 | 100 | 105 | 113 | 119 | 126 | 131 | 136 | 141 | 146 | 154 | 162 | 170 | 175 | 182 | 190 | 198 | 205 | 213 | 219 | 227 | 235 | 242 | 248 | 256 | 262 | 269 | 275 | 283 | 289 | 295 | 300 | 307 | 312 | 318 | 324 | 332 | 340 | 348 | 354 | 362 | 370 | 377 | 385 | 391 | 398 | 406 | 413 | 420 | 427 | 435 | 442 | 449 | 457 | 464 | 470 | 478 | 486 | 492 | 499 | 505 | 513 | 519 | 524 | 529 | 536 | 541 | 547 | 553 | 559 | 565 | 572 | 580 | 586 | 591 | 598 | 606 | 613 | 619 | 627 | 635 | 641 | 648 | 656 | 664 | 671 | 676 | 682 | 689 | 696 | 702
165 | 1.5155 | 14 | 27 | 62 | 102 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 3 | 5 | 11 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 11 | 18 | 23 | 29 | 34 | 39 | 46 | 54 | 60 | 67 | 73 | 80 | 85 | 91 | 99 | 106 | 114 | 120 | 126 | 131 | 138 | 146 | 151 | 158 | 165 | 171 | 178 | 184 | 192 | 198 | 206 | 213 | 220 | 227 | 233 | 241 | 248 | 255 | 262 | 269 | 275 | 283 | 291 | 298 | 305 | 310 | 318 | 326 | 331 | 338 | 343 | 349 | 356 | 364 | 369 | 375 | 382 | 390 | 396 | 402 | 410 | 417 | 425 | 432 | 437 | 443 | 449 | 454 | 460 | 465 | 472 | 478 | 485 | 491 | 499 | 505 | 511 | 517 | 522 | 527 | 535 | 540 | 548 | 553 | 561 | 567 | 572 | 579 | 585 | 593 | 600 | 606 | 611 | 619 | 625 | 632 | 639 | 644 | 649 | 655 | 660 | 666 | 672
166 | 1.0978 | 9 | 25 | 45 | 69 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 4 | 7 | 10 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 16 | 24 | 30 | 36 | 44 | 49 | 57 | 63 | 69 | 76 | 84 | 92 | 98 | 103 | 108 | 115 | 123 | 131 | 139 | 144 | 150 | 155 | 162 | 170 | 175 | 183 | 188 | 193 | 201 | 209 | 215 | 221 | 228 | 236 | 244 | 251 | 258 | 264 | 272 | 278 | 285 | 293 | 301 | 309 | 314 | 320 | 326 | 334 | 341 | 347 | 354 | 360 | 366 | 372 | 378 | 385 | 391 | 399 | 404 | 412 | 419 | 427 | 435 | 442 | 450 | 458 | 465 | 471 | 476 | 483 | 489 | 496 | 503 | 511 | 516 | 521 | 529 | 535 | 542 | 549 | 557 | 563 | 568 | 575 | 583 | 588 | 596 | 601 | 606 | 613 | 618 | 623 | 629 | 637 | 642 | 650 | 658 | 665 | 672 | 679 | 686 | 693 | 700
167 | 1.921 | 16 | 45 | 92 | 148 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 3 | 7 | 14 | 24 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 7 | 14 | 20 | 25 | 33 | 38 | 46 | 54 | 60 | 65 | 73 | 81 | 86 | 92 | 97 | 105 | 112 | 118 | 123 | 128 | 134 | 139 | 145 | 152 | 160 | 167 | 175 | 183 | 189 | 196 | 202 | 207 | 214 | 219 | 227 | 235 | 242 | 250 | 256 | 262 | 268 | 275 | 283 | 290 | 298 | 306 | 311 | 317 | 325 | 331 | 336 | 343 | 350 | 355 | 361 | 367 | 373 | 379 | 387 | 394 | 402 | 409 | 417 | 424 | 432 | 437 | 443 | 448 | 454 | 459 | 467 | 473 | 479 | 484 | 489 | 496 | 502 | 510 | 516 | 521 | 526 | 534 | 542 | 549 | 554 | 559 | 566 | 571 | 578 | 584 | 591 | 598 | 606 | 614 | 619 | 625 | 633 | 640 | 647 | 654 | 662 | 670 | 675 | 683
168 | 1.028 | 10 | 21 | 41 | 67 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 4 | 7 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 11 | 18 | 23 | 29 | 35 | 43 | 49 | 55 | 61 | 66 | 71 | 77 | 83 | 91 | 98 | 103 | 108 | 114 | 121 | 129 | 134 | 139 | 144 | 151 | 158 | 164 | 172 | 180 | 186 | 191 | 196 | 203 | 211 | 216 | 221 | 229 | 235 | 243 | 251 | 258 | 265 | 273 | 278 | 284 | 292 | 299 | 305 | 311 | 319 | 325 | 333 | 341 | 346 | 354 | 361 | 368 | 376 | 384 | 391 | 399 | 407 | 415 | 423 | 430 | 438 | 443 | 448 | 456 | 462 | 468 | 476 | 484 | 492 | 500 | 506 | 511 | 517 | 523 | 530 | 538 | 544 | 550 | 558 | 566 | 573 | 578 | 584 | 589 | 594 | 600 | 606 | 612 | 619 | 625 | 630 | 635 | 640 | 648 | 655 | 660 | 666 | 672 | 680
169 | 1.3656 | 7 | 27 | 49 | 82 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 2 | 4 | 8 | 13 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 14 | 22 | 28 | 34 | 41 | 46 | 52 | 59 | 64 | 70 | 78 | 85 | 90 | 95 | 102 | 110 | 115 | 120 | 125 | 133 | 141 | 146 | 152 | 160 | 167 | 174 | 180 | 186 | 192 | 199 | 207 | 215 | 223 | 228 | 233 | 238 | 244 | 249 | 254 | 262 | 268 | 273 | 280 | 285 | 292 | 300 | 306 | 312 | 318 | 325 | 332 | 338 | 346 | 354 | 361 | 366 | 372 | 380 | 388 | 396 | 402 | 407 | 413 | 419 | 425 | 432 | 440 | 446 | 453 | 459 | 464 | 471 | 479 | 486 | 491 | 496 | 501 | 506 | 513 | 520 | 527 | 533 | 538 | 546 | 551 | 559 | 566 | 572 | 577 | 584 | 589 | 597 | 605 | 612 | 620 | 625 | 630 | 635 | 642 | 648 | 656 | 664 | 670
170 | 1.5905 | 16 | 40 | 64 | 98 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 3 | 6 | 10 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 14 | 21 | 28 | 34 | 42 | 48 | 56 | 61 | 69 | 76 | 84 | 89 | 94 | 100 | 108 | 116 | 124 | 131 | 138 | 145 | 151 | 156 | 161 | 169 | 174 | 182 | 188 | 193 | 200 | 206 | 214 | 219 | 224 | 230 | 238 | 246 | 252 | 259 | 265 | 272 | 277 | 282 | 288 | 294 | 301 | 306 | 314 | 321 | 329 | 336 | 344 | 351 | 356 | 362 | 369 | 376 | 382 | 388 | 394 | 402 | 409 | 414 | 421 | 428 | 435 | 440 | 445 | 450 | 456 | 462 | 468 | 474 | 479 | 485 | 491 | 498 | 503 | 509 | 516 | 523 | 530 | 538 | 546 | 552 | 557 | 564 | 570 | 578 | 584 | 590 | 597 | 602 | 609 | 616 | 624 | 632 | 637 | 643 | 650 | 655 | 660 | 667 | 672
171 | 1.1069 | 10 | 24 | 42 | 70 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 4 | 6 | 11 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 16 | 22 | 29 | 37 | 43 | 51 | 58 | 63 | 68 | 75 | 80 | 85 | 90 | 95 | 100 | 106 | 113 | 118 | 125 | 132 | 139 | 146 | 152 | 157 | 165 | 172 | 177 | 182 | 189 | 196 | 204 | 211 | 217 | 225 | 233 | 240 | 245 | 250 | 256 | 261 | 269 | 276 | 284 | 292 | 298 | 303 | 308 | 315 | 323 | 330 | 336 | 344 | 349 | 356 | 361 | 369 | 376 | 382 | 387 | 392 | 398 | 406 | 412 | 417 | 424 | 432 | 438 | 444 | 452 | 459 | 466 | 473 | 478 | 485 | 492 | 497 | 504 | 509 | 515 | 523 | 530 | 535 | 542 | 549 | 557 | 562 | 567 | 573 | 579 | 587 | 593 | 601 | 609 | 615 | 621 | 629 | 635 | 642 | 648 | 653 | 660 | 665 | 672
172 | 1.3422 | 14 | 31 | 57 | 84 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 2 | 5 | 10 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 14 | 22 | 28 | 34 | 40 | 45 | 50 | 55 | 61 | 68 | 73 | 78 | 84 | 90 | 98 | 106 | 112 | 119 | 127 | 133 | 139 | 147 | 152 | 160 | 166 | 171 | 178 | 183 | 189 | 197 | 205 | 213 | 220 | 227 | 235 | 241 | 246 | 253 | 261 | 266 | 274 | 282 | 288 | 293 | 298 | 305 | 310 | 315 | 321 | 328 | 336 | 344 | 352 | 360 | 367 | 373 | 378 | 384 | 392 | 399 | 406 | 412 | 418 | 423 | 431 | 436 | 441 | 448 | 455 | 461 | 469 | 477 | 482 | 488 | 493 | 500 | 505 | 512 | 517 | 522 | 527 | 534 | 541 | 547 | 555 | 562 | 567 | 573 | 580 | 587 | 594 | 602 | 609 | 614 | 622 | 628 | 633 | 640 | 648 | 654 | 660 | 667 | 672
173 | 1.4747 | 15 | 33 | 64 | 101 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 3 | 5 | 10 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 13 | 21 | 27 | 35 | 40 | 45 | 51 | 57 | 65 | 72 | 77 | 84 | 90 | 95 | 101 | 107 | 115 | 122 | 130 | 136 | 144 | 151 | 157 | 164 | 169 | 176 | 184 | 189 | 195 | 202 | 209 | 217 | 224 | 230 | 236 | 241 | 247 | 254 | 262 | 269 | 277 | 284 | 291 | 296 | 302 | 308 | 314 | 320 | 326 | 331 | 336 | 343 | 349 | 355 | 361 | 368 | 374 | 381 | 388 | 393 | 400 | 405 | 411 | 418 | 423 | 429 | 434 | 442 | 448 | 455 | 463 | 470 | 478 | 484 | 491 | 496 | 503 | 509 | 515 | 520 | 526 | 532 | 540 | 545 | 552 | 560 | 565 | 572 | 578 | 583 | 591 | 597 | 602 | 610 | 618 | 624 | 631 | 638 | 646 | 652 | 657 | 664 | 671
174 | 1.2172 | 9 | 23 | 53 | 85 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 2 | 4 | 8 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 15 | 22 | 28 | 36 | 43 | 51 | 59 | 65 | 72 | 80 | 86 | 91 | 99 | 105 | 113 | 120 | 125 | 131 | 137 | 144 | 150 | 157 | 162 | 169 | 177 | 185 | 190 | 198 | 204 | 209 | 215 | 222 | 228 | 236 | 244 | 251 | 256 | 264 | 271 | 276 | 283 | 290 | 297 | 305 | 311 | 318 | 325 | 332 | 337 | 344 | 350 | 356 | 363 | 371 | 379 | 386 | 392 | 400 | 405 | 411 | 417 | 424 | 430 | 436 | 442 | 448 | 456 | 463 | 470 | 478 | 484 | 489 | 494 | 500 | 507 | 514 | 521 | 527 | 533 | 541 | 547 | 552 | 560 | 567 | 575 | 582 | 588 | 596 | 601 | 607 | 615 | 621 | 628 | 634 | 641 | 649 | 656 | 662 | 667 | 672 | 678 | 683 | 691
175 | 1.8747 | 15 | 30 | 68 | 113 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 3 | 5 | 10 | 17 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 13 | 21 | 26 | 33 | 39 | 47 | 55 | 62 | 69 | 76 | 82 | 87 | 95 | 101 | 109 | 114 | 120 | 127 | 135 | 142 | 147 | 153 | 159 | 164 | 170 | 176 | 181 | 188 | 193 | 199 | 207 | 214 | 221 | 226 | 232 | 240 | 245 | 250 | 258 | 266 | 272 | 280 | 287 | 295 | 301 | 308 | 313 | 320 | 325 | 332 | 340 | 345 | 350 | 358 | 364 | 371 | 377 | 382 | 389 | 396 | 404 | 412 | 419 | 427 | 432 | 438 | 443 | 451 | 457 | 463 | 470 | 475 | 482 | 489 | 497 | 503 | 509 | 516 | 521 | 526 | 534 | 539 | 545 | 553 | 559 | 565 | 571 | 577 | 584 | 592 | 597 | 602 | 607 | 612 | 620 | 626 | 634 | 642 | 648 | 656 | 662 | 670 | 678
176 | 1.1182 | 9 | 21 | 38 | 71 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 2 | 3 | 6 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 15 | 23 | 28 | 36 | 43 | 50 | 56 | 61 | 68 | 76 | 81 | 87 | 95 | 103 | 111 | 118 | 124 | 129 | 136 | 144 | 149 | 157 | 163 | 169 | 175 | 180 | 185 | 191 | 199 | 205 | 213 | 219 | 224 | 229 | 236 | 242 | 247 | 252 | 259 | 265 | 270 | 277 | 283 | 288 | 295 | 303 | 310 | 315 | 321 | 328 | 336 | 341 | 349 | 356 | 361 | 368 | 376 | 384 | 392 | 400 | 406 | 412 | 420 | 428 | 434 | 441 | 446 | 452 | 458 | 466 | 472 | 477 | 482 | 488 | 494 | 499 | 505 | 512 | 518 | 524 | 530 | 538 | 545 | 551 | 557 | 562 | 569 | 576 | 582 | 590 | 595 | 600 | 608 | 615 | 623 | 628 | 633 | 639 | 645 | 651 | 657 | 664 | 671
177 | 1.4417 | 8 | 29 | 55 | 86 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 2 | 5 | 9 | 13 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 5 | 11 | 19 | 27 | 32 | 40 | 47 | 53 | 58 | 66 | 72 | 79 | 86 | 94 | 100 | 107 | 115 | 121 | 128 | 134 | 139 | 147 | 152 | 159 | 165 | 172 | 179 | 185 | 193 | 200 | 206 | 214 | 220 | 225 | 233 | 239 | 247 | 252 | 257 | 262 | 268 | 273 | 278 | 286 | 294 | 300 | 307 | 315 | 320 | 326 | 334 | 341 | 347 | 354 | 360 | 367 | 373 | 380 | 385 | 393 | 400 | 407 | 415 | 423 | 429 | 434 | 441 | 448 | 456 | 463 | 469 | 474 | 479 | 484 | 490 | 498 | 503 | 511 | 517 | 525 | 532 | 540 | 545 | 553 | 561 | 567 | 575 | 582 | 589 | 595 | 603 | 609 | 614 | 622 | 629 | 637 | 643 | 649 | 657 | 663 | 669 | 674 | 682 | 687
178 | 1.6483 | 12 | 26 | 53 | 103 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 2 | 5 | 9 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 13 | 19 | 25 | 30 | 37 | 43 | 50 | 58 | 63 | 71 | 76 | 81 | 89 | 97 | 102 | 107 | 114 | 121 | 127 | 132 | 140 | 145 | 152 | 158 | 166 | 171 | 179 | 184 | 191 | 199 | 204 | 212 | 218 | 225 | 232 | 239 | 245 | 253 | 258 | 264 | 272 | 280 | 288 | 294 | 301 | 306 | 313 | 321 | 329 | 334 | 339 | 345 | 351 | 359 | 366 | 371 | 376 | 382 | 387 | 393 | 401 | 407 | 412 | 420 | 427 | 433 | 439 | 445 | 451 | 459 | 464 | 470 | 476 | 484 | 490 | 498 | 503 | 508 | 514 | 519 | 524 | 530 | 537 | 542 | 548 | 553 | 561 | 566 | 574 | 579 | 585 | 592 | 597 | 602 | 607 | 613 | 618 | 624 | 631 | 637 | 644 | 649 | 655
179 | 1.7641 | 16 | 36 | 75 | 125 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 3 | 6 | 12 | 20 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 7 | 14 | 20 | 25 | 31 | 38 | 45 | 51 | 58 | 65 | 72 | 77 | 83 | 91 | 96 | 102 | 109 | 115 | 121 | 127 | 135 | 143 | 149 | 156 | 161 | 167 | 174 | 182 | 189 | 195 | 203 | 211 | 218 | 226 | 233 | 239 | 245 | 252 | 260 | 268 | 273 | 278 | 283 | 290 | 295 | 300 | 308 | 314 | 321 | 329 | 335 | 340 | 347 | 352 | 358 | 366 | 373 | 381 | 387 | 394 | 401 | 408 | 416 | 421 | 427 | 433 | 441 | 449 | 456 | 462 | 469 | 474 | 481 | 487 | 492 | 500 | 506 | 513 | 520 | 527 | 533 | 540 | 547 | 554 | 562 | 567 | 572 | 578 | 583 | 588 | 595 | 601 | 607 | 612 | 618 | 626 | 633 | 639 | 645 | 653 | 661 | 666 | 674 | 681
180 | 1.5167 | 13 | 30 | 64 | 108 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 2 | 5 | 11 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 14 | 19 | 24 | 32 | 37 | 44 | 50 | 55 | 63 | 68 | 75 | 81 | 87 | 94 | 99 | 105 | 110 | 118 | 126 | 134 | 139 | 144 | 152 | 158 | 165 | 173 | 181 | 187 | 194 | 201 | 206 | 213 | 219 | 224 | 229 | 234 | 239 | 244 | 252 | 259 | 264 | 269 | 274 | 281 | 287 | 295 | 301 | 307 | 314 | 322 | 328 | 335 | 341 | 348 | 354 | 362 | 367 | 374 | 379 | 385 | 391 | 399 | 406 | 411 | 417 | 424 | 432 | 439 | 446 | 454 | 459 | 465 | 470 | 477 | 485 | 493 | 500 | 505 | 512 | 520 | 526 | 532 | 539 | 545 | 553 | 561 | 566 | 571 | 576 | 583 | 588 | 594 | 601 | 608 | 615 | 620 | 626 | 633 | 641 | 646 | 654 | 660 | 665
181 | 1.9407 | 10 | 28 | 67 | 120 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 2 | 5 | 11 | 19 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 14 | 19 | 24 | 29 | 37 | 45 | 52 | 57 | 64 | 71 | 76 | 82 | 89 | 95 | 101 | 109 | 115 | 120 | 125 | 133 | 140 | 145 | 150 | 158 | 165 | 172 | 177 | 182 | 187 | 192 | 200 | 205 | 213 | 220 | 227 | 233 | 239 | 244 | 249 | 257 | 262 | 270 | 275 | 283 | 290 | 297 | 303 | 310 | 318 | 325 | 331 | 339 | 345 | 353 | 359 | 366 | 372 | 380 | 386 | 394 | 401 | 406 | 411 | 416 | 421 | 426 | 434 | 440 | 447 | 453 | 459 | 467 | 475 | 481 | 489 | 496 | 503 | 509 | 514 | 519 | 526 | 531 | 536 | 541 | 547 | 554 | 559 | 564 | 570 | 577 | 585 | 593 | 601 | 608 | 613 | 618 | 626 | 633 | 641 | 646 | 652 | 659 | 665
182 | 1.1539 | 9 | 19 | 44 | 72 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 4 | 8 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 18 | 24 | 30 | 35 | 43 | 50 | 57 | 62 | 68 | 73 | 81 | 89 | 95 | 101 | 107 | 114 | 120 | 126 | 131 | 138 | 143 | 150 | 156 | 163 | 170 | 178 | 184 | 192 | 198 | 206 | 211 | 217 | 222 | 230 | 236 | 241 | 248 | 253 | 258 | 265 | 271 | 276 | 282 | 288 | 294 | 302 | 307 | 314 | 320 | 328 | 334 | 340 | 347 | 353 | 359 | 367 | 373 | 381 | 387 | 392 | 398 | 405 | 412 | 417 | 422 | 427 | 435 | 440 | 445 | 452 | 457 | 464 | 469 | 475 | 480 | 486 | 494 | 501 | 507 | 513 | 518 | 524 | 532 | 540 | 545 | 551 | 557 | 563 | 569 | 576 | 584 | 591 | 596 | 601 | 608 | 613 | 620 | 625 | 631 | 638 | 646 | 653
183 | 1.1353 | 7 | 19 | 41 | 74 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 1 | 4 | 7 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 12 | 17 | 25 | 31 | 39 | 44 | 51 | 57 | 62 | 69 | 76 | 82 | 88 | 94 | 100 | 106 | 113 | 121 | 126 | 133 | 138 | 145 | 152 | 160 | 165 | 170 | 176 | 182 | 190 | 195 | 201 | 206 | 211 | 218 | 225 | 230 | 237 | 243 | 251 | 258 | 263 | 268 | 275 | 280 | 288 | 293 | 299 | 306 | 314 | 321 | 329 | 334 | 341 | 349 | 355 | 360 | 367 | 373 | 379 | 386 | 392 | 399 | 406 | 413 | 419 | 425 | 431 | 437 | 445 | 451 | 458 | 464 | 471 | 476 | 484 | 489 | 495 | 502 | 508 | 515 | 520 | 528 | 534 | 542 | 549 | 555 | 562 | 567 | 575 | 583 | 589 | 595 | 603 | 609 | 615 | 620 | 625 | 633 | 638 | 645 | 653 | 659 | 667
184 | 1.6915 | 9 | 33 | 67 | 111 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 2 | 6 | 11 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 5 | 11 | 17 | 24 | 32 | 37 | 45 | 51 | 56 | 64 | 71 | 78 | 86 | 93 | 101 | 109 | 115 | 121 | 127 | 132 | 139 | 144 | 150 | 158 | 163 | 170 | 175 | 180 | 185 | 193 | 199 | 207 | 213 | 220 | 226 | 234 | 240 | 245 | 251 | 256 | 264 | 272 | 277 | 285 | 291 | 297 | 302 | 309 | 314 | 321 | 328 | 334 | 339 | 345 | 353 | 359 | 367 | 372 | 379 | 385 | 390 | 395 | 402 | 409 | 417 | 422 | 430 | 436 | 444 | 451 | 456 | 463 | 471 | 478 | 484 | 491 | 497 | 505 | 511 | 519 | 524 | 532 | 538 | 543 | 551 | 556 | 564 | 569 | 577 | 585 | 592 | 599 | 605 | 611 | 618 | 625 | 632 | 639 | 646 | 652 | 659 | 667 | 673 | 679
185 | 1.5505 | 14 | 38 | 77 | 116 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 2 | 6 | 13 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 16 | 21 | 26 | 33 | 38 | 44 | 50 | 57 | 63 | 68 | 73 | 79 | 86 | 94 | 101 | 109 | 117 | 122 | 127 | 134 | 141 | 146 | 153 | 158 | 166 | 173 | 179 | 184 | 190 | 198 | 204 | 211 | 218 | 224 | 231 | 239 | 246 | 253 | 261 | 269 | 277 | 284 | 291 | 297 | 303 | 311 | 316 | 322 | 328 | 336 | 341 | 346 | 353 | 361 | 366 | 373 | 381 | 388 | 396 | 404 | 412 | 418 | 426 | 431 | 436 | 444 | 451 | 459 | 465 | 471 | 479 | 485 | 493 | 501 | 507 | 514 | 522 | 528 | 534 | 542 | 550 | 558 | 565 | 570 | 576 | 582 | 589 | 595 | 601 | 607 | 614 | 621 | 628 | 634 | 640 | 648 | 656 | 663 | 669 | 675 | 680 | 688 | 693
186 | 1.8979 | 12 | 39 | 72 | 116 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 2 | 6 | 10 | 18 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 8 | 14 | 21 | 28 | 36 | 44 | 52 | 59 | 67 | 72 | 79 | 87 | 92 | 99 | 104 | 109 | 114 | 120 | 125 | 133 | 138 | 144 | 150 | 155 | 161 | 166 | 173 | 178 | 185 | 190 | 196 | 201 | 209 | 214 | 219 | 225 | 231 | 236 | 243 | 248 | 255 | 262 | 268 | 276 | 284 | 291 | 296 | 304 | 309 | 315 | 323 | 328 | 334 | 342 | 349 | 356 | 362 | 367 | 374 | 382 | 387 | 392 | 399 | 405 | 410 | 415 | 421 | 428 | 433 | 440 | 447 | 455 | 460 | 465 | 470 | 477 | 484 | 490 | 498 | 503 | 510 | 516 | 523 | 529 | 537 | 543 | 551 | 557 | 564 | 572 | 580 | 587 | 592 | 599 | 606 | 611 | 618 | 626 | 634 | 641 | 647 | 654 | 660 | 668
187 | 1.5526 | 14 | 32 | 68 | 101 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 3 | 5 | 11 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 13 | 21 | 27 | 35 | 41 | 46 | 53 | 60 | 66 | 74 | 79 | 84 | 91 | 97 | 103 | 110 | 116 | 124 | 132 | 140 | 148 | 153 | 160 | 166 | 173 | 179 | 187 | 195 | 202 | 210 | 216 | 222 | 230 | 236 | 241 | 247 | 252 | 257 | 263 | 270 | 278 | 283 | 289 | 296 | 304 | 310 | 318 | 323 | 331 | 337 | 345 | 352 | 358 | 366 | 374 | 382 | 388 | 396 | 403 | 408 | 416 | 423 | 428 | 433 | 440 | 448 | 454 | 462 | 468 | 474 | 480 | 485 | 491 | 499 | 507 | 514 | 521 | 529 | 537 | 542 | 547 | 555 | 562 | 569 | 574 | 582 | 587 | 592 | 599 | 604 | 610 | 617 | 623 | 630 | 637 | 642 | 650 | 657 | 664 | 669 | 674 | 679 | 686
188 | 1.2653 | 8 | 20 | 51 | 88 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 3 | 8 | 13 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 15 | 23 | 30 | 37 | 45 | 50 | 56 | 63 | 68 | 74 | 82 | 90 | 95 | 100 | 105 | 113 | 120 | 126 | 132 | 137 | 145 | 151 | 157 | 164 | 170 | 176 | 183 | 189 | 195 | 200 | 206 | 214 | 222 | 228 | 236 | 244 | 251 | 257 | 265 | 272 | 280 | 285 | 290 | 295 | 300 | 306 | 311 | 317 | 322 | 330 | 335 | 340 | 348 | 356 | 361 | 369 | 376 | 382 | 387 | 392 | 400 | 408 | 415 | 421 | 429 | 436 | 443 | 450 | 455 | 461 | 468 | 476 | 481 | 487 | 493 | 500 | 505 | 511 | 516 | 521 | 527 | 533 | 541 | 546 | 551 | 558 | 563 | 569 | 574 | 580 | 588 | 593 | 598 | 603 | 609 | 617 | 623 | 628 | 633 | 640 | 648 | 656 | 662
189 | 1.3787 | 9 | 27 | 54 | 86 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 2 | 5 | 9 | 14 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 11 | 17 | 23 | 28 | 36 | 44 | 49 | 56 | 62 | 68 | 74 | 80 | 88 | 93 | 99 | 105 | 110 | 115 | 122 | 129 | 134 | 142 | 149 | 156 | 164 | 169 | 177 | 185 | 191 | 196 | 204 | 210 | 216 | 224 | 229 | 236 | 244 | 250 | 256 | 264 | 272 | 277 | 284 | 291 | 299 | 307 | 313 | 320 | 327 | 335 | 340 | 348 | 355 | 363 | 368 | 374 | 381 | 388 | 394 | 399 | 406 | 413 | 421 | 426 | 434 | 439 | 445 | 450 | 458 | 466 | 472 | 479 | 486 | 494 | 500 | 505 | 511 | 516 | 521 | 529 | 535 | 541 | 547 | 554 | 560 | 567 | 575 | 580 | 587 | 595 | 601 | 607 | 613 | 621 | 628 | 635 | 643 | 649 | 657 | 663 | 671 | 676 | 683
190 | 1.1798 | 12 | 29 | 50 | 86 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 2 | 5 | 8 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 14 | 21 | 26 | 31 | 36 | 42 | 50 | 56 | 62 | 68 | 75 | 83 | 91 | 97 | 104 | 110 | 116 | 122 | 128 | 135 | 140 | 145 | 151 | 159 | 167 | 175 | 183 | 188 | 193 | 198 | 204 | 210 | 215 | 220 | 225 | 230 | 237 | 243 | 251 | 257 | 263 | 268 | 276 | 282 | 287 | 294 | 302 | 309 | 315 | 320 | 327 | 332 | 337 | 344 | 352 | 359 | 365 | 370 | 378 | 385 | 393 | 399 | 404 | 411 | 418 | 425 | 430 | 435 | 443 | 449 | 456 | 461 | 469 | 474 | 480 | 486 | 494 | 500 | 505 | 512 | 520 | 527 | 535 | 543 | 551 | 559 | 566 | 571 | 576 | 582 | 589 | 596 | 604 | 610 | 616 | 624 | 630 | 635 | 641 | 648 | 655 | 662 | 669
191 | 1.419 | 10 | 22 | 49 | 82 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 2 | 4 | 8 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 6 | 12 | 17 | 22 | 29 | 36 | 43 | 50 | 56 | 63 | 71 | 77 | 82 | 88 | 96 | 104 | 112 | 118 | 124 | 130 | 137 | 143 | 148 | 155 | 163 | 169 | 176 | 183 | 189 | 195 | 202 | 207 | 214 | 219 | 225 | 231 | 236 | 243 | 248 | 255 | 260 | 266 | 271 | 278 | 284 | 292 | 299 | 307 | 315 | 321 | 328 | 336 | 344 | 349 | 356 | 362 | 370 | 378 | 385 | 390 | 398 | 403 | 409 | 414 | 419 | 427 | 433 | 438 | 443 | 450 | 457 | 465 | 471 | 476 | 484 | 492 | 498 | 503 | 511 | 518 | 523 | 529 | 536 | 542 | 547 | 554 | 559 | 566 | 574 | 579 | 585 | 590 | 598 | 604 | 610 | 616 | 622 | 628 | 636 | 643 | 648 | 655 | 660 | 668
192 | 1.0474 | 10 | 19 | 46 | 67 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 3 | 6 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 7 | 15 | 23 | 31 | 39 | 47 | 53 | 60 | 68 | 75 | 80 | 87 | 92 | 99 | 105 | 113 | 119 | 127 | 134 | 139 | 144 | 152 | 160 | 168 | 175 | 182 | 189 | 195 | 202 | 210 | 217 | 223 | 229 | 236 | 242 | 248 | 256 | 262 | 269 | 274 | 279 | 285 | 290 | 296 | 302 | 308 | 313 | 318 | 325 | 333 | 338 | 346 | 353 | 359 | 367 | 374 | 379 | 387 | 392 | 397 | 402 | 408 | 414 | 422 | 429 | 435 | 442 | 448 | 453 | 458 | 463 | 468 | 476 | 482 | 489 | 494 | 501 | 507 | 512 | 518 | 523 | 530 | 538 | 543 | 548 | 553 | 559 | 565 | 573 | 580 | 585 | 592 | 597 | 605 | 610 | 616 | 621 | 629 | 634 | 639 | 646 | 651 | 657 | 665
193 | 1.7044 | 12 | 31 | 64 | 100 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 3 | 6 | 10 | 16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 6 | 11 | 19 | 24 | 29 | 37 | 44 | 51 | 56 | 64 | 70 | 78 | 85 | 93 | 99 | 105 | 112 | 117 | 125 | 131 | 137 | 142 | 147 | 154 | 160 | 165 | 171 | 176 | 182 | 187 | 195 | 200 | 207 | 213 | 221 | 229 | 234 | 242 | 248 | 256 | 262 | 269 | 276 | 284 | 290 | 298 | 306 | 313 | 321 | 329 | 334 | 342 | 350 | 355 | 363 | 371 | 376 | 384 | 391 | 399 | 406 | 412 | 419 | 426 | 431 | 438 | 446 | 454 | 461 | 469 | 477 | 485 | 493 | 499 | 504 | 511 | 519 | 526 | 534 | 542 | 547 | 552 | 560 | 566 | 573 | 581 | 589 | 596 | 602 | 608 | 616 | 621 | 626 | 631 | 636 | 644 | 652 | 659 | 666 | 671 | 678 | 685 | 693 | 698
194 | 1.7627 | 9 | 27 | 63 | 108 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 5 | 11 | 18 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 13 | 18 | 24 | 29 | 36 | 44 | 49 | 54 | 60 | 66 | 74 | 80 | 85 | 91 | 96 | 102 | 109 | 117 | 123 | 128 | 135 | 142 | 148 | 153 | 158 | 166 | 174 | 180 | 185 | 190 | 196 | 201 | 207 | 214 | 221 | 229 | 235 | 240 | 246 | 252 | 260 | 268 | 273 | 280 | 288 | 296 | 301 | 307 | 315 | 320 | 328 | 333 | 340 | 347 | 353 | 358 | 366 | 374 | 380 | 388 | 396 | 402 | 409 | 417 | 424 | 432 | 439 | 444 | 450 | 458 | 463 | 470 | 476 | 482 | 487 | 494 | 502 | 507 | 513 | 519 | 526 | 533 | 538 | 543 | 549 | 555 | 561 | 569 | 574 | 579 | 584 | 589 | 596 | 604 | 609 | 615 | 620 | 627 | 634 | 641 | 647 | 654 | 661
195 | 1.1954 | 12 | 23 | 47 | 76 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 3 | 4 | 7 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 11 | 19 | 27 | 35 | 42 | 47 | 54 | 60 | 67 | 73 | 79 | 87 | 94 | 99 | 107 | 113 | 120 | 127 | 134 | 140 | 147 | 152 | 159 | 164 | 170 | 176 | 183 | 188 | 196 | 201 | 206 | 213 | 218 | 223 | 230 | 238 | 245 | 251 | 257 | 263 | 268 | 274 | 282 | 290 | 298 | 303 | 309 | 315 | 321 | 326 | 333 | 340 | 348 | 353 | 360 | 367 | 372 | 378 | 383 | 388 | 395 | 403 | 411 | 419 | 425 | 432 | 437 | 445 | 451 | 457 | 463 | 470 | 477 | 484 | 489 | 495 | 500 | 505 | 512 | 517 | 525 | 533 | 539 | 547 | 552 | 558 | 565 | 572 | 577 | 582 | 587 | 593 | 598 | 605 | 611 | 617 | 623 | 630 | 636 | 641 | 649 | 657 | 665
196 | 1.9928 | 14 | 44 | 84 | 142 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 2 | 7 | 13 | 23 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 7 | 14 | 22 | 29 | 34 | 39 | 45 | 53 | 60 | 66 | 71 | 78 | 85 | 91 | 96 | 104 | 111 | 117 | 122 | 129 | 135 | 140 | 148 | 154 | 161 | 166 | 174 | 179 | 185 | 193 | 199 | 204 | 212 | 218 | 224 | 229 | 234 | 239 | 247 | 254 | 260 | 265 | 272 | 277 | 283 | 291 | 298 | 305 | 312 | 319 | 327 | 335 | 343 | 349 | 355 | 363 | 368 | 376 | 381 | 389 | 397 | 404 | 410 | 417 | 423 | 428 | 434 | 441 | 447 | 454 | 461 | 468 | 476 | 481 | 489 | 495 | 503 | 511 | 519 | 527 | 533 | 540 | 546 | 554 | 560 | 567 | 574 | 580 | 586 | 591 | 596 | 601 | 607 | 613 | 618 | 625 | 633 | 641 | 648 | 655 | 662 | 669 | 677 | 682
197 | 1.7173 | 11 | 34 | 77 | 122 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 2 | 6 | 13 | 20 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 7 | 12 | 18 | 25 | 30 | 35 | 42 | 47 | 54 | 59 | 66 | 73 | 79 | 86 | 92 | 100 | 105 | 112 | 120 | 125 | 132 | 140 | 145 | 151 | 158 | 166 | 173 | 180 | 187 | 193 | 201 | 209 | 217 | 222 | 229 | 236 | 243 | 249 | 256 | 263 | 268 | 274 | 280 | 288 | 294 | 302 | 307 | 315 | 321 | 329 | 334 | 340 | 345 | 353 | 358 | 364 | 369 | 377 | 384 | 390 | 398 | 406 | 411 | 417 | 424 | 430 | 436 | 441 | 446 | 451 | 459 | 467 | 474 | 479 | 486 | 492 | 497 | 505 | 512 | 518 | 525 | 533 | 541 | 547 | 552 | 558 | 565 | 571 | 579 | 584 | 592 | 598 | 606 | 613 | 621 | 626 | 632 | 640 | 648 | 656 | 663 | 668 | 674 | 682
198 | 1.5635 | 15 | 34 | 69 | 110 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 3 | 6 | 11 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 13 | 19 | 25 | 31 | 36 | 44 | 52 | 58 | 63 | 70 | 77 | 85 | 93 | 99 | 106 | 113 | 119 | 125 | 132 | 139 | 145 | 152 | 160 | 166 | 173 | 179 | 186 | 192 | 199 | 207 | 214 | 222 | 227 | 233 | 239 | 247 | 253 | 260 | 265 | 273 | 279 | 286 | 294 | 299 | 306 | 313 | 318 | 324 | 329 | 334 | 342 | 349 | 354 | 359 | 366 | 371 | 376 | 382 | 390 | 397 | 405 | 411 | 418 | 424 | 431 | 437 | 442 | 450 | 458 | 466 | 473 | 480 | 488 | 494 | 500 | 508 | 516 | 522 | 530 | 536 | 541 | 548 | 556 | 561 | 566 | 573 | 578 | 585 | 592 | 598 | 605 | 613 | 619 | 625 | 633 | 640 | 648 | 654 | 662 | 668 | 675 | 683 | 688
199 | 1.9751 | 14 | 40 | 88 | 128 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 3 | 6 | 14 | 20 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 6 | 13 | 19 | 27 | 35 | 41 | 48 | 53 | 60 | 65 | 73 | 78 | 83 | 91 | 96 | 104 | 111 | 117 | 122 | 130 | 136 | 141 | 146 | 153 | 160 | 167 | 172 | 180 | 185 | 193 | 198 | 206 | 212 | 218 | 226 | 232 | 238 | 244 | 252 | 260 | 267 | 273 | 280 | 288 | 293 | 300 | 306 | 314 | 320 | 326 | 332 | 339 | 347 | 354 | 362 | 368 | 375 | 382 | 387 | 394 | 399 | 405 | 413 | 418 | 426 | 432 | 438 | 443 | 449 | 454 | 462 | 470 | 475 | 480 | 486 | 492 | 497 | 503 | 510 | 516 | 521 | 529 | 537 | 542 | 547 | 555 | 562 | 567 | 575 | 582 | 587 | 594 | 600 | 606 | 614 | 621 | 629 | 636 | 644 | 652 | 657 | 664 | 670 | 677
200 | 1.7762 | 13 | 38 | 76 | 126 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 2 | 6 | 12 | 21 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 7 | 14 | 19 | 26 | 34 | 39 | 44 | 52 | 60 | 66 | 72 | 78 | 85 | 91 | 96 | 101 | 108 | 113 | 119 | 124 | 132 | 140 | 148 | 153 | 159 | 164 | 171 | 178 | 183 | 190 | 196 | 203 | 211 | 216 | 223 | 228 | 235 | 243 | 250 | 255 | 261 | 269 | 276 | 282 | 288 | 293 | 299 | 307 | 314 | 321 | 326 | 333 | 341 | 348 | 354 | 362 | 368 | 373 | 379 | 385 | 392 | 398 | 404 | 412 | 419 | 427 | 435 | 443 | 449 | 455 | 463 | 468 | 473 | 481 | 486 | 491 | 496 | 504 | 512 | 518 | 524 | 530 | 536 | 544 | 552 | 558 | 564 | 572 | 579 | 585 | 593 | 600 | 607 | 613 | 618 | 623 | 630 | 638 | 643 | 651 | 657 | 665 | 671 | 679
201 | 1.5652 | 15 | 28 | 52 | 87 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 3 | 5 | 8 | 14 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 14 | 21 | 26 | 32 | 37 | 44 | 52 | 60 | 65 | 71 | 79 | 85 | 90 | 98 | 105 | 110 | 117 | 124 | 132 | 138 | 144 | 149 | 155 | 160 | 166 | 173 | 179 | 185 | 192 | 200 | 205 | 212 | 217 | 225 | 230 | 237 | 242 | 248 | 255 | 260 | 267 | 274 | 279 | 287 | 294 | 299 | 306 | 313 | 318 | 326 | 332 | 338 | 345 | 353 | 359 | 364 | 371 | 378 | 385 | 393 | 400 | 405 | 411 | 417 | 423 | 431 | 436 | 441 | 447 | 454 | 461 | 469 | 476 | 481 | 486 | 492 | 497 | 503 | 509 | 515 | 520 | 525 | 532 | 540 | 548 | 556 | 564 | 570 | 578 | 583 | 591 | 599 | 604 | 612 | 617 | 623 | 628 | 634 | 642 | 648 | 656 | 662 | 669
202 | 1.0382 | 11 | 24 | 40 | 63 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 4 | 6 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 15 | 22 | 30 | 38 | 44 | 49 | 55 | 60 | 66 | 72 | 80 | 86 | 94 | 99 | 104 | 111 | 117 | 122 | 130 | 135 | 143 | 148 | 153 | 158 | 165 | 171 | 176 | 182 | 187 | 193 | 201 | 206 | 213 | 219 | 225 | 231 | 239 | 244 | 252 | 260 | 265 | 270 | 275 | 283 | 290 | 295 | 303 | 311 | 318 | 325 | 333 | 338 | 346 | 353 | 360 | 365 | 372 | 380 | 388 | 396 | 401 | 407 | 415 | 422 | 428 | 436 | 443 | 450 | 458 | 463 | 471 | 478 | 485 | 493 | 501 | 508 | 515 | 521 | 528 | 536 | 542 | 549 | 557 | 563 | 569 | 574 | 579 | 587 | 594 | 600 | 605 | 610 | 617 | 623 | 630 | 637 | 645 | 653 | 658 | 663 | 669 | 675 | 682
203 | 1.2555 | 11 | 22 | 53 | 81 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 4 | 10 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 11 | 16 | 22 | 27 | 34 | 39 | 46 | 51 | 58 | 64 | 70 | 77 | 84 | 91 | 97 | 104 | 110 | 116 | 121 | 126 | 133 | 139 | 146 | 151 | 157 | 165 | 171 | 176 | 183 | 189 | 194 | 202 | 208 | 213 | 221 | 229 | 237 | 245 | 253 | 258 | 266 | 273 | 278 | 283 | 291 | 299 | 305 | 311 | 316 | 323 | 331 | 336 | 341 | 346 | 351 | 357 | 362 | 367 | 374 | 379 | 385 | 390 | 395 | 403 | 408 | 415 | 421 | 427 | 434 | 440 | 445 | 453 | 460 | 468 | 473 | 478 | 486 | 491 | 499 | 504 | 512 | 520 | 526 | 531 | 538 | 545 | 550 | 556 | 563 | 570 | 578 | 583 | 589 | 595 | 601 | 609 | 616 | 621 | 628 | 634 | 641 | 648 | 655
204 | 1.3337 | 11 | 25 | 54 | 84 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 2 | 4 | 9 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 13 | 19 | 27 | 33 | 39 | 47 | 53 | 61 | 67 | 74 | 80 | 88 | 95 | 101 | 108 | 116 | 121 | 127 | 135 | 140 | 145 | 150 | 155 | 162 | 168 | 175 | 181 | 186 | 193 | 198 | 204 | 209 | 214 | 222 | 227 | 235 | 241 | 246 | 251 | 258 | 265 | 272 | 279 | 284 | 290 | 298 | 304 | 312 | 317 | 322 | 327 | 334 | 341 | 346 | 354 | 359 | 367 | 373 | 378 | 386 | 393 | 401 | 406 | 413 | 421 | 429 | 435 | 442 | 447 | 454 | 462 | 468 | 473 | 480 | 487 | 494 | 499 | 505 | 513 | 519 | 524 | 530 | 538 | 544 | 552 | 559 | 564 | 571 | 577 | 584 | 592 | 599 | 607 | 614 | 621 | 626 | 632 | 639 | 647 | 652 | 660 | 668 | 676
205 | 1.2479 | 9 | 22 | 46 | 76 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 2 | 4 | 8 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 11 | 17 | 23 | 30 | 36 | 43 | 48 | 53 | 58 | 66 | 74 | 81 | 86 | 91 | 97 | 105 | 113 | 118 | 125 | 132 | 140 | 148 | 154 | 160 | 166 | 172 | 180 | 186 | 191 | 196 | 203 | 211 | 217 | 225 | 231 | 236 | 241 | 247 | 254 | 259 | 265 | 270 | 275 | 282 | 289 | 294 | 299 | 305 | 311 | 317 | 322 | 329 | 334 | 342 | 349 | 356 | 363 | 368 | 373 | 381 | 389 | 395 | 402 | 407 | 414 | 420 | 426 | 434 | 441 | 447 | 455 | 460 | 466 | 472 | 478 | 486 | 491 | 498 | 506 | 511 | 516 | 524 | 532 | 539 | 547 | 554 | 560 | 567 | 573 | 579 | 587 | 592 | 597 | 604 | 610 | 618 | 625 | 633 | 638 | 645 | 653 | 659 | 666
206 | 1.7359 | 14 | 28 | 65 | 105 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 2 | 4 | 10 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 15 | 22 | 30 | 37 | 43 | 48 | 56 | 62 | 67 | 73 | 80 | 86 | 91 | 96 | 104 | 112 | 119 | 124 | 131 | 138 | 144 | 150 | 156 | 164 | 171 | 179 | 186 | 191 | 198 | 204 | 212 | 219 | 226 | 232 | 238 | 245 | 250 | 256 | 261 | 269 | 277 | 282 | 288 | 294 | 300 | 306 | 311 | 318 | 325 | 330 | 337 | 342 | 347 | 353 | 358 | 366 | 373 | 378 | 384 | 391 | 398 | 405 | 410 | 418 | 424 | 431 | 436 | 444 | 452 | 458 | 466 | 471 | 479 | 486 | 494 | 500 | 505 | 510 | 517 | 523 | 529 | 534 | 539 | 545 | 550 | 557 | 562 | 567 | 573 | 579 | 586 | 594 | 601 | 607 | 613 | 620 | 628 | 634 | 640 | 648 | 654 | 660 | 667
207 | 1.7867 | 18 | 40 | 73 | 109 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 3 | 6 | 11 | 18 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 8 | 15 | 21 | 27 | 32 | 40 | 48 | 53 | 59 | 66 | 73 | 78 | 85 | 90 | 96 | 101 | 108 | 113 | 118 | 124 | 131 | 136 | 144 | 150 | 155 | 161 | 169 | 176 | 184 | 189 | 197 | 203 | 210 | 217 | 222 | 230 | 235 | 242 | 249 | 256 | 261 | 267 | 274 | 279 | 284 | 291 | 299 | 307 | 313 | 321 | 327 | 333 | 339 | 347 | 355 | 361 | 367 | 373 | 378 | 384 | 389 | 397 | 405 | 410 | 418 | 424 | 430 | 436 | 444 | 451 | 457 | 462 | 470 | 478 | 483 | 490 | 498 | 505 | 513 | 521 | 529 | 536 | 542 | 550 | 558 | 566 | 573 | 578 | 586 | 591 | 599 | 605 | 610 | 616 | 623 | 629 | 637 | 642 | 647 | 655 | 660 | 665 | 673 | 678
208 | 1.3771 | 14 | 32 | 59 | 88 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 2 | 5 | 10 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 14 | 21 | 29 | 35 | 41 | 46 | 51 | 56 | 61 | 68 | 74 | 81 | 87 | 93 | 101 | 106 | 111 | 119 | 125 | 130 | 138 | 143 | 148 | 156 | 164 | 172 | 179 | 186 | 192 | 200 | 206 | 214 | 220 | 226 | 234 | 241 | 249 | 257 | 263 | 269 | 276 | 283 | 290 | 296 | 303 | 309 | 316 | 323 | 328 | 334 | 341 | 348 | 353 | 359 | 367 | 373 | 378 | 383 | 389 | 395 | 401 | 407 | 415 | 422 | 429 | 436 | 443 | 448 | 454 | 460 | 468 | 473 | 478 | 485 | 491 | 498 | 504 | 511 | 517 | 525 | 531 | 537 | 543 | 549 | 554 | 559 | 566 | 573 | 581 | 589 | 595 | 601 | 607 | 613 | 621 | 627 | 635 | 642 | 650 | 656 | 664 | 670 | 678
209 | 1.0613 | 6 | 19 | 39 | 68 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 1 | 3 | 7 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 13 | 19 | 25 | 31 | 36 | 41 | 47 | 55 | 63 | 69 | 76 | 84 | 89 | 96 | 104 | 112 | 120 | 127 | 134 | 139 | 147 | 153 | 161 | 168 | 173 | 178 | 185 | 190 | 196 | 201 | 206 | 211 | 218 | 223 | 228 | 234 | 239 | 245 | 251 | 256 | 264 | 270 | 277 | 282 | 289 | 296 | 302 | 310 | 316 | 323 | 331 | 337 | 344 | 352 | 359 | 367 | 374 | 379 | 386 | 392 | 398 | 404 | 410 | 415 | 420 | 427 | 434 | 442 | 447 | 453 | 460 | 467 | 473 | 480 | 488 | 494 | 499 | 507 | 512 | 518 | 526 | 533 | 540 | 546 | 552 | 558 | 564 | 571 | 576 | 582 | 590 | 598 | 605 | 611 | 616 | 622 | 627 | 633 | 640 | 645 | 653 | 660 | 668
210 | 1.5518 | 14 | 30 | 66 | 98 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 2 | 5 | 10 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 15 | 22 | 28 | 36 | 44 | 49 | 57 | 65 | 71 | 77 | 85 | 90 | 97 | 104 | 109 | 116 | 121 | 127 | 133 | 140 | 148 | 154 | 159 | 164 | 171 | 177 | 184 | 190 | 197 | 202 | 210 | 217 | 225 | 231 | 237 | 242 | 249 | 254 | 262 | 268 | 275 | 281 | 288 | 296 | 302 | 307 | 312 | 319 | 325 | 332 | 339 | 344 | 351 | 359 | 364 | 372 | 380 | 388 | 393 | 401 | 406 | 411 | 418 | 423 | 430 | 436 | 443 | 450 | 456 | 461 | 469 | 475 | 483 | 489 | 495 | 500 | 506 | 511 | 518 | 523 | 529 | 537 | 542 | 549 | 554 | 560 | 568 | 574 | 582 | 587 | 594 | 600 | 606 | 611 | 619 | 626 | 633 | 640 | 645 | 653 | 660 | 666 | 672
211 | 1.4624 | 15 | 37 | 62 | 105 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 3 | 6 | 10 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 10 | 15 | 22 | 30 | 38 | 46 | 54 | 59 | 65 | 72 | 78 | 86 | 93 | 100 | 107 | 112 | 117 | 123 | 131 | 139 | 145 | 151 | 159 | 165 | 172 | 179 | 184 | 190 | 198 | 206 | 212 | 218 | 226 | 234 | 242 | 250 | 258 | 263 | 271 | 278 | 285 | 293 | 301 | 308 | 315 | 320 | 325 | 330 | 336 | 342 | 350 | 355 | 362 | 367 | 372 | 378 | 383 | 389 | 395 | 402 | 410 | 416 | 424 | 430 | 438 | 445 | 453 | 461 | 467 | 474 | 482 | 488 | 494 | 500 | 507 | 513 | 520 | 527 | 533 | 539 | 544 | 551 | 556 | 562 | 569 | 575 | 582 | 588 | 594 | 599 | 604 | 609 | 617 | 624 | 630 | 637 | 645 | 650 | 655 | 660 | 668 | 674 | 682
212 | 1.4372 | 13 | 35 | 67 | 96 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 3 | 6 | 11 | 15 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 11 | 16 | 23 | 30 | 35 | 43 | 51 | 56 | 64 | 69 | 77 | 83 | 91 | 96 | 102 | 107 | 115 | 122 | 130 | 135 | 142 | 149 | 155 | 162 | 168 | 175 | 183 | 191 | 198 | 204 | 209 | 215 | 220 | 225 | 231 | 237 | 245 | 251 | 256 | 264 | 269 | 277 | 283 | 288 | 294 | 299 | 307 | 314 | 320 | 326 | 333 | 341 | 347 | 352 | 360 | 366 | 374 | 380 | 388 | 396 | 404 | 412 | 419 | 426 | 431 | 438 | 444 | 450 | 457 | 463 | 468 | 474 | 480 | 487 | 495 | 500 | 505 | 512 | 520 | 526 | 533 | 539 | 545 | 552 | 558 | 566 | 574 | 579 | 586 | 593 | 598 | 605 | 612 | 618 | 625 | 633 | 641 | 647 | 653 | 660 | 665 | 672 | 679
213 | 1.3458 | 9 | 26 | 55 | 86 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 2 | 5 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 11 | 17 | 23 | 28 | 33 | 41 | 49 | 57 | 65 | 70 | 75 | 80 | 87 | 92 | 100 | 106 | 111 | 118 | 125 | 131 | 139 | 145 | 151 | 159 | 166 | 172 | 177 | 184 | 190 | 198 | 205 | 210 | 218 | 223 | 228 | 234 | 240 | 248 | 255 | 262 | 270 | 276 | 283 | 291 | 296 | 303 | 311 | 319 | 327 | 332 | 339 | 346 | 351 | 359 | 365 | 370 | 375 | 380 | 385 | 391 | 396 | 404 | 412 | 418 | 424 | 429 | 435 | 443 | 448 | 453 | 458 | 465 | 473 | 479 | 486 | 494 | 499 | 506 | 514 | 519 | 524 | 529 | 537 | 543 | 551 | 556 | 561 | 566 | 571 | 577 | 584 | 589 | 597 | 604 | 611 | 616 | 622 | 629 | 637 | 642 | 648 | 656 | 664
214 | 1.2748 | 13 | 24 | 51 | 83 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 2 | 4 | 7 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 7 | 14 | 21 | 28 | 36 | 44 | 51 | 59 | 64 | 71 | 78 | 85 | 93 | 98 | 103 | 110 | 118 | 124 | 129 | 134 | 141 | 148 | 153 | 158 | 163 | 171 | 176 | 181 | 188 | 193 | 200 | 206 | 214 | 222 | 227 | 234 | 240 | 247 | 253 | 261 | 269 | 274 | 282 | 287 | 292 | 299 | 306 | 313 | 319 | 326 | 331 | 337 | 343 | 351 | 358 | 366 | 371 | 377 | 382 | 389 | 394 | 401 | 408 | 414 | 421 | 428 | 433 | 441 | 449 | 457 | 464 | 470 | 475 | 483 | 488 | 494 | 499 | 504 | 510 | 515 | 520 | 528 | 533 | 539 | 546 | 554 | 561 | 566 | 571 | 576 | 583 | 590 | 596 | 604 | 612 | 617 | 625 | 632 | 640 | 645 | 650 | 658 | 664 | 672
215 | 1.7005 | 9 | 25 | 61 | 111 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 5 | 10 | 18 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 5 | 11 | 18 | 23 | 29 | 34 | 40 | 46 | 54 | 61 | 66 | 71 | 79 | 87 | 92 | 98 | 105 | 112 | 117 | 123 | 130 | 137 | 145 | 153 | 158 | 164 | 171 | 179 | 186 | 193 | 200 | 206 | 214 | 220 | 226 | 234 | 240 | 247 | 254 | 262 | 267 | 275 | 283 | 288 | 294 | 302 | 307 | 312 | 317 | 324 | 329 | 336 | 344 | 351 | 357 | 365 | 370 | 377 | 385 | 392 | 398 | 403 | 411 | 418 | 423 | 431 | 439 | 447 | 452 | 458 | 465 | 470 | 478 | 483 | 488 | 494 | 502 | 510 | 518 | 523 | 530 | 535 | 541 | 547 | 553 | 559 | 566 | 574 | 579 | 584 | 590 | 598 | 604 | 610 | 616 | 621 | 627 | 635 | 641 | 647 | 655 | 662 | 669 | 675
216 | 1.2884 | 13 | 26 | 56 | 85 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 3 | 5 | 10 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 12 | 17 | 22 | 29 | 35 | 41 | 47 | 54 | 60 | 66 | 71 | 79 | 84 | 89 | 95 | 102 | 108 | 115 | 120 | 126 | 134 | 141 | 149 | 154 | 159 | 164 | 171 | 176 | 184 | 189 | 197 | 204 | 210 | 218 | 223 | 230 | 237 | 244 | 250 | 256 | 261 | 266 | 274 | 282 | 288 | 294 | 301 | 308 | 313 | 321 | 329 | 334 | 341 | 349 | 357 | 362 | 367 | 375 | 382 | 390 | 397 | 403 | 410 | 416 | 424 | 432 | 438 | 446 | 454 | 460 | 466 | 471 | 476 | 482 | 488 | 493 | 500 | 507 | 513 | 521 | 529 | 534 | 542 | 547 | 552 | 560 | 567 | 572 | 579 | 584 | 589 | 595 | 600 | 606 | 613 | 619 | 625 | 630 | 638 | 645 | 651 | 659 | 665
217 | 1.1215 | 8 | 23 | 47 | 78 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 1 | 4 | 7 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8 | 14 | 19 | 26 | 31 | 39 | 47 | 52 | 60 | 65 | 71 | 77 | 83 | 91 | 96 | 101 | 109 | 115 | 120 | 128 | 134 | 140 | 147 | 155 | 160 | 167 | 174 | 181 | 189 | 194 | 201 | 209 | 214 | 219 | 224 | 231 | 237 | 242 | 249 | 257 | 264 | 270 | 278 | 285 | 291 | 298 | 305 | 312 | 319 | 327 | 332 | 339 | 346 | 353 | 359 | 367 | 372 | 380 | 388 | 395 | 403 | 410 | 417 | 423 | 428 | 436 | 443 | 451 | 457 | 464 | 470 | 477 | 483 | 491 | 497 | 502 | 510 | 515 | 520 | 528 | 536 | 542 | 549 | 554 | 561 | 569 | 574 | 579 | 584 | 589 | 594 | 600 | 607 | 614 | 622 | 630 | 635 | 643 | 650 | 658 | 666 | 673 | 681 | 687
218 | 1.0026 | 7 | 16 | 39 | 67 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 1 | 3 | 6 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 7 | 13 | 20 | 25 | 33 | 39 | 47 | 55 | 60 | 65 | 72 | 80 | 85 | 91 | 99 | 107 | 113 | 120 | 126 | 133 | 138 | 143 | 149 | 155 | 162 | 168 | 174 | 181 | 186 | 194 | 200 | 206 | 213 | 218 | 223 | 229 | 236 | 242 | 249 | 256 | 263 | 269 | 275 | 282 | 287 | 294 | 299 | 305 | 312 | 317 | 322 | 329 | 337 | 343 | 348 | 356 | 361 | 366 | 371 | 379 | 387 | 394 | 399 | 407 | 414 | 421 | 427 | 434 | 440 | 445 | 452 | 459 | 465 | 470 | 476 | 483 | 488 | 495 | 503 | 508 | 516 | 521 | 527 | 535 | 543 | 549 | 557 | 562 | 569 | 574 | 580 | 586 | 594 | 599 | 604 | 609 | 615 | 623 | 631 | 639 | 647 | 653 | 659 | 666
219 | 1.6858 | 11 | 33 | 72 | 111 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 5 | 12 | 18 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 15 | 22 | 29 | 37 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 82 | 87 | 93 | 100 | 107 | 113 | 120 | 127 | 132 | 140 | 147 | 154 | 161 | 167 | 174 | 179 | 186 | 194 | 201 | 206 | 212 | 220 | 225 | 232 | 239 | 246 | 252 | 259 | 266 | 271 | 278 | 285 | 291 | 299 | 305 | 311 | 316 | 322 | 330 | 337 | 344 | 352 | 357 | 365 | 373 | 380 | 388 | 395 | 401 | 409 | 416 | 423 | 431 | 438 | 445 | 453 | 459 | 466 | 474 | 480 | 488 | 496 | 501 | 509 | 517 | 522 | 527 | 532 | 540 | 548 | 556 | 562 | 567 | 573 | 579 | 587 | 595 | 601 | 607 | 613 | 618 | 624 | 629 | 635 | 643 | 651 | 656 | 662 | 669 | 674 | 680 | 686
220 | 1.0033 | 8 | 24 | 44 | 66 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 1 | 4 | 7 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 15 | 20 | 27 | 32 | 38 | 44 | 49 | 57 | 64 | 71 | 79 | 87 | 92 | 100 | 106 | 112 | 118 | 125 | 131 | 139 | 144 | 152 | 160 | 165 | 171 | 179 | 186 | 191 | 196 | 203 | 208 | 216 | 222 | 227 | 232 | 237 | 243 | 249 | 255 | 263 | 270 | 275 | 283 | 290 | 297 | 302 | 307 | 315 | 323 | 328 | 335 | 340 | 346 | 353 | 361 | 369 | 375 | 380 | 388 | 395 | 403 | 408 | 416 | 421 | 428 | 435 | 441 | 448 | 453 | 460 | 468 | 475 | 481 | 489 | 496 | 502 | 510 | 517 | 524 | 531 | 536 | 541 | 549 | 557 | 564 | 571 | 579 | 586 | 593 | 600 | 606 | 613 | 620 | 628 | 633 | 638 | 644 | 650 | 656 | 664 | 672 | 680 | 686
221 | 1.1805 | 10 | 23 | 49 | 81 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 4 | 7 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 13 | 20 | 26 | 33 | 41 | 49 | 56 | 61 | 68 | 73 | 79 | 87 | 95 | 102 | 109 | 116 | 123 | 128 | 135 | 141 | 148 | 154 | 160 | 167 | 174 | 182 | 189 | 194 | 202 | 207 | 215 | 220 | 227 | 235 | 240 | 246 | 252 | 257 | 262 | 269 | 276 | 284 | 290 | 298 | 303 | 310 | 315 | 323 | 328 | 333 | 340 | 346 | 354 | 362 | 368 | 374 | 382 | 387 | 394 | 400 | 405 | 412 | 418 | 423 | 428 | 435 | 440 | 447 | 454 | 460 | 467 | 475 | 483 | 488 | 493 | 499 | 504 | 509 | 515 | 521 | 527 | 534 | 542 | 547 | 554 | 559 | 567 | 575 | 581 | 588 | 594 | 599 | 607 | 614 | 620 | 625 | 633 | 640 | 645 | 650 | 655 | 662 | 670
222 | 1.0146 | 6 | 18 | 36 | 58 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 1 | 3 | 6 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8 | 13 | 18 | 24 | 31 | 38 | 45 | 50 | 55 | 61 | 69 | 75 | 81 | 86 | 93 | 99 | 107 | 115 | 120 | 127 | 133 | 140 | 148 | 153 | 161 | 169 | 177 | 182 | 188 | 196 | 201 | 208 | 213 | 221 | 226 | 233 | 241 | 248 | 253 | 258 | 263 | 270 | 275 | 282 | 288 | 294 | 302 | 308 | 315 | 322 | 328 | 335 | 343 | 348 | 354 | 359 | 366 | 371 | 378 | 384 | 390 | 395 | 402 | 407 | 414 | 419 | 424 | 429 | 435 | 443 | 449 | 457 | 465 | 471 | 478 | 485 | 493 | 501 | 509 | 514 | 522 | 530 | 535 | 541 | 546 | 554 | 561 | 569 | 577 | 585 | 593 | 600 | 608 | 615 | 623 | 630 | 636 | 644 | 649 | 654 | 661 | 668 | 675 | 680
223 | 1.8392 | 12 | 31 | 68 | 107 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 6 | 11 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 13 | 18 | 24 | 30 | 37 | 43 | 50 | 55 | 63 | 70 | 77 | 83 | 88 | 95 | 103 | 109 | 114 | 120 | 127 | 133 | 139 | 147 | 152 | 158 | 164 | 171 | 179 | 185 | 192 | 197 | 203 | 210 | 215 | 222 | 227 | 233 | 239 | 246 | 252 | 259 | 264 | 272 | 278 | 286 | 292 | 298 | 305 | 312 | 318 | 324 | 331 | 337 | 344 | 352 | 360 | 368 | 376 | 384 | 389 | 395 | 403 | 408 | 413 | 420 | 425 | 430 | 436 | 442 | 448 | 455 | 461 | 466 | 471 | 479 | 484 | 490 | 497 | 503 | 510 | 517 | 523 | 528 | 534 | 542 | 550 | 556 | 563 | 571 | 579 | 585 | 592 | 597 | 603 | 610 | 615 | 623 | 630 | 638 | 643 | 649 | 655 | 663 | 671
224 | 1.6701 | 9 | 23 | 60 | 111 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 2 | 3 | 9 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 15 | 23 | 29 | 34 | 42 | 49 | 57 | 62 | 70 | 77 | 84 | 90 | 98 | 104 | 112 | 117 | 122 | 128 | 135 | 143 | 151 | 156 | 162 | 168 | 174 | 180 | 188 | 193 | 198 | 203 | 209 | 217 | 225 | 231 | 237 | 244 | 251 | 259 | 264 | 269 | 274 | 281 | 288 | 293 | 301 | 308 | 316 | 323 | 329 | 336 | 343 | 350 | 358 | 366 | 374 | 381 | 388 | 394 | 400 | 406 | 411 | 418 | 425 | 431 | 438 | 445 | 451 | 458 | 466 | 473 | 478 | 486 | 491 | 498 | 506 | 513 | 520 | 525 | 532 | 537 | 542 | 548 | 554 | 562 | 567 | 573 | 579 | 584 | 592 | 597 | 605 | 611 | 619 | 625 | 632 | 638 | 646 | 654 | 661 | 667 | 675 | 681 | 688
225 | 1.4586 | 9 | 30 | 55 | 93 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 2 | 5 | 10 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 14 | 19 | 24 | 32 | 38 | 44 | 49 | 54 | 60 | 66 | 74 | 80 | 85 | 90 | 95 | 100 | 107 | 115 | 122 | 129 | 134 | 139 | 146 | 152 | 158 | 166 | 173 | 179 | 187 | 192 | 200 | 205 | 212 | 219 | 224 | 229 | 236 | 242 | 248 | 255 | 263 | 268 | 274 | 282 | 289 | 297 | 303 | 309 | 314 | 320 | 328 | 333 | 339 | 345 | 352 | 358 | 364 | 369 | 376 | 382 | 389 | 397 | 403 | 411 | 417 | 422 | 427 | 432 | 440 | 445 | 452 | 459 | 464 | 472 | 478 | 484 | 490 | 496 | 503 | 509 | 516 | 521 | 529 | 535 | 540 | 545 | 550 | 556 | 564 | 571 | 578 | 584 | 590 | 596 | 604 | 609 | 615 | 620 | 627 | 633 | 638 | 643 | 649
226 | 1.1062 | 7 | 19 | 39 | 68 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1 | 3 | 6 | 10 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 14 | 21 | 29 | 36 | 44 | 50 | 57 | 64 | 71 | 77 | 82 | 90 | 96 | 102 | 110 | 116 | 121 | 128 | 134 | 142 | 148 | 154 | 159 | 165 | 170 | 177 | 184 | 192 | 200 | 208 | 215 | 220 | 228 | 235 | 240 | 248 | 254 | 262 | 268 | 275 | 283 | 291 | 297 | 302 | 307 | 313 | 319 | 325 | 330 | 338 | 345 | 352 | 357 | 364 | 370 | 375 | 383 | 390 | 396 | 404 | 412 | 420 | 428 | 433 | 438 | 443 | 449 | 454 | 461 | 468 | 475 | 482 | 490 | 495 | 503 | 509 | 516 | 523 | 530 | 536 | 541 | 548 | 555 | 563 | 571 | 579 | 584 | 592 | 597 | 602 | 608 | 616 | 623 | 628 | 636 | 642 | 648 | 655 | 663 | 671 | 676 | 683 | 689
227 | 1.819 | 17 | 36 | 73 | 126 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 3 | 5 | 11 | 19 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 8 | 16 | 24 | 29 | 36 | 42 | 50 | 55 | 63 | 68 | 74 | 82 | 87 | 94 | 101 | 108 | 113 | 119 | 126 | 134 | 141 | 148 | 156 | 161 | 167 | 175 | 180 | 187 | 192 | 200 | 207 | 212 | 219 | 226 | 232 | 239 | 247 | 254 | 261 | 268 | 275 | 282 | 290 | 298 | 304 | 311 | 317 | 322 | 330 | 335 | 341 | 346 | 353 | 360 | 365 | 370 | 376 | 383 | 390 | 398 | 406 | 414 | 421 | 426 | 434 | 439 | 444 | 450 | 457 | 463 | 471 | 477 | 482 | 490 | 496 | 502 | 508 | 515 | 520 | 527 | 535 | 542 | 549 | 556 | 563 | 570 | 578 | 583 | 588 | 596 | 604 | 610 | 617 | 623 | 628 | 633 | 639 | 647 | 654 | 661 | 666 | 673 | 681 | 686
228 | 1.5095 | 13 | 26 | 54 | 89 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 2 | 5 | 9 | 14 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 13 | 18 | 24 | 32 | 37 | 42 | 49 | 56 | 63 | 71 | 78 | 84 | 89 | 95 | 102 | 107 | 114 | 121 | 129 | 136 | 141 | 146 | 154 | 162 | 170 | 175 | 180 | 186 | 193 | 198 | 206 | 213 | 221 | 226 | 234 | 239 | 247 | 255 | 260 | 268 | 275 | 282 | 289 | 295 | 300 | 308 | 316 | 322 | 327 | 332 | 337 | 344 | 352 | 360 | 365 | 371 | 377 | 385 | 390 | 398 | 406 | 413 | 421 | 428 | 436 | 442 | 450 | 458 | 465 | 473 | 481 | 486 | 493 | 500 | 507 | 515 | 523 | 529 | 535 | 542 | 548 | 553 | 559 | 565 | 572 | 579 | 586 | 593 | 599 | 605 | 610 | 617 | 623 | 628 | 635 | 643 | 649 | 657 | 662 | 670 | 678 | 686 | 694
229 | 1.5841 | 16 | 36 | 70 | 110 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 3 | 6 | 11 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 12 | 18 | 26 | 32 | 39 | 45 | 53 | 60 | 67 | 75 | 80 | 87 | 94 | 101 | 107 | 115 | 121 | 128 | 134 | 141 | 147 | 153 | 158 | 164 | 171 | 177 | 183 | 189 | 195 | 203 | 208 | 215 | 220 | 226 | 233 | 240 | 245 | 253 | 259 | 267 | 272 | 278 | 284 | 289 | 296 | 302 | 310 | 316 | 324 | 330 | 338 | 345 | 350 | 355 | 362 | 370 | 376 | 381 | 389 | 397 | 403 | 408 | 415 | 423 | 428 | 434 | 440 | 447 | 455 | 462 | 470 | 475 | 482 | 487 | 495 | 503 | 510 | 515 | 523 | 530 | 537 | 542 | 550 | 556 | 561 | 567 | 573 | 578 | 586 | 594 | 602 | 610 | 615 | 620 | 626 | 633 | 640 | 645 | 650 | 656 | 663 | 669 | 677
230 | 1.6647 | 10 | 35 | 72 | 119 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 2 | 6 | 11 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 12 | 19 | 26 | 34 | 41 | 48 | 56 | 61 | 66 | 74 | 81 | 87 | 92 | 97 | 105 | 110 | 115 | 120 | 128 | 135 | 141 | 148 | 153 | 160 | 165 | 170 | 176 | 182 | 188 | 195 | 201 | 208 | 214 | 221 | 226 | 234 | 242 | 249 | 254 | 262 | 270 | 278 | 286 | 294 | 300 | 307 | 313 | 318 | 325 | 331 | 337 | 345 | 353 | 359 | 365 | 372 | 379 | 387 | 392 | 397 | 404 | 410 | 417 | 425 | 430 | 435 | 443 | 449 | 454 | 460 | 468 | 476 | 484 | 492 | 498 | 506 | 514 | 520 | 526 | 532 | 538 | 545 | 552 | 560 | 565 | 570 | 575 | 583 | 588 | 593 | 598 | 603 | 608 | 615 | 622 | 629 | 637 | 642 | 648 | 654 | 662 | 668 | 676
231 | 1.936 | 16 | 38 | 81 | 120 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 3 | 6 | 12 | 18 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 15 | 23 | 29 | 35 | 40 | 48 | 54 | 60 | 68 | 76 | 84 | 90 | 98 | 105 | 112 | 117 | 122 | 130 | 136 | 143 | 151 | 157 | 165 | 172 | 177 | 185 | 193 | 199 | 206 | 214 | 219 | 225 | 233 | 241 | 248 | 253 | 258 | 264 | 272 | 278 | 286 | 294 | 300 | 306 | 314 | 322 | 327 | 333 | 338 | 343 | 348 | 355 | 363 | 368 | 376 | 383 | 389 | 395 | 402 | 408 | 414 | 422 | 429 | 437 | 442 | 447 | 455 | 463 | 468 | 473 | 481 | 487 | 495 | 503 | 509 | 517 | 523 | 528 | 536 | 542 | 547 | 552 | 559 | 565 | 572 | 578 | 584 | 590 | 598 | 603 | 608 | 613 | 621 | 626 | 632 | 637 | 644 | 649 | 657 | 663 | 671 | 678 | 686
232 | 1.7132 | 11 | 32 | 58 | 110 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 2 | 5 | 9 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 12 | 19 | 25 | 32 | 40 | 47 | 54 | 60 | 65 | 72 | 80 | 87 | 95 | 102 | 109 | 114 | 119 | 124 | 131 | 136 | 142 | 150 | 156 | 164 | 169 | 175 | 182 | 190 | 197 | 202 | 209 | 216 | 224 | 231 | 237 | 244 | 249 | 254 | 260 | 266 | 272 | 280 | 286 | 291 | 299 | 307 | 313 | 321 | 329 | 334 | 339 | 347 | 354 | 359 | 364 | 371 | 378 | 384 | 391 | 398 | 406 | 412 | 417 | 422 | 428 | 435 | 442 | 448 | 453 | 458 | 463 | 471 | 476 | 483 | 488 | 494 | 499 | 506 | 512 | 520 | 525 | 530 | 535 | 541 | 546 | 552 | 558 | 563 | 569 | 574 | 580 | 585 | 593 | 601 | 609 | 614 | 620 | 626 | 632 | 639 | 646 | 652 | 658
233 | 1.8301 | 19 | 36 | 64 | 119 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 3 | 6 | 10 | 18 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 7 | 14 | 22 | 28 | 34 | 42 | 49 | 54 | 59 | 66 | 73 | 80 | 88 | 95 | 103 | 110 | 117 | 123 | 128 | 133 | 141 | 148 | 154 | 159 | 167 | 174 | 182 | 187 | 192 | 199 | 206 | 212 | 220 | 228 | 233 | 239 | 245 | 253 | 258 | 264 | 270 | 275 | 281 | 286 | 292 | 300 | 307 | 313 | 320 | 326 | 333 | 340 | 348 | 356 | 363 | 370 | 378 | 384 | 392 | 397 | 404 | 412 | 417 | 423 | 430 | 438 | 443 | 451 | 457 | 464 | 471 | 479 | 487 | 494 | 502 | 507 | 512 | 520 | 526 | 533 | 540 | 546 | 551 | 558 | 564 | 572 | 578 | 583 | 591 | 596 | 603 | 608 | 614 | 621 | 628 | 636 | 642 | 647 | 655 | 663 | 670 | 676 | 683 | 689
234 | 1.7315 | 14 | 37 | 67 | 116 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 2 | 6 | 11 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 14 | 19 | 24 | 31 | 39 | 47 | 52 | 57 | 62 | 67 | 74 | 82 | 88 | 96 | 103 | 108 | 114 | 120 | 125 | 132 | 140 | 147 | 154 | 161 | 167 | 175 | 183 | 191 | 196 | 202 | 209 | 217 | 224 | 232 | 238 | 245 | 252 | 258 | 265 | 272 | 279 | 285 | 292 | 299 | 304 | 311 | 316 | 323 | 331 | 339 | 346 | 353 | 359 | 366 | 371 | 377 | 384 | 391 | 396 | 402 | 407 | 415 | 420 | 425 | 433 | 439 | 447 | 453 | 460 | 466 | 472 | 478 | 484 | 490 | 495 | 502 | 507 | 514 | 522 | 529 | 537 | 544 | 550 | 555 | 562 | 570 | 578 | 585 | 592 | 600 | 607 | 612 | 619 | 627 | 633 | 638 | 643 | 648 | 653 | 661 | 666 | 671 | 679
235 | 1.4876 | 8 | 26 | 64 | 103 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 2 | 5 | 11 | 17 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 12 | 19 | 25 | 30 | 36 | 41 | 48 | 53 | 61 | 66 | 72 | 80 | 86 | 92 | 99 | 107 | 115 | 121 | 129 | 136 | 141 | 149 | 156 | 164 | 170 | 175 | 183 | 188 | 194 | 199 | 205 | 210 | 217 | 224 | 229 | 235 | 243 | 251 | 258 | 266 | 273 | 281 | 287 | 292 | 300 | 307 | 314 | 319 | 326 | 334 | 340 | 345 | 352 | 357 | 364 | 372 | 379 | 384 | 391 | 399 | 405 | 411 | 417 | 423 | 430 | 436 | 444 | 451 | 457 | 465 | 473 | 480 | 485 | 491 | 496 | 501 | 506 | 511 | 517 | 525 | 533 | 540 | 548 | 554 | 559 | 566 | 572 | 579 | 584 | 591 | 596 | 602 | 610 | 615 | 621 | 628 | 634 | 641 | 648 | 653 | 661 | 669 | 677
236 | 1.0373 | 10 | 25 | 45 | 72 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 5 | 8 | 11 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 13 | 19 | 24 | 29 | 35 | 43 | 51 | 58 | 66 | 74 | 80 | 86 | 93 | 98 | 105 | 110 | 116 | 121 | 127 | 132 | 138 | 143 | 149 | 154 | 161 | 169 | 177 | 185 | 193 | 199 | 204 | 209 | 215 | 221 | 227 | 234 | 242 | 250 | 256 | 262 | 269 | 274 | 282 | 287 | 294 | 300 | 306 | 312 | 320 | 327 | 332 | 338 | 346 | 351 | 357 | 362 | 369 | 377 | 385 | 391 | 397 | 405 | 410 | 415 | 420 | 428 | 436 | 442 | 448 | 454 | 459 | 464 | 470 | 478 | 485 | 491 | 499 | 506 | 512 | 517 | 525 | 530 | 535 | 541 | 549 | 555 | 563 | 570 | 577 | 583 | 589 | 596 | 604 | 609 | 617 | 623 | 631 | 636 | 641 | 648 | 654 | 659 | 665
237 | 1.6459 | 17 | 34 | 67 | 115 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 3 | 5 | 11 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 15 | 21 | 27 | 35 | 42 | 48 | 53 | 58 | 64 | 72 | 77 | 84 | 92 | 97 | 105 | 111 | 119 | 124 | 132 | 139 | 146 | 151 | 159 | 165 | 171 | 179 | 187 | 193 | 200 | 205 | 213 | 219 | 225 | 232 | 240 | 246 | 253 | 259 | 264 | 270 | 277 | 284 | 292 | 299 | 305 | 313 | 319 | 325 | 330 | 336 | 341 | 346 | 353 | 359 | 366 | 374 | 382 | 390 | 397 | 403 | 411 | 419 | 426 | 432 | 440 | 446 | 452 | 459 | 465 | 472 | 479 | 484 | 491 | 497 | 503 | 508 | 516 | 522 | 527 | 534 | 542 | 549 | 554 | 562 | 570 | 576 | 581 | 588 | 594 | 601 | 608 | 615 | 622 | 629 | 634 | 641 | 649 | 655 | 660 | 668 | 676 | 682 | 688
238 | 1.6026 | 12 | 27 | 61 | 103 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 2 | 5 | 10 | 15 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 7 | 13 | 20 | 26 | 32 | 40 | 46 | 52 | 57 | 64 | 71 | 79 | 87 | 95 | 103 | 109 | 116 | 121 | 128 | 134 | 142 | 149 | 155 | 163 | 168 | 175 | 180 | 186 | 194 | 200 | 207 | 212 | 217 | 222 | 230 | 235 | 240 | 247 | 252 | 259 | 266 | 271 | 277 | 284 | 290 | 298 | 306 | 311 | 318 | 323 | 328 | 333 | 341 | 348 | 353 | 358 | 363 | 370 | 375 | 380 | 388 | 394 | 401 | 408 | 415 | 423 | 430 | 438 | 443 | 450 | 458 | 465 | 472 | 479 | 484 | 490 | 498 | 503 | 510 | 515 | 520 | 528 | 536 | 541 | 547 | 553 | 560 | 566 | 573 | 581 | 586 | 594 | 602 | 609 | 616 | 624 | 631 | 636 | 643 | 650 | 655 | 661 | 667 | 675
239 | 1.0493 | 6 | 16 | 42 | 65 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 1 | 3 | 8 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 14 | 19 | 24 | 29 | 34 | 40 | 48 | 55 | 62 | 68 | 73 | 78 | 86 | 91 | 98 | 106 | 113 | 118 | 124 | 130 | 137 | 145 | 152 | 159 | 167 | 174 | 182 | 187 | 195 | 201 | 207 | 212 | 220 | 226 | 234 | 241 | 249 | 256 | 263 | 269 | 275 | 280 | 288 | 295 | 302 | 310 | 315 | 321 | 326 | 333 | 338 | 345 | 351 | 358 | 365 | 370 | 376 | 382 | 388 | 395 | 401 | 406 | 412 | 419 | 427 | 435 | 442 | 449 | 456 | 461 | 468 | 473 | 481 | 488 | 496 | 501 | 509 | 514 | 520 | 528 | 534 | 541 | 548 | 556 | 562 | 567 | 572 | 577 | 585 | 593 | 599 | 607 | 613 | 621 | 626 | 632 | 637 | 643 | 649 | 656 | 664 | 670 | 675
240 | 1.2724 | 8 | 28 | 48 | 76 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 2 | 5 | 8 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 13 | 19 | 25 | 32 | 38 | 45 | 53 | 59 | 67 | 73 | 81 | 88 | 95 | 102 | 109 | 114 | 121 | 127 | 132 | 139 | 145 | 152 | 160 | 167 | 173 | 179 | 185 | 191 | 198 | 205 | 210 | 215 | 223 | 228 | 235 | 240 | 248 | 253 | 260 | 267 | 272 | 280 | 285 | 293 | 301 | 306 | 311 | 318 | 326 | 332 | 340 | 348 | 355 | 363 | 371 | 378 | 384 | 389 | 397 | 404 | 411 | 418 | 425 | 432 | 439 | 446 | 452 | 459 | 465 | 473 | 480 | 487 | 492 | 500 | 505 | 512 | 518 | 526 | 531 | 539 | 546 | 552 | 557 | 565 | 571 | 579 | 587 | 594 | 599 | 605 | 610 | 618 | 626 | 632 | 638 | 645 | 650 | 656 | 661 | 668 | 676 | 684 | 691
241 | 1.8914 | 16 | 45 | 76 | 133 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 3 | 7 | 12 | 20 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 8 | 15 | 21 | 28 | 33 | 41 | 47 | 53 | 59 | 66 | 73 | 80 | 88 | 96 | 102 | 110 | 116 | 123 | 128 | 133 | 141 | 148 | 153 | 161 | 169 | 175 | 182 | 189 | 194 | 200 | 206 | 213 | 220 | 227 | 234 | 239 | 246 | 254 | 260 | 268 | 274 | 281 | 287 | 293 | 301 | 307 | 314 | 321 | 328 | 334 | 341 | 349 | 354 | 359 | 366 | 373 | 378 | 385 | 393 | 400 | 405 | 413 | 418 | 424 | 430 | 438 | 445 | 451 | 458 | 463 | 469 | 475 | 482 | 489 | 494 | 500 | 506 | 511 | 517 | 523 | 528 | 534 | 539 | 545 | 552 | 560 | 567 | 573 | 581 | 586 | 592 | 598 | 606 | 612 | 617 | 625 | 630 | 638 | 643 | 648 | 655 | 662 | 670 | 676
242 | 1.577 | 12 | 36 | 63 | 95 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 2 | 6 | 10 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 13 | 18 | 25 | 31 | 38 | 44 | 52 | 59 | 66 | 71 | 79 | 86 | 94 | 99 | 106 | 112 | 119 | 127 | 135 | 143 | 149 | 156 | 164 | 170 | 176 | 184 | 189 | 196 | 204 | 212 | 219 | 227 | 235 | 243 | 248 | 256 | 264 | 272 | 280 | 286 | 292 | 297 | 304 | 310 | 315 | 320 | 328 | 333 | 340 | 347 | 354 | 359 | 366 | 374 | 380 | 385 | 390 | 395 | 403 | 410 | 418 | 423 | 428 | 436 | 444 | 452 | 459 | 465 | 473 | 480 | 488 | 494 | 501 | 508 | 516 | 521 | 527 | 534 | 542 | 550 | 557 | 562 | 569 | 577 | 582 | 587 | 594 | 601 | 609 | 616 | 621 | 629 | 635 | 642 | 647 | 653 | 658 | 663 | 670 | 675 | 683 | 691 | 697
243 | 1.125 | 11 | 25 | 54 | 78 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 4 | 9 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 14 | 19 | 26 | 33 | 39 | 44 | 52 | 59 | 65 | 72 | 80 | 85 | 91 | 97 | 102 | 107 | 114 | 119 | 125 | 133 | 138 | 146 | 154 | 162 | 168 | 174 | 180 | 185 | 192 | 200 | 207 | 212 | 219 | 227 | 232 | 240 | 245 | 250 | 256 | 262 | 268 | 273 | 280 | 285 | 290 | 295 | 303 | 308 | 313 | 320 | 325 | 332 | 338 | 343 | 349 | 356 | 363 | 368 | 375 | 380 | 385 | 391 | 398 | 404 | 409 | 416 | 421 | 429 | 436 | 443 | 449 | 456 | 462 | 469 | 474 | 481 | 488 | 495 | 500 | 508 | 516 | 524 | 530 | 535 | 543 | 551 | 557 | 562 | 570 | 575 | 581 | 589 | 596 | 601 | 607 | 615 | 620 | 628 | 635 | 643 | 648 | 653 | 661
244 | 1.08 | 8 | 18 | 43 | 69 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 1 | 3 | 6 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 13 | 21 | 28 | 35 | 43 | 48 | 56 | 64 | 70 | 78 | 85 | 92 | 100 | 107 | 114 | 121 | 129 | 136 | 141 | 146 | 154 | 161 | 169 | 174 | 182 | 189 | 195 | 201 | 208 | 214 | 222 | 227 | 234 | 241 | 246 | 252 | 258 | 266 | 271 | 279 | 287 | 294 | 299 | 306 | 313 | 321 | 327 | 333 | 338 | 344 | 349 | 356 | 361 | 366 | 374 | 379 | 386 | 393 | 400 | 406 | 414 | 420 | 428 | 435 | 440 | 445 | 450 | 456 | 463 | 469 | 475 | 483 | 491 | 499 | 507 | 514 | 522 | 527 | 533 | 540 | 548 | 553 | 561 | 568 | 575 | 581 | 586 | 594 | 600 | 608 | 613 | 619 | 626 | 632 | 640 | 647 | 654 | 661 | 666 | 674 | 680 | 685 | 692
245 | 1.2166 | 11 | 22 | 46 | 74 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 2 | 4 | 8 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 11 | 19 | 24 | 32 | 38 | 44 | 51 | 57 | 65 | 72 | 80 | 87 | 94 | 100 | 106 | 114 | 120 | 126 | 133 | 140 | 148 | 156 | 161 | 168 | 174 | 180 | 186 | 192 | 198 | 205 | 210 | 216 | 223 | 231 | 238 | 243 | 250 | 258 | 265 | 271 | 278 | 286 | 291 | 297 | 305 | 312 | 318 | 324 | 329 | 335 | 343 | 348 | 356 | 362 | 368 | 376 | 382 | 387 | 395 | 403 | 410 | 416 | 423 | 430 | 438 | 446 | 454 | 460 | 466 | 471 | 477 | 483 | 488 | 495 | 500 | 505 | 512 | 517 | 525 | 532 | 537 | 543 | 551 | 557 | 563 | 570 | 575 | 580 | 587 | 592 | 599 | 605 | 610 | 615 | 622 | 630 | 638 | 646 | 652 | 657 | 663 | 668 | 674
246 | 1.7157 | 9 | 25 | 56 | 96 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 4 | 9 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 19 | 27 | 34 | 39 | 44 | 50 | 58 | 64 | 72 | 78 | 86 | 91 | 97 | 102 | 109 | 114 | 121 | 127 | 132 | 139 | 144 | 152 | 158 | 163 | 168 | 173 | 179 | 187 | 194 | 202 | 207 | 214 | 222 | 228 | 236 | 244 | 252 | 260 | 267 | 273 | 278 | 283 | 289 | 294 | 302 | 309 | 315 | 321 | 326 | 334 | 339 | 346 | 352 | 358 | 365 | 371 | 378 | 384 | 392 | 398 | 403 | 408 | 416 | 422 | 427 | 434 | 439 | 444 | 449 | 457 | 463 | 469 | 476 | 481 | 489 | 495 | 503 | 510 | 515 | 521 | 527 | 534 | 542 | 550 | 558 | 563 | 571 | 579 | 587 | 592 | 600 | 607 | 613 | 621 | 629 | 635 | 640 | 647 | 653 | 660 | 668 | 674
247 | 1.3413 | 13 | 27 | 48 | 83 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 4 | 8 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 16 | 24 | 29 | 36 | 41 | 46 | 53 | 61 | 67 | 72 | 77 | 82 | 90 | 95 | 100 | 108 | 115 | 121 | 126 | 134 | 142 | 149 | 154 | 159 | 167 | 174 | 181 | 187 | 195 | 200 | 208 | 215 | 223 | 229 | 236 | 243 | 250 | 255 | 262 | 269 | 277 | 282 | 289 | 294 | 300 | 307 | 313 | 320 | 328 | 333 | 339 | 347 | 352 | 357 | 363 | 369 | 374 | 379 | 384 | 392 | 400 | 406 | 414 | 421 | 427 | 435 | 440 | 446 | 451 | 457 | 463 | 468 | 476 | 483 | 491 | 499 | 506 | 512 | 518 | 524 | 532 | 539 | 547 | 553 | 558 | 563 | 569 | 575 | 582 | 587 | 594 | 602 | 609 | 616 | 624 | 629 | 635 | 643 | 651 | 657 | 662 | 669 | 675
248 | 1.9333 | 18 | 42 | 73 | 128 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 3 | 7 | 12 | 21 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 8 | 13 | 21 | 26 | 32 | 39 | 47 | 52 | 58 | 63 | 71 | 77 | 82 | 87 | 92 | 97 | 104 | 110 | 117 | 122 | 130 | 135 | 140 | 146 | 151 | 157 | 162 | 169 | 177 | 184 | 192 | 200 | 206 | 211 | 218 | 224 | 229 | 236 | 243 | 249 | 256 | 263 | 270 | 275 | 282 | 288 | 294 | 302 | 308 | 314 | 321 | 327 | 334 | 339 | 347 | 354 | 359 | 365 | 370 | 376 | 381 | 386 | 393 | 400 | 406 | 411 | 418 | 426 | 432 | 440 | 446 | 452 | 457 | 464 | 472 | 477 | 482 | 490 | 495 | 502 | 508 | 514 | 519 | 525 | 532 | 539 | 547 | 552 | 559 | 567 | 575 | 580 | 586 | 593 | 600 | 605 | 612 | 618 | 626 | 633 | 638 | 645 | 653 | 661
249 | 1.6613 | 10 | 34 | 61 | 105 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 2 | 6 | 10 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 6 | 13 | 20 | 28 | 33 | 41 | 46 | 51 | 59 | 65 | 73 | 78 | 85 | 90 | 96 | 103 | 109 | 116 | 121 | 126 | 131 | 138 | 144 | 149 | 155 | 161 | 168 | 175 | 183 | 188 | 196 | 202 | 207 | 214 | 219 | 225 | 231 | 238 | 243 | 250 | 255 | 261 | 267 | 274 | 280 | 286 | 293 | 299 | 306 | 313 | 320 | 326 | 331 | 339 | 347 | 352 | 359 | 367 | 372 | 380 | 385 | 390 | 397 | 402 | 408 | 413 | 418 | 425 | 431 | 436 | 444 | 449 | 456 | 461 | 467 | 475 | 483 | 489 | 495 | 503 | 509 | 515 | 521 | 528 | 535 | 541 | 547 | 552 | 558 | 563 | 568 | 574 | 581 | 588 | 593 | 600 | 607 | 614 | 621 | 628 | 633 | 640 | 648 | 656
250 | 1.3847 | 14 | 28 | 49 | 86 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 2 | 4 | 7 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 24 | 31 | 39 | 45 | 51 | 57 | 64 | 71 | 78 | 84 | 90 | 97 | 104 | 111 | 116 | 124 | 132 | 140 | 148 | 156 | 161 | 168 | 175 | 181 | 187 | 193 | 199 | 204 | 209 | 217 | 225 | 231 | 237 | 242 | 247 | 253 | 260 | 266 | 272 | 280 | 286 | 292 | 299 | 307 | 314 | 321 | 327 | 332 | 339 | 345 | 350 | 355 | 362 | 370 | 377 | 382 | 389 | 396 | 403 | 411 | 416 | 424 | 432 | 438 | 443 | 448 | 454 | 459 | 466 | 474 | 480 | 485 | 490 | 495 | 502 | 508 | 513 | 520 | 527 | 534 | 540 | 546 | 553 | 561 | 568 | 575 | 583 | 591 | 599 | 606 | 614 | 620 | 627 | 633 | 638 | 645 | 652 | 660 | 666 | 673 | 681 | 686
251 | 1.9035 | 18 | 47 | 93 | 133 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 3 | 7 | 14 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 8 | 16 | 24 | 30 | 36 | 42 | 50 | 55 | 61 | 68 | 75 | 82 | 89 | 97 | 102 | 107 | 112 | 118 | 125 | 131 | 136 | 141 | 147 | 155 | 163 | 170 | 178 | 183 | 191 | 196 | 202 | 208 | 216 | 221 | 227 | 232 | 237 | 244 | 250 | 256 | 261 | 269 | 274 | 280 | 287 | 292 | 299 | 306 | 313 | 319 | 326 | 333 | 340 | 347 | 353 | 360 | 367 | 375 | 382 | 390 | 398 | 404 | 409 | 416 | 423 | 429 | 434 | 439 | 447 | 452 | 458 | 465 | 471 | 476 | 482 | 487 | 492 | 497 | 503 | 510 | 517 | 522 | 528 | 535 | 543 | 550 | 558 | 565 | 572 | 579 | 584 | 589 | 597 | 604 | 612 | 619 | 624 | 629 | 637 | 644 | 651 | 658 | 664 | 672
252 | 1.4208 | 9 | 31 | 61 | 90 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 2 | 5 | 10 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 14 | 21 | 27 | 34 | 41 | 47 | 52 | 59 | 65 | 72 | 77 | 84 | 91 | 96 | 101 | 109 | 114 | 121 | 127 | 134 | 139 | 145 | 153 | 158 | 164 | 171 | 178 | 184 | 192 | 197 | 204 | 209 | 215 | 223 | 228 | 235 | 243 | 250 | 258 | 265 | 272 | 279 | 287 | 295 | 301 | 307 | 312 | 320 | 325 | 332 | 337 | 343 | 351 | 359 | 364 | 369 | 374 | 382 | 390 | 398 | 404 | 410 | 416 | 421 | 429 | 437 | 442 | 450 | 455 | 462 | 470 | 475 | 483 | 490 | 498 | 504 | 512 | 520 | 527 | 532 | 538 | 545 | 550 | 556 | 561 | 569 | 575 | 581 | 586 | 594 | 600 | 605 | 613 | 619 | 627 | 634 | 640 | 645 | 651 | 656 | 661 | 669 | 676
253 | 1.6329 | 14 | 39 | 80 | 128 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 3 | 7 | 13 | 21 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 10 | 18 | 23 | 28 | 34 | 39 | 46 | 52 | 59 | 67 | 75 | 82 | 89 | 97 | 102 | 107 | 112 | 119 | 127 | 134 | 140 | 145 | 151 | 159 | 164 | 172 | 179 | 187 | 193 | 198 | 205 | 212 | 219 | 224 | 232 | 238 | 246 | 254 | 260 | 266 | 273 | 281 | 289 | 296 | 301 | 307 | 313 | 320 | 325 | 331 | 337 | 343 | 349 | 354 | 360 | 367 | 374 | 380 | 388 | 393 | 401 | 409 | 416 | 422 | 427 | 432 | 437 | 443 | 449 | 457 | 464 | 472 | 479 | 487 | 493 | 500 | 508 | 516 | 521 | 528 | 533 | 539 | 547 | 553 | 558 | 564 | 570 | 577 | 582 | 590 | 596 | 602 | 610 | 618 | 624 | 630 | 638 | 644 | 649 | 654 | 662 | 670 | 678
254 | 1.3953 | 9 | 23 | 53 | 81 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 2 | 3 | 8 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8 | 16 | 24 | 30 | 36 | 43 | 51 | 56 | 63 | 70 | 77 | 82 | 89 | 94 | 99 | 106 | 112 | 117 | 122 | 127 | 134 | 141 | 149 | 155 | 162 | 169 | 174 | 181 | 186 | 191 | 199 | 207 | 215 | 221 | 226 | 233 | 241 | 246 | 254 | 260 | 267 | 274 | 280 | 287 | 294 | 300 | 308 | 316 | 323 | 329 | 334 | 342 | 349 | 357 | 363 | 370 | 377 | 382 | 389 | 394 | 401 | 407 | 413 | 418 | 426 | 433 | 440 | 448 | 453 | 461 | 466 | 474 | 479 | 485 | 491 | 499 | 505 | 512 | 520 | 528 | 536 | 541 | 548 | 556 | 563 | 568 | 575 | 580 | 587 | 594 | 602 | 609 | 617 | 625 | 631 | 638 | 646 | 653 | 658 | 664 | 669 | 675 | 680 | 687
255 | 1.7217 | 14 | 32 | 65 | 107 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 2 | 5 | 10 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 7 | 15 | 21 | 27 | 32 | 38 | 46 | 52 | 60 | 68 | 74 | 81 | 89 | 97 | 105 | 113 | 121 | 126 | 134 | 140 | 145 | 151 | 156 | 161 | 166 | 172 | 179 | 184 | 191 | 199 | 206 | 212 | 220 | 226 | 232 | 238 | 245 | 253 | 259 | 266 | 274 | 282 | 290 | 298 | 306 | 313 | 318 | 324 | 330 | 338 | 343 | 348 | 355 | 362 | 369 | 375 | 382 | 388 | 396 | 404 | 412 | 418 | 426 | 433 | 439 | 445 | 451 | 458 | 465 | 473 | 479 | 485 | 490 | 496 | 501 | 507 | 512 | 518 | 524 | 532 | 540 | 548 | 555 | 561 | 568 | 575 | 581 | 587 | 594 | 599 | 605 | 610 | 616 | 623 | 628 | 634 | 642 | 647 | 652 | 659 | 664 | 672 | 679 | 686
256 | 1.5024 | 8 | 22 | 45 | 79 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 2 | 4 | 7 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 12 | 20 | 28 | 36 | 44 | 49 | 57 | 65 | 71 | 77 | 83 | 88 | 95 | 103 | 109 | 117 | 124 | 132 | 138 | 143 | 151 | 156 | 162 | 169 | 174 | 181 | 187 | 195 | 201 | 209 | 214 | 219 | 227 | 235 | 241 | 246 | 253 | 258 | 266 | 273 | 278 | 283 | 288 | 294 | 300 | 306 | 313 | 319 | 325 | 330 | 337 | 342 | 347 | 352 | 358 | 365 | 370 | 375 | 383 | 391 | 397 | 405 | 410 | 417 | 424 | 430 | 435 | 442 | 449 | 454 | 459 | 465 | 470 | 478 | 483 | 491 | 499 | 506 | 513 | 519 | 526 | 532 | 538 | 546 | 552 | 559 | 564 | 570 | 577 | 585 | 592 | 597 | 604 | 612 | 620 | 626 | 631 | 636 | 641 | 646 | 652 | 657 | 662
257 | 1.8894 | 12 | 31 | 73 | 113 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 2 | 5 | 11 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 12 | 20 | 26 | 34 | 42 | 47 | 55 | 62 | 69 | 77 | 83 | 91 | 96 | 102 | 110 | 118 | 124 | 129 | 135 | 143 | 151 | 156 | 164 | 172 | 177 | 182 | 190 | 196 | 201 | 208 | 214 | 221 | 228 | 236 | 241 | 249 | 256 | 262 | 270 | 277 | 285 | 292 | 300 | 305 | 311 | 319 | 327 | 335 | 340 | 348 | 354 | 361 | 366 | 374 | 381 | 388 | 396 | 403 | 411 | 416 | 422 | 427 | 433 | 441 | 446 | 454 | 459 | 464 | 472 | 479 | 487 | 495 | 501 | 506 | 514 | 520 | 528 | 536 | 542 | 548 | 556 | 564 | 570 | 575 | 582 | 590 | 596 | 603 | 608 | 615 | 621 | 627 | 635 | 640 | 648 | 655 | 660 | 668 | 673 | 679 | 687 | 695 | 703
258 | 1.8941 | 16 | 41 | 85 | 133 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 3 | 6 | 12 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 13 | 20 | 28 | 36 | 44 | 52 | 57 | 64 | 69 | 77 | 85 | 92 | 99 | 104 | 111 | 118 | 123 | 131 | 137 | 142 | 147 | 152 | 159 | 167 | 173 | 181 | 186 | 192 | 198 | 204 | 212 | 218 | 225 | 232 | 240 | 245 | 251 | 259 | 265 | 271 | 279 | 284 | 290 | 296 | 303 | 308 | 314 | 322 | 327 | 335 | 342 | 349 | 356 | 361 | 369 | 376 | 381 | 388 | 394 | 401 | 406 | 411 | 419 | 424 | 432 | 439 | 444 | 450 | 456 | 462 | 470 | 476 | 481 | 488 | 493 | 498 | 504 | 511 | 516 | 521 | 528 | 535 | 542 | 547 | 555 | 561 | 568 | 574 | 579 | 586 | 594 | 602 | 609 | 616 | 624 | 632 | 640 | 646 | 652 | 660 | 666 | 674 | 681
259 | 1.7812 | 13 | 28 | 62 | 100 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 2 | 4 | 9 | 15 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 15 | 22 | 30 | 38 | 46 | 52 | 57 | 63 | 71 | 78 | 85 | 92 | 99 | 107 | 113 | 119 | 124 | 130 | 138 | 144 | 151 | 157 | 165 | 171 | 177 | 185 | 190 | 197 | 204 | 209 | 214 | 219 | 227 | 234 | 241 | 249 | 257 | 265 | 270 | 275 | 281 | 286 | 291 | 298 | 306 | 314 | 320 | 325 | 332 | 340 | 347 | 352 | 358 | 364 | 372 | 377 | 384 | 392 | 397 | 402 | 410 | 415 | 423 | 431 | 436 | 444 | 450 | 456 | 462 | 467 | 472 | 479 | 484 | 489 | 496 | 501 | 508 | 514 | 520 | 528 | 535 | 540 | 547 | 553 | 558 | 566 | 572 | 577 | 585 | 592 | 600 | 607 | 613 | 621 | 626 | 632 | 638 | 646 | 653 | 658 | 664 | 671 | 679
260 | 1.0977 | 10 | 26 | 48 | 73 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 2 | 5 | 8 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 5 | 10 | 16 | 24 | 30 | 37 | 45 | 52 | 58 | 66 | 72 | 80 | 88 | 94 | 102 | 108 | 114 | 122 | 127 | 132 | 139 | 145 | 152 | 159 | 165 | 173 | 178 | 184 | 191 | 197 | 202 | 207 | 213 | 221 | 227 | 235 | 241 | 246 | 253 | 261 | 269 | 277 | 283 | 290 | 295 | 300 | 308 | 313 | 321 | 326 | 332 | 339 | 347 | 352 | 360 | 366 | 373 | 379 | 386 | 392 | 398 | 406 | 411 | 419 | 427 | 433 | 440 | 447 | 454 | 461 | 466 | 471 | 479 | 484 | 491 | 497 | 504 | 509 | 514 | 520 | 528 | 536 | 541 | 547 | 555 | 561 | 568 | 573 | 580 | 585 | 591 | 599 | 605 | 611 | 618 | 623 | 629 | 634 | 640 | 646 | 654 | 660 | 668 | 676
261 | 1.7706 | 16 | 43 | 74 | 113 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 3 | 7 | 11 | 17 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 7 | 13 | 18 | 24 | 32 | 38 | 46 | 54 | 61 | 68 | 74 | 82 | 88 | 93 | 99 | 107 | 113 | 118 | 125 | 133 | 141 | 148 | 153 | 159 | 166 | 171 | 179 | 185 | 190 | 195 | 201 | 207 | 212 | 220 | 225 | 232 | 238 | 243 | 250 | 258 | 264 | 270 | 278 | 286 | 293 | 300 | 305 | 311 | 319 | 325 | 332 | 338 | 344 | 351 | 356 | 363 | 369 | 376 | 383 | 391 | 396 | 401 | 409 | 417 | 423 | 429 | 435 | 441 | 449 | 455 | 460 | 465 | 471 | 476 | 483 | 491 | 498 | 504 | 512 | 519 | 526 | 531 | 539 | 547 | 552 | 560 | 565 | 570 | 578 | 583 | 590 | 598 | 605 | 613 | 618 | 624 | 631 | 638 | 645 | 651 | 659 | 664 | 672 | 680
262 | 1.2741 | 11 | 26 | 57 | 84 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 2 | 5 | 10 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 12 | 17 | 24 | 30 | 38 | 44 | 50 | 55 | 63 | 69 | 77 | 84 | 90 | 96 | 104 | 112 | 119 | 127 | 132 | 139 | 144 | 149 | 156 | 162 | 167 | 172 | 177 | 183 | 188 | 194 | 202 | 208 | 214 | 221 | 229 | 235 | 243 | 251 | 257 | 264 | 269 | 277 | 283 | 291 | 296 | 303 | 310 | 318 | 323 | 329 | 336 | 343 | 348 | 356 | 363 | 369 | 377 | 384 | 391 | 398 | 403 | 408 | 416 | 422 | 429 | 434 | 442 | 448 | 455 | 462 | 469 | 477 | 483 | 490 | 498 | 503 | 508 | 513 | 518 | 525 | 531 | 537 | 545 | 553 | 558 | 564 | 569 | 575 | 583 | 591 | 596 | 604 | 609 | 615 | 621 | 628 | 633 | 639 | 646 | 652 | 658 | 664 | 669
263 | 1.5488 | 10 | 31 | 58 | 99 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 2 | 6 | 10 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 12 | 17 | 24 | 29 | 37 | 43 | 49 | 57 | 64 | 69 | 75 | 82 | 88 | 95 | 101 | 107 | 114 | 120 | 128 | 133 | 139 | 146 | 151 | 157 | 162 | 170 | 178 | 184 | 192 | 199 | 207 | 215 | 221 | 226 | 231 | 239 | 246 | 253 | 260 | 268 | 273 | 280 | 287 | 295 | 302 | 309 | 316 | 321 | 326 | 333 | 338 | 346 | 352 | 357 | 363 | 369 | 376 | 382 | 387 | 394 | 400 | 407 | 412 | 418 | 423 | 429 | 435 | 440 | 447 | 452 | 457 | 464 | 471 | 477 | 484 | 490 | 498 | 505 | 511 | 518 | 525 | 532 | 537 | 545 | 550 | 557 | 563 | 569 | 576 | 583 | 588 | 596 | 604 | 612 | 618 | 624 | 632 | 638 | 645 | 652 | 657 | 662 | 667
264 | 1.5608 | 16 | 32 | 57 | 98 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 3 | 6 | 10 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 6 | 11 | 17 | 24 | 29 | 34 | 40 | 48 | 53 | 59 | 66 | 71 | 76 | 82 | 89 | 95 | 102 | 110 | 116 | 123 | 131 | 136 | 144 | 151 | 156 | 162 | 167 | 175 | 182 | 187 | 193 | 200 | 205 | 212 | 220 | 225 | 232 | 238 | 245 | 250 | 257 | 263 | 271 | 278 | 285 | 293 | 298 | 304 | 310 | 318 | 325 | 331 | 337 | 342 | 350 | 358 | 363 | 370 | 376 | 383 | 389 | 394 | 402 | 409 | 416 | 421 | 429 | 436 | 444 | 451 | 457 | 465 | 473 | 479 | 485 | 493 | 500 | 505 | 513 | 519 | 525 | 533 | 540 | 546 | 551 | 556 | 561 | 569 | 575 | 581 | 588 | 594 | 600 | 608 | 616 | 623 | 628 | 636 | 641 | 647 | 654 | 659 | 664 | 669
265 | 1.799 | 15 | 42 | 80 | 120 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 3 | 7 | 12 | 19 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 13 | 20 | 27 | 32 | 39 | 44 | 51 | 59 | 67 | 73 | 80 | 85 | 90 | 95 | 101 | 108 | 115 | 123 | 130 | 138 | 146 | 152 | 158 | 164 | 169 | 174 | 182 | 187 | 194 | 201 | 209 | 215 | 221 | 227 | 232 | 239 | 246 | 253 | 259 | 266 | 271 | 276 | 284 | 292 | 298 | 304 | 312 | 318 | 325 | 332 | 340 | 346 | 353 | 361 | 368 | 376 | 383 | 390 | 396 | 402 | 409 | 417 | 425 | 431 | 436 | 444 | 450 | 455 | 461 | 468 | 475 | 480 | 485 | 492 | 500 | 507 | 512 | 518 | 525 | 532 | 540 | 545 | 550 | 558 | 565 | 572 | 579 | 585 | 592 | 599 | 604 | 612 | 620 | 625 | 632 | 639 | 644 | 652 | 657 | 663 | 670 | 675 | 681
266 | 1.456 | 8 | 29 | 66 | 99 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 2 | 5 | 11 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 13 | 19 | 24 | 29 | 34 | 41 | 49 | 55 | 60 | 67 | 74 | 81 | 89 | 95 | 100 | 107 | 115 | 122 | 130 | 135 | 143 | 150 | 157 | 163 | 168 | 176 | 182 | 190 | 196 | 201 | 206 | 213 | 220 | 225 | 230 | 236 | 244 | 249 | 256 | 263 | 269 | 277 | 282 | 287 | 293 | 298 | 305 | 311 | 319 | 324 | 330 | 337 | 343 | 350 | 355 | 361 | 369 | 374 | 382 | 387 | 393 | 400 | 406 | 412 | 418 | 426 | 431 | 437 | 443 | 449 | 456 | 463 | 470 | 476 | 484 | 489 | 494 | 502 | 509 | 516 | 521 | 529 | 535 | 542 | 549 | 555 | 562 | 568 | 575 | 583 | 588 | 595 | 602 | 607 | 613 | 621 | 629 | 636 | 643 | 648 | 655 | 661 | 667
267 | 1.2692 | 9 | 25 | 57 | 94 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 2 | 4 | 9 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 15 | 21 | 26 | 33 | 40 | 48 | 56 | 64 | 72 | 79 | 86 | 91 | 96 | 103 | 108 | 114 | 122 | 130 | 137 | 145 | 151 | 157 | 164 | 172 | 177 | 184 | 189 | 195 | 203 | 208 | 215 | 223 | 229 | 234 | 239 | 246 | 252 | 260 | 266 | 273 | 279 | 285 | 290 | 295 | 301 | 306 | 313 | 318 | 325 | 330 | 336 | 342 | 349 | 356 | 364 | 370 | 376 | 381 | 387 | 394 | 399 | 407 | 415 | 420 | 428 | 436 | 443 | 448 | 455 | 463 | 471 | 476 | 482 | 487 | 495 | 502 | 507 | 514 | 519 | 524 | 530 | 537 | 542 | 548 | 555 | 563 | 568 | 575 | 581 | 588 | 595 | 601 | 609 | 617 | 625 | 632 | 639 | 646 | 654 | 661 | 668 | 676 | 684
268 | 1.4347 | 13 | 28 | 60 | 104 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 5 | 9 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 13 | 20 | 25 | 33 | 41 | 49 | 55 | 60 | 65 | 71 | 78 | 84 | 92 | 98 | 106 | 114 | 122 | 128 | 136 | 143 | 148 | 154 | 160 | 167 | 175 | 180 | 187 | 194 | 200 | 205 | 210 | 218 | 225 | 231 | 237 | 243 | 250 | 256 | 264 | 272 | 279 | 287 | 294 | 299 | 306 | 312 | 318 | 324 | 332 | 339 | 346 | 354 | 362 | 370 | 375 | 383 | 388 | 396 | 404 | 411 | 416 | 423 | 429 | 436 | 444 | 450 | 457 | 462 | 467 | 473 | 481 | 487 | 495 | 502 | 507 | 515 | 523 | 529 | 537 | 542 | 550 | 556 | 564 | 571 | 579 | 585 | 592 | 600 | 608 | 616 | 622 | 627 | 633 | 638 | 644 | 650 | 655 | 663 | 671 | 679 | 684 | 691 | 696
269 | 1.1891 | 10 | 22 | 42 | 76 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 2 | 3 | 6 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 16 | 22 | 30 | 35 | 43 | 51 | 57 | 64 | 71 | 78 | 85 | 91 | 97 | 104 | 111 | 116 | 122 | 130 | 137 | 142 | 149 | 157 | 164 | 170 | 175 | 181 | 186 | 194 | 200 | 205 | 210 | 215 | 223 | 230 | 237 | 243 | 251 | 257 | 263 | 268 | 273 | 281 | 288 | 296 | 304 | 309 | 314 | 322 | 329 | 334 | 342 | 347 | 352 | 360 | 366 | 374 | 380 | 386 | 391 | 396 | 402 | 408 | 415 | 423 | 429 | 436 | 442 | 447 | 454 | 461 | 468 | 475 | 481 | 487 | 495 | 503 | 510 | 518 | 524 | 531 | 537 | 544 | 549 | 556 | 564 | 569 | 575 | 580 | 585 | 592 | 597 | 602 | 607 | 613 | 619 | 624 | 630 | 636 | 644 | 652 | 660 | 665 | 672
270 | 1.709 | 12 | 33 | 64 | 104 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 2 | 5 | 10 | 15 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 13 | 21 | 27 | 35 | 40 | 45 | 53 | 60 | 67 | 73 | 81 | 89 | 96 | 104 | 111 | 118 | 126 | 134 | 139 | 147 | 155 | 161 | 166 | 172 | 178 | 183 | 191 | 198 | 204 | 212 | 219 | 224 | 232 | 240 | 245 | 253 | 260 | 265 | 271 | 277 | 285 | 293 | 298 | 305 | 310 | 318 | 325 | 331 | 338 | 345 | 352 | 358 | 365 | 370 | 375 | 381 | 389 | 394 | 402 | 409 | 414 | 422 | 429 | 435 | 442 | 447 | 455 | 462 | 469 | 476 | 483 | 488 | 494 | 499 | 504 | 509 | 515 | 522 | 528 | 535 | 543 | 551 | 558 | 565 | 571 | 576 | 582 | 589 | 594 | 600 | 606 | 612 | 618 | 623 | 628 | 633 | 639 | 647 | 654 | 660 | 667 | 675 | 683
271 | 1.4291 | 8 | 21 | 50 | 92 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 4 | 8 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 19 | 27 | 33 | 38 | 45 | 52 | 58 | 65 | 70 | 75 | 80 | 86 | 91 | 98 | 103 | 108 | 115 | 120 | 126 | 132 | 138 | 145 | 153 | 158 | 166 | 172 | 177 | 184 | 189 | 197 | 202 | 210 | 215 | 223 | 228 | 235 | 241 | 247 | 254 | 259 | 264 | 269 | 274 | 281 | 287 | 293 | 299 | 305 | 313 | 318 | 323 | 329 | 334 | 342 | 348 | 355 | 363 | 369 | 374 | 380 | 386 | 393 | 399 | 406 | 414 | 420 | 427 | 435 | 442 | 449 | 457 | 464 | 472 | 480 | 488 | 493 | 500 | 506 | 512 | 517 | 525 | 532 | 538 | 545 | 551 | 559 | 564 | 571 | 578 | 585 | 593 | 598 | 604 | 611 | 616 | 622 | 628 | 634 | 642 | 650 | 655 | 660
272 | 1.7763 | 11 | 29 | 70 | 115 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 2 | 5 | 12 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 11 | 18 | 25 | 30 | 36 | 41 | 49 | 54 | 59 | 65 | 72 | 78 | 86 | 94 | 102 | 109 | 114 | 122 | 129 | 135 | 143 | 148 | 154 | 159 | 165 | 172 | 178 | 186 | 194 | 201 | 208 | 215 | 223 | 231 | 238 | 246 | 251 | 257 | 262 | 269 | 274 | 280 | 288 | 293 | 299 | 307 | 313 | 321 | 329 | 336 | 344 | 350 | 358 | 363 | 370 | 375 | 381 | 386 | 393 | 400 | 407 | 415 | 421 | 427 | 434 | 440 | 446 | 452 | 459 | 466 | 474 | 481 | 486 | 491 | 496 | 504 | 511 | 518 | 526 | 534 | 540 | 546 | 552 | 558 | 564 | 569 | 576 | 581 | 588 | 593 | 600 | 608 | 616 | 621 | 626 | 631 | 636 | 643 | 651 | 658 | 665 | 670 | 677
273 | 1.0049 | 6 | 21 | 46 | 74 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 2 | 4 | 8 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 5 | 11 | 18 | 26 | 31 | 37 | 45 | 53 | 59 | 67 | 72 | 78 | 86 | 92 | 98 | 103 | 108 | 114 | 120 | 127 | 134 | 139 | 145 | 152 | 159 | 166 | 173 | 178 | 184 | 192 | 197 | 202 | 207 | 215 | 221 | 228 | 234 | 242 | 249 | 256 | 262 | 268 | 274 | 279 | 285 | 293 | 301 | 307 | 312 | 319 | 327 | 332 | 339 | 347 | 352 | 357 | 362 | 367 | 375 | 381 | 388 | 395 | 403 | 408 | 416 | 423 | 428 | 434 | 439 | 446 | 453 | 460 | 465 | 473 | 478 | 485 | 492 | 497 | 504 | 511 | 519 | 524 | 531 | 537 | 542 | 548 | 555 | 563 | 570 | 575 | 582 | 590 | 595 | 601 | 606 | 611 | 616 | 624 | 630 | 636 | 644 | 651 | 657 | 663
274 | 1.8461 | 19 | 47 | 88 | 127 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 3 | 8 | 13 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 16 | 21 | 27 | 32 | 40 | 45 | 52 | 59 | 66 | 74 | 81 | 89 | 94 | 102 | 110 | 116 | 121 | 129 | 137 | 142 | 149 | 155 | 162 | 167 | 175 | 182 | 187 | 193 | 201 | 206 | 214 | 222 | 229 | 234 | 240 | 246 | 251 | 258 | 263 | 268 | 274 | 280 | 288 | 296 | 301 | 306 | 314 | 319 | 327 | 333 | 341 | 347 | 355 | 361 | 366 | 373 | 378 | 386 | 392 | 398 | 403 | 410 | 418 | 425 | 433 | 439 | 444 | 452 | 457 | 465 | 471 | 479 | 486 | 494 | 502 | 510 | 516 | 521 | 528 | 533 | 539 | 547 | 555 | 561 | 569 | 577 | 583 | 590 | 596 | 601 | 608 | 615 | 621 | 626 | 631 | 638 | 643 | 650 | 658 | 665 | 670 | 677 | 685
275 | 1.8415 | 15 | 41 | 69 | 110 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 3 | 6 | 11 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 13 | 21 | 29 | 35 | 42 | 48 | 56 | 62 | 67 | 72 | 78 | 86 | 91 | 98 | 106 | 114 | 119 | 124 | 131 | 139 | 145 | 153 | 158 | 163 | 171 | 179 | 184 | 191 | 198 | 206 | 212 | 219 | 224 | 230 | 236 | 244 | 250 | 257 | 265 | 273 | 281 | 289 | 294 | 301 | 308 | 313 | 318 | 326 | 331 | 338 | 345 | 351 | 359 | 365 | 370 | 377 | 383 | 391 | 397 | 404 | 410 | 415 | 420 | 428 | 436 | 442 | 448 | 454 | 461 | 469 | 477 | 483 | 491 | 498 | 506 | 512 | 519 | 526 | 534 | 539 | 547 | 552 | 559 | 566 | 574 | 580 | 586 | 593 | 598 | 605 | 611 | 616 | 622 | 629 | 637 | 645 | 653 | 658 | 663 | 671 | 676 | 683 | 690
276 | 1.5731 | 10 | 26 | 63 | 97 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 2 | 5 | 10 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 5 | 10 | 18 | 24 | 30 | 35 | 40 | 48 | 56 | 64 | 72 | 78 | 86 | 94 | 102 | 109 | 115 | 121 | 129 | 136 | 141 | 149 | 156 | 162 | 169 | 175 | 183 | 189 | 197 | 205 | 210 | 216 | 221 | 226 | 231 | 239 | 245 | 250 | 255 | 263 | 268 | 276 | 281 | 286 | 294 | 299 | 306 | 313 | 319 | 326 | 331 | 339 | 346 | 352 | 358 | 364 | 370 | 377 | 383 | 391 | 397 | 402 | 410 | 415 | 420 | 427 | 432 | 437 | 445 | 453 | 460 | 466 | 472 | 478 | 483 | 491 | 498 | 506 | 512 | 519 | 524 | 531 | 537 | 544 | 550 | 555 | 561 | 566 | 573 | 578 | 585 | 591 | 596 | 602 | 609 | 616 | 622 | 629 | 635 | 641 | 648 | 653 | 658 | 665
277 | 1.6607 | 14 | 28 | 53 | 95 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 3 | 5 | 9 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 13 | 19 | 24 | 32 | 37 | 43 | 48 | 56 | 64 | 69 | 74 | 80 | 86 | 93 | 101 | 107 | 113 | 121 | 126 | 134 | 140 | 145 | 150 | 157 | 164 | 172 | 179 | 186 | 193 | 201 | 208 | 215 | 223 | 231 | 238 | 243 | 249 | 255 | 263 | 269 | 277 | 284 | 289 | 296 | 301 | 309 | 317 | 325 | 332 | 337 | 344 | 352 | 357 | 364 | 370 | 376 | 384 | 390 | 397 | 404 | 411 | 417 | 423 | 429 | 434 | 441 | 448 | 453 | 458 | 463 | 470 | 478 | 485 | 490 | 495 | 501 | 506 | 512 | 520 | 527 | 533 | 540 | 545 | 552 | 559 | 566 | 572 | 577 | 585 | 591 | 599 | 604 | 610 | 616 | 623 | 630 | 635 | 643 | 650 | 656 | 662 | 669 | 677
278 | 1.9466 | 12 | 28 | 75 | 124 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 2 | 4 | 12 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 16 | 23 | 30 | 37 | 43 | 51 | 59 | 64 | 69 | 74 | 79 | 86 | 93 | 100 | 106 | 112 | 117 | 124 | 129 | 136 | 142 | 149 | 155 | 163 | 171 | 177 | 182 | 190 | 196 | 202 | 207 | 214 | 220 | 226 | 234 | 240 | 247 | 252 | 258 | 263 | 268 | 274 | 282 | 290 | 296 | 303 | 309 | 314 | 319 | 327 | 335 | 342 | 348 | 354 | 362 | 369 | 377 | 383 | 388 | 395 | 403 | 410 | 418 | 424 | 431 | 437 | 443 | 450 | 457 | 464 | 469 | 476 | 481 | 486 | 493 | 498 | 504 | 510 | 515 | 523 | 530 | 535 | 543 | 550 | 556 | 564 | 572 | 580 | 587 | 595 | 600 | 607 | 615 | 620 | 626 | 633 | 639 | 644 | 652 | 660 | 667 | 675 | 682
279 | 1.3614 | 13 | 33 | 58 | 87 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 3 | 5 | 9 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 5 | 12 | 20 | 28 | 35 | 41 | 48 | 56 | 62 | 69 | 76 | 84 | 90 | 96 | 104 | 109 | 117 | 122 | 127 | 133 | 139 | 146 | 153 | 160 | 167 | 175 | 182 | 189 | 195 | 200 | 207 | 213 | 218 | 225 | 231 | 236 | 244 | 250 | 256 | 264 | 272 | 278 | 283 | 289 | 294 | 299 | 305 | 310 | 316 | 322 | 328 | 335 | 341 | 346 | 351 | 358 | 366 | 374 | 381 | 389 | 394 | 399 | 406 | 412 | 417 | 423 | 428 | 433 | 438 | 443 | 450 | 457 | 463 | 468 | 473 | 479 | 485 | 490 | 496 | 501 | 506 | 512 | 520 | 528 | 536 | 542 | 550 | 556 | 561 | 567 | 575 | 581 | 589 | 597 | 605 | 610 | 616 | 621 | 628 | 635 | 641 | 647 | 654 | 659
280 | 1.8053 | 19 | 39 | 72 | 109 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 3 | 6 | 11 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 16 | 21 | 29 | 36 | 42 | 48 | 53 | 59 | 65 | 72 | 78 | 84 | 91 | 98 | 104 | 112 | 120 | 127 | 132 | 140 | 145 | 151 | 157 | 164 | 172 | 178 | 183 | 191 | 197 | 202 | 207 | 214 | 220 | 228 | 233 | 241 | 249 | 256 | 261 | 268 | 275 | 282 | 288 | 296 | 301 | 306 | 314 | 321 | 327 | 335 | 343 | 349 | 356 | 364 | 370 | 376 | 384 | 391 | 399 | 405 | 410 | 416 | 423 | 428 | 433 | 438 | 444 | 449 | 456 | 463 | 471 | 478 | 485 | 491 | 497 | 504 | 511 | 517 | 524 | 530 | 535 | 543 | 551 | 559 | 567 | 574 | 580 | 585 | 590 | 595 | 602 | 609 | 617 | 624 | 632 | 637 | 643 | 649 | 655 | 662 | 670 | 675 | 681
281 | 1.5422 | 8 | 30 | 57 | 104 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 1 | 5 | 9 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 15 | 23 | 29 | 35 | 41 | 47 | 54 | 62 | 70 | 75 | 80 | 87 | 95 | 102 | 110 | 116 | 124 | 132 | 137 | 143 | 151 | 157 | 164 | 169 | 175 | 180 | 188 | 196 | 204 | 212 | 219 | 226 | 233 | 238 | 246 | 253 | 259 | 265 | 272 | 278 | 284 | 291 | 296 | 304 | 309 | 317 | 323 | 331 | 336 | 343 | 348 | 353 | 358 | 364 | 369 | 375 | 383 | 391 | 397 | 402 | 410 | 417 | 425 | 431 | 437 | 444 | 449 | 456 | 464 | 472 | 479 | 485 | 491 | 499 | 504 | 512 | 517 | 525 | 530 | 538 | 544 | 549 | 557 | 563 | 570 | 576 | 582 | 587 | 592 | 599 | 607 | 614 | 619 | 625 | 630 | 637 | 644 | 652 | 660 | 666 | 674 | 679 | 686
282 | 1.6684 | 12 | 29 | 66 | 105 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 3 | 6 | 12 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 10 | 15 | 21 | 26 | 33 | 40 | 47 | 52 | 58 | 63 | 69 | 74 | 81 | 89 | 94 | 101 | 108 | 116 | 124 | 131 | 137 | 143 | 150 | 155 | 160 | 165 | 170 | 176 | 181 | 187 | 192 | 200 | 207 | 212 | 219 | 224 | 230 | 236 | 244 | 250 | 255 | 261 | 269 | 274 | 279 | 284 | 291 | 298 | 306 | 313 | 320 | 326 | 331 | 336 | 343 | 351 | 357 | 365 | 371 | 376 | 382 | 387 | 392 | 400 | 405 | 410 | 418 | 426 | 431 | 438 | 446 | 452 | 460 | 466 | 472 | 480 | 485 | 493 | 500 | 505 | 512 | 518 | 525 | 531 | 536 | 544 | 550 | 558 | 564 | 570 | 577 | 582 | 588 | 593 | 600 | 608 | 615 | 623 | 631 | 637 | 644 | 651 | 658
283 | 1.3972 | 13 | 25 | 56 | 91 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 2 | 4 | 9 | 14 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 13 | 21 | 26 | 33 | 39 | 47 | 53 | 60 | 67 | 73 | 80 | 88 | 93 | 98 | 105 | 110 | 115 | 123 | 129 | 134 | 142 | 148 | 154 | 161 | 166 | 171 | 176 | 184 | 189 | 195 | 200 | 207 | 212 | 218 | 224 | 232 | 240 | 246 | 254 | 262 | 269 | 276 | 282 | 290 | 297 | 303 | 311 | 317 | 324 | 332 | 339 | 346 | 351 | 359 | 364 | 372 | 379 | 384 | 391 | 398 | 405 | 412 | 419 | 427 | 433 | 439 | 444 | 450 | 457 | 465 | 470 | 475 | 483 | 490 | 495 | 503 | 508 | 514 | 520 | 525 | 531 | 536 | 544 | 551 | 559 | 567 | 572 | 578 | 585 | 593 | 598 | 605 | 613 | 619 | 624 | 632 | 639 | 647 | 655 | 662 | 669 | 675 | 681
284 | 1.7391 | 16 | 34 | 74 | 127 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 3 | 6 | 13 | 22 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 10 | 16 | 21 | 28 | 35 | 42 | 47 | 53 | 58 | 63 | 68 | 75 | 81 | 88 | 93 | 99 | 104 | 111 | 118 | 126 | 132 | 140 | 147 | 154 | 161 | 167 | 173 | 179 | 184 | 191 | 196 | 203 | 209 | 217 | 223 | 231 | 238 | 245 | 253 | 261 | 266 | 274 | 281 | 289 | 294 | 300 | 306 | 313 | 320 | 328 | 333 | 339 | 347 | 354 | 361 | 368 | 374 | 379 | 387 | 392 | 399 | 407 | 413 | 419 | 426 | 431 | 438 | 446 | 453 | 461 | 467 | 473 | 478 | 483 | 491 | 497 | 504 | 511 | 516 | 521 | 526 | 534 | 540 | 547 | 554 | 562 | 570 | 575 | 582 | 589 | 597 | 603 | 611 | 618 | 623 | 629 | 637 | 643 | 649 | 655 | 661 | 667 | 675
285 | 1.722 | 14 | 39 | 70 | 120 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 3 | 7 | 11 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 11 | 17 | 22 | 30 | 37 | 44 | 50 | 58 | 65 | 71 | 79 | 87 | 95 | 100 | 106 | 114 | 119 | 126 | 132 | 140 | 145 | 150 | 156 | 161 | 169 | 177 | 185 | 191 | 196 | 201 | 209 | 215 | 220 | 226 | 231 | 238 | 244 | 249 | 256 | 264 | 272 | 278 | 283 | 290 | 297 | 302 | 308 | 316 | 323 | 328 | 336 | 344 | 352 | 358 | 366 | 372 | 377 | 384 | 389 | 394 | 401 | 406 | 413 | 418 | 425 | 430 | 437 | 445 | 450 | 458 | 463 | 471 | 478 | 485 | 492 | 497 | 502 | 510 | 517 | 525 | 531 | 539 | 544 | 549 | 555 | 561 | 566 | 573 | 579 | 585 | 590 | 597 | 602 | 609 | 614 | 622 | 627 | 633 | 638 | 646 | 654 | 662 | 668
286 | 1.9694 | 16 | 36 | 84 | 138 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 3 | 6 | 13 | 22 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 6 | 14 | 21 | 26 | 34 | 41 | 47 | 53 | 58 | 65 | 73 | 80 | 87 | 92 | 98 | 105 | 110 | 115 | 122 | 130 | 136 | 141 | 148 | 154 | 162 | 169 | 175 | 183 | 190 | 198 | 206 | 213 | 220 | 228 | 234 | 241 | 247 | 254 | 261 | 266 | 274 | 282 | 287 | 292 | 299 | 305 | 310 | 317 | 324 | 330 | 338 | 343 | 351 | 358 | 365 | 373 | 379 | 386 | 391 | 396 | 402 | 409 | 417 | 425 | 430 | 437 | 443 | 448 | 454 | 459 | 467 | 472 | 479 | 485 | 493 | 498 | 503 | 509 | 517 | 525 | 532 | 540 | 547 | 554 | 559 | 565 | 570 | 576 | 581 | 586 | 594 | 602 | 610 | 616 | 622 | 628 | 634 | 640 | 648 | 653 | 660 | 666 | 672 | 679
287 | 1.6459 | 12 | 36 | 61 | 104 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 2 | 6 | 10 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 12 | 18 | 25 | 31 | 39 | 45 | 52 | 58 | 66 | 73 | 80 | 88 | 94 | 99 | 105 | 112 | 118 | 123 | 131 | 137 | 142 | 149 | 157 | 163 | 171 | 177 | 185 | 192 | 199 | 205 | 213 | 218 | 226 | 232 | 237 | 243 | 248 | 256 | 262 | 268 | 273 | 279 | 285 | 292 | 299 | 304 | 309 | 314 | 319 | 325 | 331 | 338 | 343 | 351 | 357 | 365 | 373 | 380 | 386 | 391 | 396 | 403 | 411 | 419 | 425 | 430 | 435 | 441 | 449 | 456 | 462 | 470 | 478 | 486 | 491 | 498 | 506 | 513 | 520 | 527 | 533 | 541 | 548 | 553 | 559 | 566 | 573 | 578 | 586 | 593 | 598 | 606 | 613 | 621 | 629 | 635 | 643 | 650 | 657 | 663 | 670 | 675 | 683
288 | 1.2152 | 9 | 28 | 56 | 93 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 2 | 5 | 9 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 13 | 21 | 27 | 32 | 40 | 46 | 53 | 61 | 66 | 71 | 77 | 84 | 89 | 97 | 104 | 111 | 117 | 123 | 131 | 138 | 145 | 152 | 157 | 164 | 170 | 177 | 184 | 189 | 197 | 205 | 211 | 219 | 226 | 234 | 240 | 248 | 256 | 263 | 271 | 276 | 281 | 286 | 293 | 299 | 305 | 312 | 320 | 325 | 331 | 339 | 347 | 352 | 357 | 363 | 369 | 374 | 380 | 387 | 394 | 399 | 407 | 412 | 419 | 427 | 433 | 439 | 447 | 453 | 460 | 466 | 474 | 481 | 488 | 495 | 502 | 509 | 514 | 522 | 529 | 535 | 543 | 550 | 557 | 564 | 569 | 577 | 584 | 592 | 600 | 606 | 611 | 616 | 624 | 632 | 640 | 646 | 653 | 661 | 667 | 673 | 679 | 686 | 694
289 | 1.9678 | 20 | 38 | 68 | 122 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 4 | 6 | 12 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 7 | 12 | 17 | 25 | 32 | 38 | 44 | 51 | 56 | 62 | 67 | 75 | 81 | 86 | 93 | 99 | 105 | 110 | 118 | 126 | 133 | 138 | 144 | 149 | 157 | 162 | 168 | 173 | 181 | 188 | 193 | 199 | 206 | 212 | 219 | 224 | 229 | 236 | 243 | 248 | 253 | 259 | 264 | 271 | 279 | 285 | 290 | 295 | 303 | 308 | 314 | 320 | 325 | 332 | 338 | 345 | 353 | 361 | 368 | 375 | 382 | 390 | 398 | 406 | 412 | 419 | 427 | 433 | 441 | 449 | 455 | 462 | 468 | 474 | 481 | 489 | 495 | 500 | 507 | 514 | 522 | 527 | 534 | 541 | 547 | 555 | 563 | 570 | 575 | 580 | 586 | 592 | 599 | 606 | 614 | 619 | 626 | 631 | 636 | 641 | 649 | 655 | 663 | 669
290 | 1.8041 | 13 | 28 | 59 | 112 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 2 | 4 | 9 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 8 | 16 | 22 | 28 | 35 | 41 | 49 | 55 | 61 | 69 | 75 | 80 | 87 | 92 | 97 | 103 | 110 | 117 | 125 | 132 | 139 | 147 | 152 | 158 | 164 | 170 | 175 | 182 | 190 | 196 | 203 | 211 | 219 | 226 | 234 | 241 | 249 | 255 | 261 | 269 | 276 | 283 | 288 | 295 | 300 | 307 | 314 | 321 | 327 | 333 | 338 | 343 | 350 | 356 | 363 | 370 | 377 | 383 | 389 | 397 | 402 | 409 | 417 | 423 | 430 | 436 | 441 | 447 | 453 | 460 | 467 | 475 | 481 | 488 | 493 | 499 | 505 | 510 | 517 | 525 | 530 | 536 | 541 | 547 | 555 | 560 | 566 | 574 | 581 | 587 | 594 | 601 | 608 | 616 | 623 | 630 | 637 | 645 | 651 | 657 | 665 | 670 | 676 | 682
291 | 1.631 | 9 | 32 | 73 | 108 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 2 | 5 | 11 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 15 | 23 | 29 | 37 | 42 | 49 | 56 | 63 | 71 | 79 | 87 | 94 | 100 | 108 | 114 | 120 | 128 | 133 | 139 | 147 | 155 | 163 | 168 | 175 | 182 | 188 | 193 | 200 | 205 | 210 | 217 | 222 | 227 | 234 | 240 | 245 | 253 | 260 | 265 | 272 | 280 | 286 | 294 | 301 | 308 | 316 | 324 | 331 | 339 | 346 | 351 | 358 | 364 | 371 | 377 | 382 | 390 | 398 | 404 | 411 | 418 | 426 | 431 | 437 | 443 | 449 | 456 | 463 | 470 | 475 | 482 | 487 | 494 | 499 | 506 | 511 | 519 | 527 | 533 | 539 | 545 | 550 | 558 | 565 | 570 | 575 | 581 | 588 | 594 | 602 | 608 | 614 | 620 | 628 | 633 | 640 | 648 | 656 | 663 | 668 | 673 | 681 | 687
292 | 1.8972 | 12 | 37 | 72 | 110 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 3 | 6 | 12 | 18 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 6 | 11 | 18 | 24 | 29 | 37 | 43 | 50 | 58 | 63 | 69 | 75 | 80 | 88 | 94 | 100 | 107 | 112 | 117 | 123 | 131 | 136 | 141 | 146 | 153 | 159 | 164 | 169 | 174 | 182 | 189 | 194 | 200 | 205 | 213 | 218 | 223 | 228 | 235 | 243 | 251 | 259 | 264 | 269 | 277 | 284 | 291 | 298 | 305 | 310 | 315 | 323 | 329 | 335 | 341 | 347 | 352 | 359 | 366 | 371 | 379 | 387 | 392 | 399 | 406 | 412 | 420 | 426 | 431 | 438 | 445 | 451 | 458 | 463 | 468 | 473 | 481 | 486 | 493 | 501 | 507 | 512 | 517 | 525 | 532 | 540 | 547 | 553 | 558 | 566 | 574 | 581 | 587 | 594 | 600 | 605 | 612 | 617 | 625 | 631 | 638 | 644 | 649 | 657
293 | 1.7925 | 18 | 33 | 73 | 127 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 3 | 5 | 11 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 15 | 23 | 31 | 39 | 45 | 51 | 58 | 65 | 72 | 77 | 83 | 88 | 95 | 103 | 110 | 115 | 121 | 129 | 137 | 143 | 150 | 156 | 161 | 168 | 173 | 178 | 183 | 191 | 196 | 203 | 210 | 217 | 225 | 233 | 240 | 246 | 253 | 258 | 265 | 273 | 279 | 287 | 293 | 299 | 307 | 314 | 322 | 328 | 335 | 341 | 347 | 354 | 361 | 367 | 374 | 379 | 385 | 391 | 397 | 405 | 413 | 421 | 428 | 435 | 443 | 449 | 454 | 461 | 467 | 475 | 483 | 491 | 497 | 502 | 508 | 516 | 524 | 530 | 538 | 544 | 552 | 560 | 568 | 575 | 581 | 589 | 596 | 604 | 610 | 617 | 625 | 633 | 641 | 649 | 657 | 662 | 667 | 673 | 678 | 683 | 688 | 696 | 704
294 | 1.1355 | 10 | 26 | 44 | 67 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 2 | 4 | 7 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 15 | 22 | 27 | 35 | 40 | 48 | 56 | 64 | 69 | 74 | 79 | 87 | 92 | 100 | 107 | 115 | 122 | 127 | 133 | 140 | 147 | 154 | 162 | 169 | 177 | 185 | 191 | 199 | 207 | 215 | 222 | 228 | 234 | 241 | 247 | 254 | 259 | 267 | 272 | 280 | 285 | 291 | 299 | 304 | 311 | 317 | 322 | 328 | 334 | 342 | 350 | 358 | 364 | 372 | 378 | 385 | 392 | 397 | 403 | 410 | 416 | 424 | 430 | 435 | 440 | 447 | 454 | 462 | 469 | 476 | 483 | 488 | 496 | 504 | 510 | 515 | 522 | 530 | 538 | 546 | 553 | 560 | 567 | 575 | 581 | 587 | 594 | 601 | 609 | 615 | 620 | 628 | 636 | 642 | 649 | 655 | 662 | 667 | 673 | 679 | 685 | 693 | 699
295 | 1.287 | 11 | 24 | 48 | 83 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 4 | 7 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 15 | 22 | 29 | 36 | 43 | 49 | 56 | 63 | 70 | 78 | 85 | 90 | 96 | 102 | 107 | 115 | 122 | 128 | 135 | 140 | 148 | 154 | 159 | 167 | 174 | 182 | 188 | 193 | 201 | 206 | 211 | 217 | 224 | 231 | 237 | 242 | 250 | 258 | 266 | 274 | 282 | 289 | 296 | 301 | 306 | 311 | 317 | 322 | 330 | 336 | 342 | 348 | 355 | 361 | 367 | 372 | 378 | 385 | 393 | 400 | 405 | 411 | 416 | 422 | 430 | 435 | 443 | 448 | 456 | 463 | 471 | 476 | 482 | 490 | 497 | 502 | 509 | 514 | 520 | 526 | 533 | 541 | 549 | 556 | 562 | 570 | 577 | 583 | 591 | 597 | 603 | 610 | 617 | 622 | 629 | 636 | 643 | 650 | 655 | 663 | 669 | 676 | 684
296 | 1.3172 | 11 | 30 | 53 | 81 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 3 | 6 | 10 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 5 | 10 | 15 | 21 | 28 | 33 | 39 | 44 | 49 | 55 | 63 | 69 | 75 | 83 | 89 | 94 | 101 | 108 | 115 | 121 | 129 | 135 | 142 | 148 | 154 | 161 | 167 | 173 | 181 | 189 | 194 | 202 | 210 | 217 | 224 | 231 | 239 | 246 | 252 | 259 | 264 | 270 | 278 | 283 | 289 | 294 | 300 | 305 | 313 | 319 | 326 | 331 | 338 | 345 | 352 | 357 | 363 | 369 | 376 | 382 | 390 | 395 | 403 | 409 | 416 | 421 | 428 | 436 | 444 | 449 | 457 | 464 | 469 | 474 | 480 | 488 | 496 | 501 | 509 | 516 | 524 | 532 | 537 | 544 | 551 | 559 | 567 | 572 | 577 | 583 | 589 | 597 | 605 | 613 | 621 | 627 | 635 | 643 | 651 | 659 | 665 | 673 | 678 | 685
297 | 1.7422 | 14 | 41 | 83 | 118 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 3 | 7 | 14 | 19 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 13 | 18 | 23 | 30 | 38 | 43 | 48 | 54 | 59 | 66 | 74 | 82 | 88 | 94 | 101 | 106 | 114 | 121 | 128 | 134 | 140 | 147 | 153 | 159 | 164 | 171 | 178 | 184 | 191 | 196 | 201 | 208 | 216 | 224 | 231 | 239 | 244 | 252 | 258 | 264 | 269 | 277 | 282 | 290 | 296 | 301 | 306 | 313 | 319 | 325 | 331 | 338 | 346 | 352 | 360 | 366 | 373 | 380 | 385 | 392 | 397 | 403 | 408 | 416 | 424 | 429 | 434 | 440 | 445 | 451 | 457 | 465 | 473 | 480 | 488 | 496 | 504 | 509 | 514 | 522 | 527 | 534 | 540 | 548 | 553 | 559 | 565 | 570 | 575 | 580 | 586 | 592 | 598 | 603 | 609 | 614 | 621 | 626 | 633 | 639 | 645 | 650 | 655
298 | 1.3291 | 7 | 26 | 58 | 86 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 1 | 4 | 8 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 15 | 23 | 31 | 38 | 46 | 53 | 61 | 69 | 75 | 83 | 91 | 96 | 103 | 111 | 116 | 123 | 129 | 134 | 140 | 147 | 153 | 158 | 164 | 169 | 174 | 182 | 190 | 198 | 205 | 211 | 218 | 224 | 229 | 234 | 241 | 249 | 255 | 263 | 269 | 277 | 283 | 290 | 295 | 301 | 306 | 312 | 317 | 323 | 330 | 335 | 342 | 349 | 357 | 362 | 368 | 376 | 383 | 388 | 396 | 402 | 407 | 413 | 419 | 424 | 432 | 437 | 444 | 450 | 458 | 466 | 471 | 477 | 485 | 492 | 499 | 507 | 513 | 519 | 526 | 534 | 539 | 547 | 552 | 559 | 566 | 571 | 578 | 584 | 590 | 597 | 602 | 608 | 613 | 621 | 626 | 632 | 638 | 643 | 651 | 656 | 664 | 670 | 676
299 | 1.8707 | 12 | 37 | 67 | 109 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 2 | 6 | 11 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 14 | 20 | 26 | 34 | 42 | 47 | 52 | 59 | 66 | 72 | 79 | 84 | 92 | 100 | 107 | 113 | 118 | 126 | 131 | 137 | 142 | 147 | 152 | 157 | 162 | 167 | 175 | 182 | 188 | 195 | 200 | 207 | 215 | 220 | 225 | 231 | 237 | 245 | 250 | 255 | 263 | 269 | 274 | 280 | 285 | 291 | 299 | 305 | 313 | 319 | 325 | 333 | 340 | 346 | 352 | 360 | 365 | 373 | 380 | 386 | 392 | 400 | 408 | 416 | 421 | 429 | 437 | 444 | 452 | 458 | 466 | 473 | 478 | 483 | 490 | 497 | 503 | 508 | 514 | 520 | 528 | 534 | 539 | 547 | 555 | 560 | 566 | 574 | 582 | 588 | 596 | 601 | 607 | 613 | 620 | 626 | 633 | 640 | 647 | 653 | 660 | 668 | 673
300 | 1.45 | 8 | 23 | 52 | 84 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 4 | 8 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 11 | 19 | 27 | 32 | 38 | 46 | 52 | 59 | 66 | 74 | 79 | 86 | 91 | 97 | 103 | 108 | 114 | 119 | 126 | 133 | 141 | 146 | 152 | 158 | 163 | 170 | 175 | 181 | 187 | 194 | 199 | 205 | 211 | 216 | 221 | 229 | 235 | 241 | 247 | 252 | 257 | 263 | 268 | 275 | 283 | 288 | 295 | 302 | 307 | 314 | 322 | 329 | 337 | 344 | 350 | 357 | 364 | 370 | 376 | 383 | 388 | 394 | 401 | 408 | 413 | 419 | 424 | 432 | 437 | 442 | 448 | 454 | 460 | 468 | 476 | 481 | 487 | 493 | 498 | 503 | 510 | 517 | 522 | 529 | 536 | 544 | 549 | 556 | 562 | 570 | 576 | 584 | 589 | 595 | 600 | 606 | 613 | 618 | 626 | 632 | 637 | 642 | 647
301 | 1.1764 | 10 | 26 | 50 | 80 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 2 | 5 | 9 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 13 | 18 | 23 | 30 | 37 | 42 | 49 | 55 | 63 | 70 | 75 | 82 | 90 | 95 | 101 | 108 | 114 | 119 | 127 | 135 | 142 | 150 | 156 | 164 | 171 | 179 | 185 | 192 | 198 | 206 | 214 | 219 | 225 | 232 | 238 | 245 | 251 | 257 | 262 | 269 | 274 | 279 | 285 | 290 | 297 | 302 | 309 | 316 | 322 | 329 | 337 | 342 | 348 | 355 | 361 | 368 | 374 | 379 | 387 | 392 | 397 | 403 | 410 | 416 | 422 | 427 | 434 | 439 | 445 | 450 | 456 | 464 | 470 | 476 | 481 | 486 | 493 | 499 | 504 | 510 | 515 | 523 | 531 | 538 | 545 | 552 | 559 | 566 | 571 | 577 | 584 | 590 | 596 | 602 | 607 | 613 | 618 | 623 | 629 | 634 | 641 | 646 | 653
302 | 1.303 | 7 | 27 | 47 | 84 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 1 | 4 | 8 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 14 | 21 | 28 | 33 | 39 | 45 | 50 | 56 | 63 | 68 | 76 | 81 | 86 | 91 | 97 | 105 | 113 | 120 | 127 | 133 | 139 | 145 | 152 | 157 | 163 | 171 | 176 | 184 | 192 | 197 | 204 | 211 | 216 | 223 | 230 | 235 | 240 | 247 | 252 | 257 | 263 | 269 | 276 | 283 | 288 | 295 | 302 | 310 | 318 | 324 | 331 | 337 | 342 | 347 | 354 | 359 | 365 | 372 | 378 | 386 | 394 | 399 | 406 | 414 | 422 | 427 | 433 | 439 | 444 | 452 | 458 | 466 | 471 | 477 | 485 | 492 | 499 | 505 | 513 | 520 | 527 | 533 | 539 | 544 | 550 | 556 | 562 | 569 | 575 | 580 | 588 | 593 | 601 | 606 | 611 | 617 | 622 | 629 | 634 | 640 | 647 | 655 | 662
303 | 1.9617 | 20 | 36 | 70 | 114 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 4 | 6 | 11 | 18 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 10 | 18 | 26 | 32 | 39 | 45 | 53 | 58 | 64 | 71 | 79 | 87 | 93 | 98 | 105 | 113 | 121 | 127 | 135 | 143 | 150 | 155 | 161 | 167 | 173 | 178 | 186 | 194 | 202 | 210 | 217 | 224 | 229 | 235 | 243 | 250 | 256 | 264 | 269 | 275 | 280 | 287 | 294 | 299 | 304 | 312 | 317 | 323 | 329 | 335 | 342 | 347 | 352 | 358 | 365 | 373 | 381 | 387 | 393 | 401 | 409 | 414 | 420 | 426 | 431 | 438 | 444 | 449 | 455 | 463 | 468 | 474 | 480 | 488 | 496 | 504 | 510 | 516 | 521 | 527 | 534 | 542 | 549 | 556 | 561 | 569 | 575 | 582 | 589 | 596 | 604 | 609 | 615 | 622 | 628 | 635 | 641 | 648 | 656 | 662 | 668 | 675 | 683
304 | 1.5059 | 11 | 34 | 69 | 106 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 2 | 5 | 11 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 14 | 22 | 28 | 35 | 41 | 49 | 55 | 61 | 67 | 73 | 79 | 84 | 91 | 97 | 102 | 109 | 117 | 125 | 131 | 138 | 146 | 151 | 159 | 166 | 174 | 181 | 187 | 195 | 203 | 211 | 216 | 223 | 229 | 236 | 241 | 248 | 255 | 262 | 270 | 277 | 285 | 291 | 296 | 301 | 309 | 314 | 322 | 330 | 336 | 341 | 346 | 353 | 361 | 368 | 376 | 384 | 392 | 400 | 406 | 411 | 416 | 424 | 429 | 434 | 442 | 447 | 455 | 460 | 465 | 470 | 475 | 482 | 488 | 496 | 501 | 506 | 511 | 518 | 523 | 531 | 539 | 547 | 554 | 560 | 566 | 574 | 581 | 588 | 594 | 599 | 606 | 613 | 618 | 623 | 629 | 635 | 640 | 648 | 656 | 661 | 666 | 671 | 678
305 | 1.4526 | 14 | 33 | 67 | 101 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 3 | 6 | 11 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 10 | 15 | 23 | 29 | 37 | 42 | 47 | 55 | 63 | 71 | 76 | 84 | 91 | 96 | 102 | 109 | 115 | 121 | 127 | 132 | 139 | 145 | 150 | 155 | 163 | 168 | 173 | 181 | 188 | 196 | 202 | 209 | 217 | 224 | 231 | 236 | 244 | 250 | 257 | 264 | 269 | 274 | 281 | 288 | 293 | 298 | 306 | 312 | 319 | 324 | 331 | 337 | 345 | 352 | 359 | 365 | 373 | 381 | 388 | 394 | 401 | 407 | 413 | 420 | 428 | 434 | 439 | 447 | 452 | 459 | 467 | 475 | 480 | 485 | 490 | 498 | 506 | 511 | 518 | 525 | 531 | 536 | 541 | 547 | 554 | 559 | 565 | 572 | 579 | 585 | 590 | 596 | 604 | 612 | 617 | 623 | 628 | 634 | 641 | 646 | 654 | 659 | 665
306 | 1.0152 | 6 | 21 | 46 | 70 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 2 | 4 | 8 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 11 | 18 | 24 | 32 | 37 | 45 | 52 | 58 | 64 | 72 | 79 | 85 | 92 | 99 | 107 | 115 | 122 | 128 | 133 | 138 | 146 | 154 | 162 | 167 | 174 | 181 | 186 | 194 | 202 | 209 | 216 | 224 | 230 | 237 | 245 | 250 | 257 | 265 | 272 | 278 | 286 | 293 | 298 | 306 | 313 | 321 | 328 | 333 | 338 | 345 | 352 | 359 | 367 | 374 | 379 | 387 | 392 | 397 | 403 | 408 | 413 | 418 | 424 | 432 | 438 | 444 | 449 | 454 | 460 | 467 | 473 | 478 | 485 | 490 | 495 | 502 | 508 | 515 | 520 | 525 | 532 | 539 | 547 | 555 | 563 | 571 | 579 | 586 | 594 | 601 | 606 | 613 | 621 | 627 | 634 | 640 | 648 | 655 | 661 | 667 | 674 | 679 | 687
307 | 1.7034 | 16 | 40 | 76 | 117 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 3 | 7 | 14 | 20 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 6 | 11 | 18 | 23 | 28 | 34 | 41 | 46 | 52 | 60 | 65 | 70 | 75 | 81 | 88 | 95 | 100 | 105 | 112 | 117 | 125 | 131 | 136 | 142 | 148 | 155 | 160 | 167 | 174 | 181 | 186 | 194 | 199 | 206 | 213 | 218 | 225 | 233 | 240 | 247 | 255 | 261 | 266 | 274 | 280 | 287 | 295 | 300 | 306 | 312 | 318 | 325 | 332 | 339 | 344 | 350 | 356 | 364 | 369 | 376 | 384 | 390 | 398 | 405 | 411 | 416 | 424 | 429 | 435 | 442 | 447 | 453 | 460 | 467 | 475 | 483 | 488 | 494 | 500 | 505 | 511 | 516 | 522 | 528 | 533 | 539 | 544 | 552 | 560 | 566 | 573 | 580 | 586 | 593 | 598 | 606 | 611 | 617 | 625 | 632 | 639 | 646 | 653 | 660
308 | 1.7764 | 9 | 34 | 72 | 115 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 2 | 5 | 11 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 14 | 22 | 27 | 34 | 40 | 48 | 54 | 61 | 66 | 73 | 81 | 89 | 95 | 102 | 108 | 114 | 120 | 125 | 133 | 141 | 146 | 153 | 160 | 165 | 171 | 178 | 186 | 191 | 197 | 205 | 210 | 216 | 224 | 231 | 239 | 247 | 252 | 257 | 262 | 269 | 277 | 283 | 290 | 298 | 305 | 313 | 320 | 327 | 335 | 340 | 345 | 350 | 357 | 365 | 372 | 380 | 387 | 395 | 400 | 408 | 416 | 423 | 429 | 434 | 440 | 445 | 450 | 455 | 461 | 468 | 475 | 480 | 487 | 494 | 499 | 505 | 510 | 518 | 525 | 532 | 539 | 547 | 555 | 561 | 566 | 572 | 578 | 584 | 589 | 596 | 601 | 606 | 611 | 618 | 626 | 634 | 640 | 646 | 651 | 657 | 663 | 671 | 679
309 | 1.822 | 13 | 39 | 81 | 118 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 2 | 6 | 13 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 6 | 14 | 21 | 27 | 32 | 39 | 47 | 55 | 60 | 66 | 71 | 77 | 82 | 89 | 96 | 102 | 109 | 117 | 122 | 129 | 135 | 142 | 147 | 152 | 158 | 163 | 168 | 173 | 181 | 189 | 197 | 205 | 213 | 220 | 226 | 234 | 241 | 249 | 256 | 262 | 269 | 277 | 285 | 291 | 296 | 301 | 309 | 316 | 324 | 331 | 339 | 344 | 352 | 357 | 365 | 372 | 380 | 386 | 393 | 399 | 405 | 410 | 415 | 422 | 429 | 436 | 444 | 450 | 456 | 461 | 466 | 473 | 479 | 485 | 492 | 500 | 507 | 512 | 517 | 522 | 530 | 535 | 543 | 549 | 554 | 562 | 569 | 575 | 581 | 587 | 595 | 600 | 605 | 613 | 619 | 625 | 632 | 640 | 648 | 656 | 663 | 669 | 676 | 681
310 | 1.1877 | 11 | 21 | 42 | 77 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 3 | 7 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 15 | 21 | 27 | 32 | 37 | 43 | 51 | 59 | 67 | 75 | 81 | 88 | 95 | 100 | 108 | 114 | 120 | 126 | 133 | 141 | 147 | 155 | 162 | 169 | 176 | 181 | 187 | 195 | 200 | 205 | 210 | 216 | 224 | 232 | 239 | 244 | 250 | 257 | 262 | 269 | 277 | 284 | 291 | 299 | 304 | 309 | 316 | 323 | 329 | 336 | 341 | 347 | 355 | 362 | 368 | 374 | 380 | 386 | 391 | 397 | 405 | 410 | 415 | 423 | 431 | 439 | 444 | 451 | 459 | 467 | 472 | 478 | 486 | 492 | 497 | 504 | 509 | 515 | 521 | 527 | 533 | 540 | 548 | 555 | 560 | 568 | 576 | 581 | 586 | 592 | 600 | 607 | 615 | 620 | 625 | 633 | 640 | 646 | 653 | 659 | 667 | 675 | 681
311 | 1.2273 | 12 | 26 | 57 | 87 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 3 | 5 | 9 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 10 | 15 | 23 | 29 | 35 | 43 | 50 | 58 | 64 | 70 | 75 | 80 | 85 | 92 | 98 | 106 | 111 | 118 | 124 | 131 | 136 | 142 | 147 | 154 | 160 | 165 | 171 | 178 | 184 | 190 | 196 | 202 | 209 | 216 | 221 | 226 | 231 | 238 | 245 | 253 | 259 | 266 | 272 | 277 | 282 | 287 | 295 | 301 | 309 | 314 | 321 | 326 | 332 | 340 | 348 | 354 | 361 | 366 | 373 | 381 | 386 | 392 | 400 | 408 | 415 | 422 | 427 | 432 | 438 | 445 | 451 | 456 | 463 | 471 | 476 | 482 | 487 | 493 | 500 | 508 | 516 | 523 | 528 | 534 | 540 | 545 | 550 | 557 | 564 | 570 | 577 | 584 | 589 | 597 | 604 | 610 | 616 | 622 | 629 | 636 | 644 | 652 | 657
312 | 1.4163 | 13 | 33 | 56 | 90 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 2 | 6 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 13 | 18 | 24 | 32 | 39 | 44 | 52 | 60 | 66 | 73 | 80 | 85 | 90 | 95 | 102 | 109 | 116 | 122 | 129 | 134 | 139 | 145 | 152 | 158 | 166 | 174 | 179 | 187 | 193 | 201 | 209 | 214 | 220 | 226 | 234 | 240 | 245 | 253 | 260 | 266 | 271 | 277 | 284 | 290 | 296 | 303 | 309 | 317 | 324 | 332 | 337 | 343 | 348 | 356 | 361 | 368 | 373 | 378 | 384 | 390 | 396 | 404 | 409 | 416 | 422 | 428 | 435 | 441 | 449 | 455 | 461 | 467 | 474 | 481 | 488 | 494 | 502 | 507 | 512 | 518 | 524 | 531 | 536 | 542 | 550 | 556 | 563 | 570 | 576 | 582 | 589 | 597 | 604 | 610 | 618 | 625 | 632 | 638 | 644 | 651 | 658 | 665 | 671
313 | 1.6762 | 17 | 39 | 75 | 114 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 3 | 6 | 12 | 18 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 7 | 15 | 22 | 29 | 35 | 42 | 48 | 53 | 58 | 64 | 70 | 77 | 84 | 89 | 97 | 105 | 110 | 117 | 124 | 131 | 137 | 143 | 148 | 154 | 160 | 167 | 175 | 181 | 187 | 194 | 202 | 207 | 214 | 221 | 229 | 234 | 240 | 246 | 252 | 257 | 262 | 270 | 278 | 284 | 292 | 299 | 306 | 311 | 317 | 323 | 330 | 337 | 344 | 352 | 358 | 365 | 372 | 380 | 388 | 394 | 399 | 404 | 410 | 415 | 422 | 428 | 435 | 440 | 448 | 453 | 459 | 465 | 472 | 480 | 485 | 490 | 496 | 503 | 509 | 515 | 523 | 530 | 537 | 543 | 548 | 554 | 560 | 567 | 575 | 583 | 590 | 597 | 604 | 611 | 619 | 626 | 634 | 639 | 647 | 653 | 660 | 668 | 675 | 683
314 | 1.4479 | 15 | 29 | 63 | 101 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 3 | 5 | 10 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 13 | 20 | 28 | 33 | 38 | 45 | 52 | 60 | 65 | 73 | 79 | 87 | 94 | 101 | 109 | 115 | 122 | 130 | 136 | 144 | 151 | 157 | 163 | 169 | 175 | 183 | 189 | 197 | 205 | 213 | 218 | 223 | 229 | 235 | 241 | 247 | 252 | 259 | 264 | 270 | 278 | 284 | 289 | 297 | 305 | 313 | 320 | 326 | 333 | 340 | 348 | 353 | 359 | 366 | 371 | 379 | 387 | 394 | 401 | 409 | 417 | 423 | 430 | 436 | 442 | 447 | 453 | 461 | 466 | 473 | 478 | 486 | 493 | 499 | 506 | 513 | 519 | 526 | 531 | 538 | 545 | 551 | 558 | 564 | 569 | 577 | 582 | 587 | 592 | 599 | 607 | 614 | 621 | 626 | 631 | 636 | 641 | 648 | 653 | 660 | 666 | 673 | 679
315 | 1.1821 | 10 | 22 | 44 | 75 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 2 | 4 | 7 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 5 | 12 | 20 | 25 | 32 | 40 | 47 | 54 | 60 | 68 | 74 | 82 | 88 | 93 | 101 | 109 | 114 | 120 | 125 | 130 | 135 | 143 | 149 | 155 | 161 | 166 | 174 | 182 | 189 | 197 | 202 | 208 | 214 | 220 | 226 | 231 | 236 | 244 | 250 | 256 | 263 | 269 | 274 | 279 | 286 | 291 | 299 | 307 | 313 | 318 | 324 | 332 | 338 | 343 | 350 | 358 | 363 | 370 | 377 | 383 | 389 | 396 | 404 | 409 | 417 | 422 | 428 | 433 | 438 | 445 | 452 | 457 | 462 | 469 | 474 | 481 | 488 | 495 | 502 | 508 | 516 | 523 | 531 | 539 | 544 | 552 | 558 | 566 | 572 | 578 | 585 | 593 | 599 | 606 | 613 | 618 | 626 | 633 | 638 | 643 | 651 | 659 | 664 | 669
316 | 1.4805 | 11 | 23 | 53 | 85 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 2 | 4 | 9 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 11 | 19 | 27 | 32 | 40 | 45 | 51 | 58 | 66 | 73 | 80 | 88 | 96 | 102 | 108 | 114 | 119 | 125 | 131 | 136 | 141 | 148 | 153 | 160 | 167 | 172 | 177 | 185 | 190 | 195 | 203 | 209 | 217 | 222 | 230 | 236 | 243 | 249 | 255 | 260 | 267 | 275 | 280 | 288 | 293 | 301 | 307 | 314 | 320 | 326 | 334 | 339 | 347 | 353 | 359 | 366 | 372 | 377 | 383 | 389 | 395 | 403 | 409 | 416 | 422 | 429 | 434 | 439 | 444 | 450 | 457 | 464 | 472 | 480 | 488 | 495 | 502 | 510 | 515 | 523 | 530 | 538 | 544 | 551 | 556 | 563 | 568 | 575 | 581 | 588 | 595 | 603 | 610 | 616 | 621 | 628 | 633 | 638 | 643 | 650 | 658 | 664 | 670
317 | 1.0483 | 8 | 19 | 44 | 76 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 2 | 3 | 7 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 12 | 20 | 27 | 35 | 42 | 48 | 54 | 60 | 67 | 73 | 79 | 85 | 91 | 98 | 106 | 114 | 122 | 128 | 133 | 140 | 145 | 152 | 157 | 162 | 169 | 174 | 179 | 187 | 193 | 201 | 208 | 213 | 221 | 226 | 231 | 236 | 242 | 247 | 255 | 263 | 270 | 278 | 284 | 291 | 298 | 304 | 310 | 318 | 324 | 332 | 340 | 346 | 353 | 359 | 364 | 370 | 376 | 382 | 389 | 396 | 403 | 411 | 416 | 424 | 430 | 436 | 444 | 451 | 457 | 463 | 469 | 476 | 484 | 492 | 499 | 505 | 513 | 521 | 528 | 534 | 539 | 546 | 553 | 559 | 566 | 574 | 579 | 584 | 592 | 600 | 605 | 613 | 619 | 626 | 631 | 639 | 645 | 653 | 661 | 669 | 676 | 681 | 687
318 | 1.5041 | 16 | 29 | 54 | 85 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 3 | 5 | 9 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 15 | 23 | 28 | 34 | 41 | 46 | 51 | 57 | 65 | 73 | 81 | 86 | 94 | 102 | 107 | 113 | 121 | 127 | 135 | 142 | 150 | 156 | 163 | 168 | 173 | 179 | 184 | 190 | 198 | 204 | 211 | 217 | 222 | 227 | 234 | 239 | 245 | 252 | 258 | 264 | 270 | 278 | 285 | 290 | 297 | 303 | 311 | 318 | 325 | 331 | 339 | 344 | 352 | 358 | 365 | 371 | 376 | 381 | 389 | 394 | 399 | 406 | 414 | 421 | 427 | 433 | 441 | 448 | 456 | 462 | 467 | 472 | 480 | 486 | 491 | 496 | 501 | 508 | 516 | 523 | 530 | 538 | 543 | 551 | 556 | 563 | 568 | 574 | 581 | 588 | 594 | 600 | 605 | 611 | 616 | 624 | 632 | 637 | 645 | 652 | 660 | 666 | 674
319 | 1.3153 | 8 | 28 | 60 | 93 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 5 | 10 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 13 | 19 | 25 | 30 | 38 | 44 | 52 | 58 | 66 | 74 | 82 | 89 | 95 | 100 | 105 | 110 | 115 | 120 | 126 | 132 | 138 | 144 | 152 | 158 | 163 | 170 | 175 | 183 | 191 | 196 | 203 | 210 | 215 | 222 | 230 | 237 | 245 | 251 | 258 | 264 | 271 | 278 | 284 | 291 | 296 | 303 | 311 | 317 | 322 | 329 | 335 | 340 | 345 | 350 | 358 | 366 | 372 | 379 | 386 | 392 | 398 | 406 | 411 | 418 | 425 | 433 | 440 | 446 | 452 | 460 | 465 | 472 | 477 | 483 | 490 | 497 | 502 | 508 | 515 | 520 | 527 | 534 | 539 | 544 | 552 | 558 | 566 | 573 | 581 | 588 | 594 | 599 | 604 | 609 | 615 | 622 | 627 | 635 | 642 | 650 | 657 | 662 | 669
320 | 1.5697 | 15 | 37 | 72 | 120 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 2 | 6 | 12 | 19 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 15 | 22 | 27 | 33 | 40 | 46 | 54 | 59 | 65 | 71 | 77 | 82 | 88 | 94 | 102 | 110 | 118 | 124 | 129 | 136 | 141 | 146 | 154 | 161 | 168 | 174 | 179 | 187 | 193 | 198 | 203 | 209 | 214 | 222 | 228 | 235 | 240 | 248 | 256 | 261 | 268 | 273 | 280 | 285 | 293 | 301 | 309 | 316 | 324 | 332 | 337 | 342 | 350 | 355 | 361 | 369 | 374 | 382 | 387 | 393 | 400 | 407 | 414 | 421 | 427 | 432 | 439 | 445 | 453 | 458 | 464 | 469 | 476 | 483 | 491 | 499 | 507 | 514 | 520 | 526 | 532 | 539 | 546 | 553 | 559 | 565 | 572 | 580 | 586 | 593 | 599 | 607 | 612 | 617 | 623 | 628 | 633 | 641 | 646 | 652 | 659 | 666 | 674
321 | 1.4521 | 8 | 24 | 54 | 86 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 2 | 4 | 10 | 14 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 12 | 17 | 24 | 31 | 37 | 42 | 47 | 52 | 60 | 68 | 73 | 78 | 86 | 92 | 99 | 107 | 115 | 120 | 127 | 134 | 139 | 145 | 150 | 158 | 163 | 170 | 175 | 182 | 188 | 194 | 201 | 209 | 214 | 222 | 229 | 236 | 241 | 246 | 251 | 257 | 264 | 270 | 278 | 285 | 292 | 299 | 307 | 312 | 319 | 326 | 334 | 339 | 345 | 353 | 361 | 366 | 374 | 380 | 388 | 395 | 401 | 406 | 411 | 416 | 422 | 427 | 435 | 443 | 450 | 457 | 465 | 473 | 479 | 484 | 492 | 498 | 504 | 511 | 516 | 523 | 528 | 535 | 542 | 548 | 556 | 561 | 566 | 573 | 578 | 583 | 589 | 595 | 602 | 608 | 613 | 620 | 628 | 633 | 640 | 646 | 654 | 660 | 668
322 | 1.8849 | 14 | 33 | 66 | 123 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 2 | 5 | 11 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 14 | 21 | 28 | 36 | 44 | 49 | 55 | 60 | 65 | 72 | 77 | 85 | 92 | 97 | 105 | 113 | 120 | 127 | 135 | 142 | 150 | 155 | 162 | 169 | 174 | 180 | 185 | 190 | 195 | 203 | 211 | 218 | 224 | 231 | 236 | 244 | 252 | 258 | 264 | 271 | 276 | 281 | 287 | 294 | 299 | 305 | 311 | 316 | 322 | 327 | 335 | 342 | 348 | 356 | 364 | 372 | 379 | 384 | 392 | 400 | 408 | 415 | 420 | 427 | 435 | 440 | 447 | 453 | 458 | 466 | 472 | 479 | 484 | 492 | 497 | 502 | 508 | 514 | 519 | 526 | 531 | 537 | 542 | 547 | 553 | 561 | 567 | 574 | 581 | 588 | 594 | 602 | 608 | 614 | 622 | 627 | 635 | 643 | 649 | 656 | 661 | 667 | 673
323 | 1.3989 | 9 | 29 | 62 | 92 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 5 | 10 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 13 | 19 | 25 | 32 | 38 | 44 | 52 | 59 | 65 | 73 | 80 | 88 | 95 | 101 | 106 | 112 | 119 | 126 | 131 | 137 | 144 | 151 | 159 | 167 | 172 | 179 | 186 | 191 | 199 | 207 | 212 | 220 | 225 | 230 | 237 | 242 | 249 | 255 | 260 | 266 | 274 | 281 | 288 | 296 | 304 | 311 | 316 | 322 | 330 | 337 | 344 | 349 | 354 | 361 | 366 | 372 | 377 | 384 | 392 | 398 | 406 | 412 | 419 | 426 | 432 | 438 | 443 | 450 | 457 | 463 | 469 | 475 | 483 | 491 | 499 | 507 | 513 | 518 | 525 | 532 | 540 | 545 | 551 | 559 | 567 | 575 | 580 | 587 | 594 | 599 | 606 | 612 | 619 | 624 | 630 | 637 | 643 | 648 | 655 | 662 | 668 | 675 | 683
324 | 1.026 | 7 | 20 | 44 | 75 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 1 | 4 | 7 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 7 | 12 | 18 | 24 | 30 | 38 | 46 | 53 | 59 | 67 | 73 | 79 | 85 | 93 | 98 | 104 | 109 | 115 | 123 | 129 | 136 | 142 | 150 | 158 | 166 | 173 | 181 | 187 | 193 | 201 | 207 | 214 | 220 | 228 | 233 | 241 | 249 | 256 | 261 | 266 | 273 | 278 | 284 | 289 | 296 | 301 | 306 | 313 | 321 | 328 | 334 | 341 | 349 | 354 | 362 | 370 | 377 | 383 | 388 | 394 | 400 | 405 | 413 | 418 | 423 | 431 | 437 | 444 | 451 | 458 | 464 | 469 | 477 | 483 | 489 | 495 | 502 | 509 | 517 | 525 | 530 | 537 | 542 | 547 | 552 | 557 | 563 | 571 | 577 | 585 | 592 | 600 | 605 | 611 | 616 | 621 | 627 | 632 | 637 | 643 | 650 | 655 | 661 | 666
325 | 1.5891 | 16 | 32 | 60 | 103 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 3 | 5 | 10 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 5 | 12 | 18 | 25 | 32 | 37 | 42 | 47 | 55 | 61 | 68 | 75 | 80 | 88 | 94 | 100 | 107 | 112 | 117 | 123 | 128 | 133 | 140 | 147 | 152 | 157 | 165 | 170 | 178 | 184 | 191 | 198 | 206 | 211 | 217 | 222 | 227 | 234 | 239 | 247 | 252 | 259 | 266 | 271 | 279 | 284 | 291 | 297 | 305 | 312 | 317 | 324 | 332 | 337 | 342 | 350 | 355 | 361 | 369 | 376 | 384 | 391 | 397 | 403 | 411 | 417 | 424 | 432 | 439 | 445 | 450 | 458 | 465 | 471 | 477 | 482 | 489 | 496 | 504 | 510 | 517 | 523 | 528 | 536 | 543 | 549 | 555 | 563 | 568 | 574 | 581 | 588 | 593 | 598 | 604 | 611 | 617 | 624 | 629 | 637 | 643 | 648 | 656 | 663
326 | 1.6503 | 10 | 35 | 65 | 102 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 2 | 7 | 11 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 10 | 16 | 22 | 29 | 34 | 40 | 47 | 55 | 61 | 69 | 76 | 81 | 87 | 95 | 103 | 110 | 116 | 124 | 129 | 134 | 142 | 150 | 157 | 165 | 173 | 181 | 186 | 192 | 199 | 205 | 212 | 219 | 224 | 230 | 238 | 245 | 251 | 258 | 264 | 269 | 277 | 283 | 289 | 294 | 301 | 309 | 315 | 323 | 328 | 335 | 343 | 349 | 355 | 363 | 369 | 374 | 381 | 386 | 393 | 400 | 408 | 416 | 421 | 426 | 432 | 438 | 444 | 452 | 460 | 467 | 475 | 481 | 489 | 496 | 503 | 508 | 515 | 522 | 529 | 535 | 543 | 549 | 556 | 563 | 568 | 573 | 579 | 586 | 591 | 599 | 607 | 615 | 620 | 626 | 633 | 640 | 648 | 654 | 660 | 665 | 673 | 680 | 685
327 | 1.7739 | 18 | 40 | 72 | 117 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 187 | 3 | 6 | 12 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 7 | 13 | 20 | 27 | 34 | 40 | 45 | 50 | 56 | 63 | 68 | 76 | 82 | 88 | 95 | 103 | 108 | 115 | 120 | 127 | 132 | 140 | 147 | 155 | 161 | 167 | 174 | 182 | 187 | 194 | 202 | 210 | 218 | 223 | 230 | 237 | 243 | 248 | 256 | 263 | 270 | 275 | 283 | 290 | 297 | 303 | 310 | 318 | 325 | 333 | 341 | 348 | 353 | 361 | 366 | 372 | 378 | 386 | 392 | 398 | 404 | 410 | 418 | 425 | 433 | 439 | 445 | 451 | 457 | 462 | 468 | 476 | 484 | 490 | 497 | 505 | 511 | 518 | 526 | 532 | 538 | 543 | 549 | 554 | 561 | 567 | 574 | 582 | 588 | 593 | 600 | 605 | 611 | 619 | 624 | 630 | 636 | 643 | 650 | 655 | 660 | 667 | 672 | 680
328 | 1.817 | 11 | 26 | 68 | 121 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 2 | 4 | 11 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 15 | 22 | 29 | 36 | 42 | 49 | 55 | 61 | 66 | 73 | 81 | 89 | 94 | 101 | 106 | 111 | 116 | 124 | 129 | 134 | 141 | 148 | 153 | 159 | 164 | 170 | 177 | 184 | 189 | 194 | 201 | 209 | 214 | 222 | 229 | 235 | 240 | 248 | 253 | 258 | 265 | 270 | 276 | 282 | 290 | 297 | 305 | 313 | 321 | 326 | 334 | 340 | 345 | 350 | 358 | 365 | 372 | 377 | 385 | 391 | 399 | 406 | 412 | 418 | 426 | 433 | 441 | 446 | 452 | 458 | 466 | 473 | 478 | 483 | 488 | 495 | 501 | 507 | 512 | 519 | 527 | 534 | 540 | 548 | 553 | 560 | 565 | 571 | 579 | 584 | 589 | 597 | 602 | 609 | 617 | 624 | 632 | 639 | 646 | 653 | 660 | 665 | 673
329 | 1.8153 | 10 | 34 | 76 | 124 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 5 | 11 | 19 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 15 | 23 | 30 | 37 | 43 | 50 | 58 | 66 | 74 | 81 | 87 | 94 | 100 | 106 | 111 | 116 | 121 | 128 | 135 | 142 | 150 | 157 | 164 | 171 | 177 | 183 | 189 | 195 | 201 | 206 | 213 | 221 | 227 | 232 | 240 | 246 | 253 | 259 | 264 | 270 | 278 | 286 | 291 | 298 | 304 | 312 | 318 | 323 | 329 | 337 | 342 | 349 | 357 | 364 | 369 | 374 | 379 | 385 | 390 | 396 | 403 | 409 | 417 | 425 | 433 | 440 | 447 | 452 | 458 | 466 | 471 | 476 | 482 | 488 | 494 | 502 | 509 | 517 | 522 | 529 | 536 | 543 | 550 | 555 | 561 | 566 | 574 | 580 | 586 | 591 | 597 | 604 | 611 | 619 | 625 | 633 | 638 | 644 | 649 | 656 | 663 | 670 | 678
330 | 1.2714 | 12 | 23 | 55 | 92 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 2 | 4 | 9 | 15 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 12 | 17 | 25 | 30 | 37 | 44 | 50 | 56 | 61 | 69 | 77 | 85 | 91 | 97 | 103 | 109 | 115 | 123 | 129 | 135 | 141 | 147 | 155 | 162 | 170 | 178 | 184 | 190 | 195 | 201 | 209 | 216 | 221 | 229 | 237 | 244 | 249 | 256 | 262 | 270 | 275 | 283 | 291 | 299 | 307 | 314 | 319 | 324 | 330 | 335 | 343 | 351 | 358 | 364 | 370 | 375 | 381 | 386 | 394 | 402 | 408 | 416 | 421 | 429 | 436 | 442 | 447 | 452 | 458 | 463 | 470 | 476 | 482 | 489 | 495 | 503 | 510 | 518 | 524 | 529 | 536 | 541 | 549 | 556 | 562 | 569 | 574 | 580 | 588 | 595 | 600 | 608 | 614 | 619 | 624 | 631 | 637 | 643 | 648 | 656 | 663 | 668 | 673
331 | 1.8657 | 15 | 30 | 58 | 100 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 3 | 5 | 10 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 13 | 19 | 24 | 31 | 37 | 44 | 49 | 55 | 63 | 68 | 73 | 79 | 87 | 93 | 98 | 104 | 112 | 120 | 127 | 132 | 139 | 146 | 152 | 157 | 162 | 168 | 173 | 179 | 185 | 192 | 200 | 207 | 214 | 220 | 225 | 231 | 238 | 245 | 250 | 257 | 263 | 271 | 278 | 285 | 290 | 298 | 306 | 313 | 319 | 327 | 334 | 339 | 344 | 350 | 355 | 363 | 371 | 376 | 383 | 391 | 397 | 403 | 411 | 419 | 425 | 433 | 438 | 444 | 449 | 456 | 462 | 467 | 473 | 478 | 486 | 493 | 500 | 505 | 512 | 519 | 526 | 534 | 541 | 549 | 555 | 561 | 567 | 575 | 581 | 588 | 593 | 599 | 605 | 612 | 617 | 623 | 630 | 638 | 644 | 652 | 657 | 663 | 668
332 | 1.8197 | 19 | 43 | 89 | 126 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 4 | 8 | 15 | 21 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 5 | 10 | 16 | 23 | 28 | 36 | 42 | 50 | 57 | 64 | 69 | 76 | 82 | 88 | 95 | 100 | 106 | 112 | 118 | 123 | 130 | 135 | 141 | 149 | 157 | 163 | 168 | 174 | 181 | 186 | 194 | 200 | 207 | 212 | 220 | 225 | 232 | 237 | 243 | 249 | 256 | 262 | 269 | 274 | 282 | 287 | 294 | 301 | 307 | 312 | 318 | 326 | 332 | 338 | 346 | 353 | 361 | 369 | 377 | 382 | 389 | 397 | 402 | 410 | 418 | 425 | 431 | 437 | 444 | 452 | 458 | 463 | 468 | 473 | 479 | 486 | 493 | 498 | 504 | 509 | 517 | 523 | 529 | 536 | 544 | 551 | 559 | 567 | 573 | 578 | 585 | 592 | 600 | 608 | 613 | 620 | 628 | 636 | 644 | 651 | 657 | 665 | 673 | 681
333 | 1.3182 | 8 | 23 | 45 | 75 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 4 | 8 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 12 | 18 | 25 | 33 | 38 | 43 | 51 | 59 | 65 | 71 | 77 | 84 | 89 | 94 | 99 | 106 | 112 | 120 | 125 | 130 | 135 | 143 | 151 | 156 | 164 | 169 | 174 | 181 | 186 | 191 | 197 | 203 | 210 | 215 | 223 | 231 | 239 | 246 | 254 | 259 | 267 | 273 | 279 | 285 | 291 | 298 | 306 | 314 | 321 | 327 | 335 | 341 | 348 | 354 | 360 | 367 | 373 | 380 | 388 | 393 | 398 | 405 | 411 | 417 | 425 | 433 | 440 | 447 | 452 | 458 | 466 | 473 | 478 | 486 | 493 | 499 | 506 | 511 | 516 | 524 | 531 | 536 | 541 | 546 | 554 | 561 | 566 | 573 | 578 | 584 | 589 | 594 | 602 | 607 | 612 | 620 | 628 | 633 | 638 | 644 | 652 | 660 | 668
334 | 1.5691 | 10 | 34 | 71 | 104 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 2 | 6 | 11 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 6 | 12 | 19 | 27 | 33 | 39 | 47 | 52 | 58 | 65 | 71 | 76 | 82 | 89 | 97 | 104 | 111 | 116 | 121 | 129 | 137 | 142 | 150 | 156 | 164 | 171 | 178 | 184 | 190 | 195 | 202 | 207 | 213 | 220 | 227 | 232 | 237 | 245 | 250 | 257 | 263 | 270 | 278 | 284 | 290 | 297 | 302 | 309 | 316 | 323 | 330 | 337 | 345 | 352 | 360 | 365 | 371 | 379 | 387 | 392 | 400 | 407 | 412 | 419 | 427 | 432 | 439 | 446 | 453 | 461 | 469 | 476 | 481 | 487 | 494 | 501 | 508 | 513 | 518 | 524 | 532 | 538 | 546 | 554 | 559 | 566 | 573 | 578 | 586 | 594 | 602 | 610 | 615 | 620 | 626 | 631 | 636 | 642 | 648 | 653 | 658 | 665 | 673 | 678
335 | 1.6485 | 12 | 36 | 63 | 106 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 2 | 6 | 9 | 16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 15 | 23 | 28 | 35 | 42 | 50 | 56 | 64 | 69 | 75 | 81 | 89 | 97 | 104 | 112 | 120 | 127 | 132 | 139 | 146 | 151 | 159 | 166 | 174 | 181 | 189 | 196 | 204 | 210 | 218 | 226 | 232 | 238 | 246 | 252 | 258 | 266 | 272 | 280 | 287 | 292 | 300 | 308 | 315 | 320 | 328 | 333 | 338 | 344 | 351 | 356 | 364 | 370 | 377 | 383 | 391 | 398 | 405 | 410 | 416 | 424 | 432 | 437 | 443 | 451 | 457 | 464 | 472 | 477 | 482 | 487 | 492 | 497 | 502 | 507 | 513 | 521 | 528 | 535 | 542 | 549 | 555 | 563 | 568 | 575 | 583 | 588 | 596 | 601 | 606 | 613 | 619 | 625 | 633 | 638 | 643 | 650 | 655 | 660 | 665 | 671 | 676 | 683
336 | 1.8067 | 19 | 43 | 83 | 134 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 3 | 7 | 12 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 13 | 19 | 26 | 34 | 42 | 49 | 56 | 64 | 72 | 78 | 84 | 92 | 97 | 105 | 111 | 119 | 126 | 134 | 140 | 146 | 152 | 160 | 165 | 173 | 178 | 185 | 192 | 200 | 206 | 211 | 218 | 226 | 234 | 239 | 245 | 252 | 258 | 266 | 273 | 278 | 285 | 290 | 296 | 302 | 310 | 317 | 325 | 333 | 341 | 346 | 351 | 357 | 365 | 370 | 378 | 386 | 394 | 399 | 406 | 411 | 416 | 422 | 427 | 432 | 439 | 446 | 454 | 462 | 470 | 478 | 486 | 491 | 499 | 505 | 510 | 515 | 520 | 527 | 535 | 541 | 546 | 554 | 561 | 566 | 571 | 578 | 583 | 590 | 597 | 603 | 608 | 615 | 623 | 628 | 633 | 640 | 648 | 654 | 660 | 666 | 674 | 679 | 687
337 | 1.7126 | 18 | 37 | 79 | 121 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 3 | 6 | 12 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 14 | 21 | 28 | 35 | 43 | 49 | 57 | 62 | 69 | 76 | 84 | 92 | 98 | 106 | 113 | 118 | 123 | 130 | 138 | 146 | 153 | 160 | 168 | 176 | 182 | 189 | 195 | 203 | 209 | 217 | 223 | 228 | 236 | 242 | 247 | 252 | 259 | 265 | 270 | 277 | 282 | 289 | 296 | 301 | 306 | 312 | 320 | 328 | 335 | 343 | 350 | 356 | 361 | 369 | 376 | 383 | 389 | 397 | 402 | 409 | 414 | 421 | 427 | 433 | 438 | 446 | 451 | 456 | 461 | 469 | 476 | 483 | 491 | 496 | 504 | 510 | 518 | 526 | 534 | 541 | 548 | 555 | 563 | 570 | 575 | 581 | 588 | 596 | 602 | 609 | 616 | 623 | 629 | 635 | 643 | 648 | 653 | 661 | 668 | 675 | 681 | 686 | 693
338 | 1.1113 | 11 | 24 | 48 | 79 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 4 | 9 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 13 | 19 | 24 | 30 | 35 | 41 | 47 | 52 | 60 | 65 | 70 | 76 | 82 | 87 | 92 | 97 | 103 | 109 | 115 | 123 | 129 | 134 | 140 | 146 | 154 | 162 | 168 | 173 | 179 | 186 | 192 | 198 | 206 | 214 | 219 | 224 | 230 | 238 | 243 | 251 | 258 | 266 | 271 | 278 | 285 | 292 | 300 | 306 | 313 | 319 | 327 | 335 | 340 | 348 | 354 | 360 | 368 | 374 | 381 | 388 | 395 | 400 | 407 | 415 | 422 | 428 | 433 | 440 | 446 | 451 | 458 | 465 | 472 | 479 | 487 | 494 | 501 | 509 | 516 | 524 | 529 | 537 | 545 | 551 | 557 | 564 | 571 | 578 | 586 | 593 | 600 | 606 | 614 | 621 | 629 | 634 | 639 | 646 | 653 | 660 | 665 | 672 | 679
339 | 1.7557 | 11 | 26 | 56 | 92 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 2 | 5 | 10 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 11 | 18 | 23 | 28 | 36 | 41 | 46 | 54 | 61 | 68 | 73 | 80 | 85 | 92 | 98 | 106 | 112 | 119 | 127 | 135 | 142 | 150 | 156 | 162 | 169 | 174 | 182 | 189 | 195 | 202 | 207 | 215 | 220 | 228 | 235 | 242 | 248 | 255 | 262 | 268 | 274 | 282 | 288 | 294 | 301 | 309 | 317 | 323 | 330 | 337 | 343 | 348 | 356 | 364 | 369 | 377 | 382 | 387 | 392 | 398 | 404 | 409 | 414 | 420 | 427 | 433 | 439 | 444 | 450 | 456 | 461 | 469 | 474 | 481 | 486 | 494 | 501 | 509 | 517 | 522 | 528 | 533 | 541 | 549 | 556 | 562 | 567 | 574 | 581 | 587 | 595 | 603 | 609 | 617 | 625 | 631 | 637 | 642 | 650 | 655 | 662 | 669 | 676
340 | 1.047 | 10 | 22 | 46 | 68 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 2 | 5 | 8 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 10 | 15 | 21 | 28 | 36 | 43 | 49 | 57 | 65 | 72 | 80 | 86 | 92 | 98 | 103 | 108 | 115 | 123 | 131 | 137 | 145 | 153 | 160 | 167 | 172 | 178 | 186 | 193 | 199 | 206 | 212 | 217 | 224 | 229 | 236 | 243 | 248 | 253 | 260 | 266 | 271 | 278 | 285 | 292 | 300 | 305 | 312 | 318 | 324 | 329 | 334 | 342 | 348 | 354 | 362 | 370 | 375 | 381 | 388 | 394 | 399 | 405 | 412 | 419 | 426 | 433 | 441 | 447 | 453 | 461 | 469 | 474 | 482 | 490 | 498 | 504 | 509 | 515 | 523 | 528 | 535 | 543 | 550 | 557 | 562 | 570 | 577 | 583 | 588 | 593 | 601 | 606 | 611 | 617 | 622 | 630 | 636 | 641 | 646 | 654 | 660 | 668 | 676
341 | 1.9207 | 12 | 30 | 75 | 127 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 2 | 5 | 12 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 8 | 14 | 20 | 25 | 31 | 39 | 44 | 51 | 57 | 64 | 71 | 76 | 84 | 91 | 98 | 103 | 108 | 113 | 121 | 129 | 135 | 140 | 148 | 155 | 161 | 168 | 173 | 178 | 186 | 194 | 201 | 209 | 216 | 221 | 226 | 232 | 238 | 245 | 252 | 258 | 263 | 269 | 274 | 280 | 288 | 296 | 301 | 306 | 311 | 319 | 327 | 335 | 340 | 346 | 351 | 359 | 367 | 372 | 378 | 385 | 390 | 396 | 403 | 410 | 417 | 425 | 430 | 436 | 442 | 448 | 455 | 461 | 469 | 474 | 482 | 490 | 497 | 502 | 509 | 517 | 522 | 530 | 535 | 540 | 547 | 553 | 559 | 567 | 574 | 580 | 588 | 593 | 601 | 606 | 613 | 618 | 624 | 631 | 638 | 646 | 651 | 659 | 664 | 670
342 | 1.3683 | 7 | 28 | 49 | 84 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 5 | 9 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 13 | 18 | 24 | 29 | 34 | 41 | 48 | 56 | 63 | 68 | 75 | 82 | 89 | 95 | 102 | 107 | 115 | 122 | 127 | 133 | 139 | 144 | 149 | 157 | 162 | 170 | 177 | 185 | 190 | 195 | 202 | 208 | 216 | 224 | 229 | 237 | 245 | 253 | 260 | 268 | 274 | 281 | 289 | 296 | 303 | 311 | 317 | 322 | 330 | 337 | 342 | 348 | 356 | 362 | 369 | 375 | 382 | 390 | 395 | 401 | 409 | 414 | 422 | 427 | 433 | 439 | 444 | 452 | 457 | 463 | 471 | 478 | 485 | 493 | 499 | 506 | 511 | 518 | 523 | 531 | 536 | 541 | 548 | 554 | 560 | 566 | 574 | 579 | 586 | 591 | 597 | 604 | 612 | 617 | 622 | 628 | 633 | 639 | 644 | 649 | 657 | 663 | 669
343 | 1.8289 | 17 | 41 | 84 | 138 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 3 | 7 | 13 | 21 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 8 | 13 | 20 | 27 | 34 | 39 | 47 | 55 | 63 | 71 | 78 | 83 | 91 | 97 | 104 | 110 | 116 | 121 | 127 | 134 | 139 | 145 | 151 | 157 | 163 | 168 | 176 | 183 | 190 | 196 | 202 | 207 | 212 | 220 | 225 | 230 | 236 | 244 | 252 | 258 | 263 | 270 | 275 | 281 | 287 | 295 | 302 | 310 | 318 | 326 | 331 | 339 | 345 | 353 | 360 | 367 | 375 | 380 | 388 | 396 | 401 | 409 | 416 | 421 | 429 | 434 | 440 | 447 | 452 | 459 | 465 | 471 | 477 | 484 | 490 | 497 | 503 | 509 | 517 | 522 | 528 | 536 | 542 | 547 | 555 | 563 | 568 | 573 | 578 | 583 | 591 | 597 | 605 | 611 | 618 | 626 | 633 | 639 | 644 | 651 | 659 | 665 | 671 | 676
344 | 1.7663 | 13 | 36 | 70 | 118 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 2 | 6 | 12 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 15 | 22 | 28 | 33 | 38 | 44 | 50 | 57 | 63 | 69 | 77 | 85 | 90 | 97 | 102 | 107 | 114 | 120 | 125 | 132 | 137 | 143 | 148 | 155 | 161 | 168 | 175 | 183 | 188 | 193 | 201 | 206 | 212 | 217 | 223 | 230 | 237 | 244 | 250 | 256 | 263 | 269 | 275 | 283 | 290 | 298 | 306 | 311 | 317 | 322 | 329 | 334 | 340 | 347 | 354 | 361 | 368 | 374 | 382 | 387 | 392 | 397 | 405 | 410 | 416 | 421 | 427 | 433 | 441 | 449 | 454 | 460 | 466 | 471 | 477 | 484 | 492 | 499 | 507 | 513 | 519 | 527 | 535 | 542 | 549 | 557 | 563 | 569 | 576 | 582 | 590 | 595 | 602 | 609 | 617 | 624 | 632 | 637 | 642 | 650 | 658 | 666 | 672
345 | 1.5266 | 14 | 37 | 73 | 106 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 3 | 6 | 13 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 13 | 19 | 26 | 32 | 37 | 42 | 47 | 53 | 60 | 67 | 72 | 79 | 86 | 93 | 99 | 104 | 111 | 116 | 124 | 129 | 135 | 143 | 151 | 159 | 166 | 174 | 180 | 186 | 191 | 196 | 201 | 209 | 214 | 222 | 228 | 234 | 240 | 246 | 253 | 259 | 264 | 271 | 278 | 286 | 294 | 301 | 308 | 315 | 321 | 327 | 334 | 342 | 349 | 354 | 362 | 367 | 372 | 377 | 385 | 391 | 397 | 403 | 410 | 418 | 423 | 428 | 436 | 442 | 449 | 455 | 463 | 468 | 476 | 483 | 488 | 495 | 501 | 507 | 514 | 520 | 528 | 535 | 542 | 548 | 556 | 562 | 567 | 573 | 581 | 586 | 592 | 597 | 602 | 608 | 615 | 622 | 629 | 637 | 642 | 647 | 654 | 661 | 669
346 | 1.1519 | 9 | 24 | 46 | 73 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 2 | 4 | 8 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 13 | 19 | 25 | 30 | 36 | 43 | 49 | 57 | 62 | 69 | 75 | 81 | 86 | 93 | 100 | 107 | 113 | 119 | 126 | 132 | 137 | 145 | 153 | 158 | 163 | 169 | 176 | 181 | 187 | 193 | 201 | 206 | 214 | 220 | 226 | 234 | 241 | 247 | 254 | 261 | 269 | 275 | 282 | 289 | 294 | 302 | 310 | 317 | 322 | 330 | 335 | 341 | 347 | 353 | 359 | 364 | 370 | 376 | 384 | 390 | 395 | 400 | 407 | 413 | 419 | 425 | 433 | 441 | 449 | 454 | 460 | 466 | 474 | 482 | 490 | 496 | 503 | 508 | 513 | 520 | 525 | 530 | 536 | 541 | 546 | 552 | 558 | 564 | 569 | 577 | 583 | 588 | 593 | 599 | 606 | 613 | 619 | 624 | 631 | 637 | 644 | 651 | 656
347 | 1.8705 | 14 | 43 | 73 | 128 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 2 | 7 | 11 | 20 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 8 | 15 | 22 | 27 | 35 | 41 | 49 | 55 | 63 | 68 | 73 | 80 | 85 | 93 | 99 | 104 | 110 | 116 | 122 | 129 | 134 | 140 | 148 | 154 | 162 | 168 | 174 | 181 | 189 | 194 | 200 | 208 | 214 | 219 | 227 | 234 | 240 | 248 | 256 | 264 | 272 | 279 | 287 | 294 | 302 | 309 | 316 | 324 | 331 | 339 | 346 | 354 | 362 | 368 | 375 | 382 | 388 | 394 | 402 | 408 | 414 | 422 | 429 | 437 | 444 | 452 | 458 | 466 | 472 | 478 | 486 | 491 | 498 | 505 | 513 | 518 | 526 | 534 | 542 | 549 | 557 | 562 | 569 | 576 | 584 | 589 | 595 | 601 | 609 | 617 | 625 | 632 | 639 | 646 | 654 | 660 | 667 | 675 | 682 | 688 | 694 | 700 | 707 | 713
348 | 1.1962 | 10 | 27 | 51 | 75 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 2 | 5 | 9 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8 | 13 | 18 | 23 | 30 | 37 | 43 | 48 | 53 | 59 | 67 | 73 | 78 | 84 | 92 | 98 | 106 | 112 | 119 | 125 | 133 | 139 | 147 | 154 | 159 | 167 | 172 | 179 | 187 | 193 | 200 | 206 | 214 | 219 | 225 | 231 | 237 | 244 | 250 | 257 | 262 | 267 | 272 | 279 | 287 | 295 | 302 | 307 | 313 | 321 | 329 | 335 | 343 | 348 | 355 | 361 | 366 | 371 | 378 | 385 | 391 | 398 | 404 | 411 | 417 | 422 | 429 | 436 | 444 | 452 | 460 | 467 | 472 | 478 | 486 | 492 | 497 | 503 | 509 | 516 | 521 | 528 | 536 | 542 | 550 | 556 | 564 | 571 | 576 | 583 | 590 | 597 | 602 | 609 | 617 | 625 | 632 | 639 | 645 | 652 | 659 | 666 | 674 | 681
349 | 1.7074 | 11 | 32 | 60 | 100 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 2 | 5 | 11 | 16 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 13 | 18 | 24 | 32 | 38 | 43 | 48 | 53 | 59 | 65 | 70 | 77 | 85 | 92 | 100 | 106 | 113 | 118 | 124 | 129 | 136 | 143 | 151 | 159 | 166 | 171 | 178 | 183 | 191 | 196 | 203 | 210 | 217 | 222 | 229 | 236 | 244 | 251 | 256 | 262 | 267 | 275 | 281 | 287 | 294 | 299 | 307 | 314 | 321 | 329 | 335 | 340 | 345 | 353 | 358 | 364 | 372 | 380 | 387 | 395 | 401 | 408 | 416 | 424 | 432 | 437 | 445 | 450 | 458 | 464 | 470 | 478 | 484 | 489 | 495 | 501 | 509 | 515 | 522 | 529 | 535 | 541 | 547 | 555 | 562 | 568 | 575 | 583 | 591 | 596 | 601 | 606 | 613 | 621 | 629 | 635 | 643 | 649 | 657 | 662 | 670 | 675 | 683
350 | 1.7188 | 16 | 32 | 63 | 103 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 3 | 6 | 10 | 16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 13 | 18 | 25 | 31 | 39 | 47 | 54 | 60 | 65 | 70 | 78 | 85 | 92 | 97 | 105 | 112 | 118 | 124 | 131 | 136 | 143 | 149 | 154 | 161 | 167 | 173 | 180 | 188 | 195 | 202 | 207 | 215 | 220 | 228 | 236 | 244 | 249 | 257 | 265 | 271 | 276 | 284 | 292 | 297 | 302 | 308 | 313 | 319 | 326 | 333 | 338 | 346 | 354 | 362 | 367 | 373 | 380 | 386 | 392 | 397 | 404 | 409 | 415 | 420 | 426 | 432 | 438 | 443 | 450 | 455 | 463 | 468 | 474 | 479 | 485 | 493 | 501 | 506 | 514 | 519 | 526 | 532 | 537 | 543 | 549 | 556 | 564 | 571 | 577 | 585 | 590 | 596 | 604 | 610 | 618 | 625 | 631 | 638 | 646 | 651 | 658 | 665 | 671
351 | 1.3615 | 9 | 26 | 51 | 81 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 4 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 15 | 22 | 27 | 33 | 38 | 45 | 51 | 57 | 64 | 70 | 77 | 83 | 88 | 93 | 99 | 104 | 112 | 120 | 126 | 133 | 138 | 146 | 153 | 159 | 164 | 169 | 175 | 180 | 188 | 196 | 203 | 210 | 216 | 222 | 228 | 235 | 240 | 246 | 251 | 256 | 261 | 266 | 274 | 280 | 287 | 293 | 298 | 304 | 309 | 314 | 319 | 325 | 331 | 339 | 347 | 355 | 360 | 368 | 375 | 383 | 388 | 393 | 398 | 405 | 410 | 418 | 425 | 433 | 439 | 447 | 455 | 460 | 468 | 473 | 480 | 488 | 495 | 501 | 509 | 515 | 520 | 525 | 530 | 537 | 544 | 552 | 560 | 568 | 574 | 581 | 586 | 593 | 598 | 605 | 613 | 619 | 626 | 633 | 640 | 647 | 655 | 661 | 667
352 | 1.9736 | 14 | 44 | 88 | 140 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 3 | 7 | 14 | 23 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 5 | 10 | 18 | 25 | 30 | 37 | 44 | 52 | 60 | 68 | 73 | 78 | 83 | 88 | 94 | 99 | 107 | 113 | 118 | 123 | 130 | 135 | 141 | 147 | 152 | 159 | 164 | 169 | 174 | 181 | 186 | 192 | 198 | 206 | 213 | 218 | 226 | 234 | 241 | 246 | 252 | 258 | 265 | 273 | 280 | 287 | 294 | 301 | 307 | 312 | 319 | 327 | 335 | 341 | 349 | 354 | 360 | 368 | 376 | 381 | 386 | 394 | 399 | 406 | 414 | 421 | 428 | 435 | 443 | 451 | 459 | 466 | 473 | 478 | 483 | 489 | 495 | 501 | 508 | 514 | 520 | 527 | 532 | 537 | 544 | 549 | 554 | 559 | 565 | 570 | 577 | 585 | 592 | 600 | 608 | 613 | 620 | 628 | 636 | 642 | 650 | 658 | 666 | 672
353 | 1.7646 | 11 | 33 | 60 | 99 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 2 | 5 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 12 | 19 | 27 | 35 | 43 | 51 | 56 | 64 | 72 | 79 | 86 | 91 | 98 | 106 | 111 | 119 | 126 | 131 | 137 | 144 | 152 | 157 | 165 | 173 | 178 | 184 | 189 | 196 | 201 | 207 | 215 | 220 | 228 | 235 | 243 | 248 | 256 | 264 | 272 | 279 | 287 | 292 | 297 | 304 | 311 | 319 | 326 | 331 | 336 | 343 | 349 | 355 | 363 | 368 | 373 | 379 | 385 | 392 | 399 | 407 | 415 | 421 | 427 | 434 | 441 | 446 | 452 | 460 | 467 | 475 | 482 | 490 | 497 | 505 | 510 | 518 | 524 | 529 | 534 | 539 | 546 | 553 | 561 | 566 | 574 | 580 | 586 | 594 | 602 | 607 | 613 | 620 | 625 | 630 | 637 | 643 | 650 | 658 | 663 | 670 | 677 | 683 | 688
354 | 1.5231 | 14 | 31 | 57 | 94 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 3 | 5 | 9 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 13 | 20 | 28 | 35 | 40 | 45 | 53 | 59 | 66 | 74 | 82 | 87 | 94 | 99 | 107 | 112 | 119 | 126 | 131 | 137 | 143 | 150 | 155 | 163 | 169 | 174 | 180 | 185 | 191 | 198 | 205 | 210 | 218 | 225 | 233 | 241 | 249 | 256 | 263 | 268 | 276 | 282 | 289 | 295 | 302 | 310 | 318 | 323 | 331 | 336 | 343 | 348 | 355 | 360 | 368 | 374 | 382 | 388 | 395 | 402 | 408 | 416 | 422 | 428 | 434 | 439 | 445 | 453 | 461 | 469 | 477 | 483 | 488 | 494 | 501 | 507 | 513 | 518 | 525 | 533 | 538 | 546 | 552 | 558 | 564 | 570 | 577 | 585 | 593 | 600 | 605 | 613 | 621 | 627 | 634 | 642 | 649 | 655 | 662 | 670 | 675 | 683 | 689
355 | 1.1002 | 12 | 26 | 47 | 79 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 2 | 4 | 8 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 15 | 21 | 27 | 32 | 39 | 45 | 53 | 58 | 65 | 71 | 78 | 85 | 91 | 98 | 105 | 111 | 118 | 124 | 129 | 137 | 142 | 149 | 155 | 163 | 168 | 175 | 183 | 189 | 196 | 204 | 210 | 217 | 225 | 231 | 236 | 243 | 249 | 257 | 265 | 272 | 277 | 282 | 290 | 298 | 305 | 310 | 316 | 324 | 331 | 338 | 343 | 348 | 353 | 359 | 366 | 374 | 381 | 389 | 396 | 402 | 407 | 415 | 422 | 427 | 433 | 438 | 446 | 451 | 457 | 464 | 472 | 480 | 486 | 491 | 497 | 503 | 509 | 517 | 522 | 528 | 534 | 539 | 545 | 550 | 555 | 563 | 568 | 574 | 580 | 585 | 592 | 598 | 605 | 613 | 619 | 624 | 632 | 637 | 642 | 649 | 656 | 662 | 667
356 | 1.9406 | 16 | 42 | 75 | 126 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 185 | 3 | 7 | 13 | 21 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 5 | 10 | 16 | 24 | 30 | 38 | 44 | 51 | 58 | 63 | 69 | 74 | 80 | 86 | 91 | 98 | 104 | 109 | 114 | 122 | 129 | 134 | 140 | 148 | 156 | 163 | 168 | 174 | 182 | 190 | 196 | 201 | 209 | 214 | 221 | 229 | 237 | 243 | 250 | 258 | 264 | 270 | 278 | 286 | 293 | 300 | 305 | 310 | 316 | 323 | 331 | 338 | 343 | 348 | 355 | 362 | 367 | 374 | 382 | 390 | 397 | 405 | 413 | 421 | 429 | 436 | 442 | 449 | 455 | 461 | 466 | 473 | 479 | 487 | 492 | 499 | 504 | 511 | 516 | 523 | 529 | 537 | 545 | 553 | 560 | 565 | 573 | 581 | 586 | 592 | 598 | 603 | 611 | 619 | 624 | 630 | 638 | 644 | 651 | 659 | 664 | 670 | 676 | 683
357 | 1.3466 | 14 | 27 | 52 | 86 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 4 | 7 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 16 | 24 | 31 | 39 | 47 | 53 | 60 | 67 | 74 | 79 | 85 | 93 | 98 | 103 | 108 | 114 | 121 | 126 | 132 | 138 | 146 | 151 | 156 | 163 | 169 | 177 | 183 | 189 | 194 | 201 | 206 | 212 | 218 | 224 | 231 | 239 | 245 | 253 | 259 | 265 | 273 | 278 | 284 | 289 | 296 | 301 | 308 | 314 | 319 | 327 | 333 | 338 | 343 | 349 | 356 | 361 | 366 | 372 | 379 | 384 | 392 | 398 | 405 | 413 | 418 | 424 | 431 | 437 | 443 | 448 | 454 | 461 | 467 | 474 | 480 | 488 | 493 | 500 | 507 | 514 | 519 | 524 | 530 | 537 | 542 | 548 | 553 | 558 | 565 | 571 | 577 | 582 | 587 | 593 | 598 | 606 | 612 | 618 | 625 | 631 | 638 | 646 | 653
358 | 1.2954 | 8 | 25 | 53 | 90 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 4 | 9 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 13 | 19 | 27 | 32 | 38 | 43 | 49 | 54 | 62 | 67 | 74 | 82 | 90 | 95 | 102 | 109 | 116 | 123 | 130 | 135 | 140 | 145 | 152 | 157 | 165 | 171 | 176 | 184 | 190 | 197 | 202 | 207 | 213 | 219 | 224 | 231 | 236 | 243 | 250 | 258 | 263 | 268 | 276 | 282 | 288 | 294 | 302 | 308 | 314 | 320 | 326 | 332 | 338 | 344 | 349 | 354 | 362 | 369 | 377 | 383 | 391 | 397 | 405 | 413 | 420 | 428 | 434 | 441 | 449 | 455 | 463 | 470 | 476 | 484 | 490 | 497 | 504 | 512 | 519 | 524 | 530 | 535 | 543 | 551 | 556 | 563 | 570 | 575 | 580 | 588 | 594 | 599 | 604 | 612 | 619 | 624 | 632 | 640 | 646 | 651 | 658 | 663 | 671
359 | 1.4225 | 12 | 25 | 60 | 97 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 2 | 4 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 14 | 22 | 28 | 35 | 43 | 48 | 53 | 60 | 66 | 73 | 81 | 86 | 94 | 101 | 106 | 114 | 122 | 129 | 136 | 143 | 148 | 156 | 162 | 167 | 172 | 178 | 184 | 192 | 200 | 207 | 212 | 218 | 224 | 232 | 238 | 246 | 251 | 257 | 263 | 271 | 278 | 286 | 294 | 299 | 307 | 315 | 323 | 329 | 334 | 340 | 346 | 351 | 356 | 361 | 366 | 373 | 378 | 384 | 389 | 395 | 400 | 406 | 411 | 418 | 426 | 434 | 440 | 445 | 453 | 461 | 467 | 475 | 481 | 488 | 494 | 500 | 507 | 514 | 521 | 529 | 534 | 539 | 544 | 550 | 556 | 561 | 569 | 576 | 582 | 590 | 595 | 602 | 607 | 613 | 621 | 629 | 636 | 643 | 649 | 654 | 661 | 669 | 674
360 | 1.0511 | 10 | 21 | 45 | 74 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 2 | 4 | 8 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 5 | 10 | 16 | 23 | 28 | 36 | 43 | 51 | 59 | 65 | 72 | 80 | 87 | 94 | 99 | 107 | 113 | 119 | 125 | 133 | 141 | 149 | 156 | 162 | 168 | 173 | 180 | 186 | 193 | 201 | 207 | 215 | 223 | 229 | 234 | 241 | 246 | 251 | 256 | 262 | 269 | 275 | 280 | 287 | 294 | 299 | 306 | 311 | 317 | 323 | 330 | 336 | 342 | 348 | 353 | 360 | 368 | 376 | 384 | 390 | 395 | 403 | 410 | 416 | 421 | 428 | 435 | 440 | 446 | 452 | 459 | 464 | 470 | 478 | 486 | 491 | 497 | 503 | 509 | 517 | 523 | 531 | 536 | 544 | 551 | 559 | 567 | 572 | 580 | 586 | 593 | 599 | 607 | 615 | 621 | 629 | 636 | 641 | 649 | 656 | 664 | 672 | 678 | 685
361 | 1.8667 | 17 | 42 | 78 | 133 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 3 | 7 | 13 | 22 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 6 | 12 | 17 | 22 | 30 | 35 | 42 | 50 | 55 | 63 | 71 | 77 | 83 | 88 | 93 | 98 | 105 | 110 | 116 | 121 | 126 | 134 | 141 | 148 | 155 | 161 | 169 | 177 | 184 | 192 | 198 | 206 | 213 | 219 | 224 | 231 | 238 | 244 | 250 | 255 | 263 | 269 | 277 | 285 | 291 | 299 | 307 | 314 | 322 | 330 | 337 | 345 | 350 | 358 | 364 | 372 | 378 | 383 | 390 | 397 | 404 | 410 | 418 | 425 | 431 | 438 | 444 | 451 | 456 | 461 | 466 | 474 | 481 | 489 | 494 | 502 | 509 | 516 | 522 | 529 | 534 | 541 | 546 | 552 | 557 | 564 | 572 | 579 | 587 | 594 | 602 | 610 | 615 | 620 | 627 | 632 | 639 | 645 | 651 | 657 | 663 | 671 | 678 | 685
362 | 1.0734 | 9 | 23 | 47 | 72 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 2 | 4 | 7 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 15 | 21 | 28 | 34 | 39 | 47 | 52 | 60 | 67 | 72 | 78 | 86 | 92 | 98 | 106 | 111 | 116 | 121 | 128 | 136 | 141 | 149 | 154 | 159 | 165 | 171 | 176 | 184 | 190 | 197 | 202 | 208 | 213 | 220 | 228 | 235 | 243 | 250 | 258 | 263 | 270 | 278 | 284 | 292 | 298 | 304 | 310 | 318 | 326 | 333 | 341 | 349 | 357 | 363 | 371 | 377 | 385 | 393 | 398 | 403 | 410 | 415 | 420 | 427 | 433 | 441 | 447 | 453 | 461 | 467 | 473 | 481 | 489 | 497 | 505 | 512 | 517 | 524 | 530 | 536 | 544 | 552 | 557 | 565 | 570 | 575 | 582 | 587 | 592 | 599 | 606 | 613 | 619 | 626 | 633 | 639 | 645 | 653 | 660 | 665 | 672 | 680 | 686
363 | 1.9112 | 20 | 42 | 86 | 125 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 3 | 7 | 13 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 6 | 13 | 20 | 26 | 34 | 41 | 49 | 56 | 62 | 70 | 77 | 84 | 90 | 97 | 103 | 110 | 117 | 124 | 130 | 137 | 145 | 150 | 158 | 164 | 170 | 178 | 184 | 189 | 194 | 200 | 206 | 211 | 218 | 226 | 232 | 237 | 243 | 251 | 257 | 264 | 269 | 277 | 284 | 292 | 300 | 308 | 315 | 321 | 326 | 332 | 339 | 344 | 349 | 354 | 360 | 368 | 376 | 384 | 390 | 396 | 404 | 410 | 418 | 425 | 432 | 439 | 446 | 454 | 459 | 464 | 472 | 479 | 487 | 494 | 500 | 508 | 514 | 522 | 529 | 537 | 542 | 549 | 555 | 562 | 567 | 575 | 580 | 588 | 593 | 598 | 604 | 612 | 617 | 622 | 628 | 635 | 642 | 649 | 657 | 665 | 673 | 680 | 686 | 694
364 | 1.3372 | 11 | 25 | 54 | 92 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 4 | 8 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 15 | 23 | 30 | 37 | 42 | 47 | 55 | 62 | 68 | 74 | 79 | 85 | 93 | 101 | 107 | 113 | 121 | 128 | 133 | 138 | 145 | 152 | 160 | 165 | 171 | 178 | 183 | 191 | 197 | 205 | 213 | 219 | 227 | 234 | 240 | 248 | 254 | 261 | 266 | 272 | 277 | 283 | 289 | 296 | 303 | 310 | 318 | 324 | 330 | 336 | 342 | 349 | 356 | 361 | 367 | 373 | 379 | 386 | 394 | 401 | 408 | 416 | 423 | 430 | 437 | 443 | 451 | 457 | 465 | 472 | 478 | 485 | 493 | 501 | 509 | 517 | 522 | 529 | 536 | 541 | 548 | 555 | 560 | 568 | 575 | 582 | 589 | 596 | 602 | 608 | 616 | 624 | 631 | 638 | 644 | 651 | 659 | 667 | 673 | 678 | 683 | 689 | 695
365 | 1.325 | 11 | 29 | 63 | 98 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 5 | 11 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 14 | 19 | 24 | 30 | 36 | 43 | 48 | 54 | 61 | 68 | 76 | 82 | 90 | 96 | 101 | 109 | 116 | 122 | 130 | 138 | 145 | 152 | 159 | 167 | 174 | 182 | 189 | 197 | 204 | 209 | 214 | 219 | 227 | 232 | 237 | 243 | 251 | 258 | 264 | 271 | 279 | 286 | 293 | 298 | 305 | 312 | 320 | 326 | 334 | 341 | 346 | 353 | 360 | 368 | 374 | 382 | 390 | 395 | 402 | 410 | 416 | 424 | 430 | 438 | 443 | 451 | 459 | 466 | 473 | 480 | 485 | 491 | 498 | 504 | 509 | 514 | 522 | 528 | 536 | 542 | 550 | 555 | 561 | 568 | 576 | 581 | 587 | 592 | 598 | 603 | 608 | 613 | 619 | 625 | 632 | 639 | 646 | 654 | 662 | 668 | 675 | 681 | 689
366 | 1.4971 | 15 | 32 | 59 | 101 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 3 | 6 | 10 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 17 | 25 | 31 | 37 | 45 | 50 | 57 | 65 | 71 | 76 | 84 | 91 | 98 | 103 | 109 | 116 | 123 | 130 | 138 | 143 | 149 | 154 | 161 | 167 | 175 | 182 | 190 | 196 | 204 | 212 | 219 | 224 | 229 | 236 | 243 | 251 | 258 | 264 | 271 | 279 | 285 | 292 | 300 | 308 | 315 | 322 | 328 | 334 | 342 | 347 | 353 | 358 | 363 | 371 | 378 | 383 | 391 | 396 | 403 | 411 | 418 | 424 | 431 | 437 | 442 | 448 | 456 | 461 | 467 | 473 | 478 | 483 | 490 | 495 | 500 | 505 | 513 | 520 | 527 | 534 | 542 | 547 | 552 | 558 | 566 | 574 | 579 | 584 | 590 | 595 | 603 | 609 | 614 | 619 | 626 | 634 | 642 | 650 | 655 | 661 | 669 | 674
367 | 1.8614 | 14 | 33 | 74 | 112 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 3 | 6 | 11 | 18 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 8 | 13 | 19 | 26 | 31 | 39 | 44 | 51 | 59 | 67 | 74 | 79 | 84 | 92 | 97 | 102 | 109 | 116 | 121 | 129 | 137 | 144 | 152 | 159 | 166 | 171 | 178 | 185 | 192 | 197 | 203 | 208 | 213 | 218 | 226 | 231 | 238 | 245 | 250 | 257 | 263 | 270 | 275 | 280 | 287 | 295 | 300 | 307 | 312 | 318 | 326 | 331 | 336 | 341 | 347 | 353 | 361 | 367 | 375 | 383 | 390 | 398 | 403 | 411 | 417 | 424 | 432 | 439 | 446 | 451 | 458 | 465 | 470 | 475 | 481 | 488 | 493 | 498 | 506 | 512 | 518 | 526 | 532 | 538 | 545 | 550 | 556 | 562 | 570 | 576 | 583 | 588 | 594 | 600 | 605 | 611 | 619 | 624 | 631 | 639 | 644 | 649 | 657 | 663
368 | 1.4838 | 14 | 32 | 56 | 92 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 5 | 8 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 16 | 24 | 30 | 35 | 42 | 50 | 57 | 65 | 70 | 75 | 82 | 88 | 93 | 100 | 105 | 112 | 118 | 123 | 128 | 135 | 142 | 147 | 154 | 160 | 167 | 175 | 180 | 186 | 193 | 200 | 206 | 211 | 217 | 222 | 227 | 232 | 239 | 246 | 253 | 261 | 269 | 274 | 282 | 289 | 296 | 303 | 311 | 316 | 321 | 329 | 334 | 342 | 350 | 357 | 365 | 370 | 377 | 385 | 393 | 398 | 406 | 412 | 419 | 427 | 433 | 441 | 448 | 454 | 461 | 466 | 474 | 482 | 490 | 497 | 504 | 512 | 517 | 523 | 528 | 533 | 539 | 544 | 549 | 555 | 560 | 567 | 574 | 579 | 585 | 590 | 595 | 603 | 608 | 616 | 624 | 631 | 637 | 644 | 649 | 656 | 661 | 669 | 676
369 | 1.2243 | 10 | 28 | 57 | 91 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 5 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 12 | 17 | 23 | 31 | 37 | 44 | 50 | 58 | 63 | 68 | 75 | 81 | 89 | 97 | 104 | 110 | 116 | 123 | 130 | 136 | 142 | 150 | 157 | 165 | 173 | 180 | 185 | 193 | 199 | 207 | 214 | 222 | 229 | 234 | 240 | 245 | 250 | 257 | 265 | 273 | 280 | 286 | 291 | 297 | 303 | 308 | 313 | 319 | 324 | 329 | 335 | 341 | 346 | 353 | 361 | 367 | 375 | 380 | 386 | 391 | 397 | 402 | 409 | 416 | 422 | 429 | 435 | 442 | 449 | 456 | 462 | 467 | 474 | 480 | 487 | 493 | 500 | 508 | 515 | 521 | 527 | 535 | 540 | 545 | 551 | 556 | 562 | 568 | 576 | 583 | 590 | 595 | 602 | 608 | 614 | 621 | 629 | 636 | 641 | 647 | 655 | 662 | 669
370 | 1.3464 | 11 | 25 | 51 | 88 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 2 | 5 | 8 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 17 | 23 | 28 | 35 | 43 | 51 | 57 | 65 | 72 | 77 | 82 | 90 | 97 | 103 | 108 | 115 | 121 | 126 | 132 | 137 | 144 | 149 | 154 | 162 | 170 | 178 | 185 | 191 | 199 | 204 | 210 | 217 | 223 | 228 | 233 | 239 | 245 | 253 | 259 | 267 | 273 | 279 | 284 | 291 | 297 | 302 | 307 | 315 | 323 | 331 | 336 | 343 | 351 | 356 | 364 | 370 | 377 | 382 | 388 | 393 | 399 | 407 | 414 | 420 | 427 | 434 | 442 | 449 | 457 | 464 | 472 | 480 | 488 | 495 | 501 | 506 | 512 | 519 | 525 | 533 | 541 | 546 | 554 | 562 | 569 | 574 | 579 | 587 | 595 | 600 | 606 | 612 | 617 | 622 | 628 | 636 | 641 | 646 | 654 | 660 | 668 | 675
371 | 1.5973 | 13 | 28 | 62 | 110 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 3 | 5 | 10 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 12 | 17 | 22 | 30 | 37 | 45 | 51 | 56 | 63 | 69 | 76 | 84 | 89 | 97 | 105 | 112 | 120 | 126 | 131 | 137 | 145 | 152 | 158 | 164 | 172 | 180 | 188 | 194 | 201 | 209 | 217 | 224 | 230 | 235 | 240 | 245 | 251 | 259 | 264 | 271 | 276 | 281 | 287 | 292 | 299 | 304 | 311 | 317 | 325 | 331 | 338 | 346 | 353 | 361 | 368 | 375 | 380 | 385 | 390 | 398 | 405 | 410 | 415 | 422 | 428 | 434 | 442 | 449 | 457 | 462 | 468 | 476 | 482 | 488 | 494 | 499 | 506 | 514 | 519 | 525 | 533 | 538 | 545 | 552 | 559 | 567 | 572 | 577 | 582 | 588 | 594 | 599 | 606 | 612 | 620 | 626 | 633 | 639 | 645 | 652 | 660 | 668 | 674
372 | 1.6158 | 10 | 28 | 69 | 103 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 4 | 11 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 7 | 14 | 20 | 28 | 33 | 41 | 47 | 54 | 59 | 65 | 73 | 79 | 86 | 93 | 101 | 107 | 113 | 120 | 126 | 132 | 138 | 143 | 151 | 158 | 164 | 169 | 177 | 183 | 191 | 199 | 204 | 209 | 215 | 221 | 228 | 236 | 244 | 249 | 255 | 262 | 267 | 274 | 279 | 284 | 289 | 294 | 300 | 305 | 312 | 317 | 325 | 331 | 338 | 343 | 349 | 357 | 365 | 373 | 379 | 384 | 392 | 399 | 405 | 411 | 417 | 424 | 432 | 437 | 443 | 448 | 456 | 463 | 470 | 475 | 480 | 485 | 493 | 501 | 508 | 516 | 521 | 527 | 534 | 539 | 547 | 553 | 560 | 566 | 571 | 578 | 583 | 589 | 597 | 603 | 611 | 619 | 627 | 634 | 639 | 646 | 652 | 659 | 666 | 674
373 | 1.9184 | 10 | 39 | 70 | 115 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 2 | 6 | 10 | 17 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 15 | 23 | 28 | 36 | 41 | 47 | 55 | 62 | 70 | 78 | 86 | 92 | 98 | 106 | 114 | 121 | 127 | 132 | 139 | 147 | 152 | 158 | 163 | 171 | 179 | 184 | 190 | 195 | 203 | 210 | 215 | 222 | 227 | 232 | 237 | 243 | 248 | 255 | 262 | 267 | 273 | 280 | 285 | 292 | 299 | 304 | 311 | 319 | 326 | 331 | 338 | 344 | 352 | 360 | 365 | 372 | 380 | 386 | 394 | 402 | 410 | 418 | 426 | 431 | 436 | 443 | 448 | 456 | 464 | 470 | 478 | 484 | 491 | 497 | 503 | 510 | 518 | 525 | 530 | 535 | 540 | 548 | 556 | 561 | 568 | 574 | 579 | 585 | 590 | 595 | 603 | 609 | 616 | 624 | 631 | 637 | 644 | 652 | 659 | 667 | 674 | 681 | 689
374 | 1.5499 | 10 | 24 | 51 | 82 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 2 | 3 | 8 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 24 | 30 | 35 | 42 | 48 | 54 | 61 | 66 | 74 | 79 | 85 | 91 | 98 | 105 | 113 | 120 | 128 | 133 | 138 | 145 | 151 | 159 | 165 | 170 | 177 | 182 | 189 | 194 | 202 | 209 | 215 | 223 | 231 | 238 | 246 | 252 | 260 | 265 | 271 | 276 | 282 | 289 | 296 | 302 | 308 | 314 | 319 | 324 | 329 | 334 | 341 | 349 | 354 | 361 | 369 | 377 | 383 | 388 | 396 | 404 | 410 | 416 | 422 | 427 | 432 | 439 | 446 | 454 | 462 | 467 | 474 | 480 | 486 | 491 | 499 | 504 | 510 | 517 | 524 | 532 | 539 | 547 | 552 | 557 | 565 | 570 | 578 | 586 | 592 | 597 | 605 | 611 | 617 | 622 | 628 | 634 | 642 | 649 | 656 | 662 | 669 | 676
375 | 1.5409 | 13 | 26 | 53 | 86 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 5 | 8 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 13 | 19 | 25 | 33 | 41 | 49 | 54 | 60 | 66 | 71 | 79 | 86 | 93 | 99 | 105 | 113 | 121 | 127 | 132 | 140 | 145 | 151 | 158 | 163 | 168 | 174 | 181 | 187 | 192 | 197 | 202 | 207 | 214 | 219 | 225 | 231 | 238 | 245 | 253 | 258 | 265 | 272 | 279 | 285 | 290 | 297 | 302 | 308 | 316 | 323 | 328 | 333 | 339 | 347 | 354 | 362 | 368 | 375 | 380 | 386 | 393 | 398 | 405 | 411 | 418 | 424 | 430 | 438 | 446 | 451 | 457 | 463 | 470 | 477 | 483 | 488 | 496 | 504 | 512 | 517 | 525 | 531 | 539 | 545 | 553 | 560 | 566 | 574 | 582 | 588 | 593 | 600 | 607 | 615 | 623 | 631 | 636 | 644 | 652 | 659 | 667 | 672 | 679
376 | 1.8766 | 16 | 35 | 67 | 111 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 3 | 5 | 10 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 14 | 20 | 28 | 36 | 44 | 49 | 55 | 61 | 68 | 75 | 81 | 88 | 94 | 99 | 104 | 109 | 114 | 121 | 128 | 133 | 141 | 147 | 152 | 157 | 165 | 171 | 179 | 184 | 192 | 197 | 203 | 211 | 217 | 225 | 230 | 236 | 244 | 249 | 254 | 260 | 268 | 276 | 282 | 289 | 295 | 302 | 309 | 317 | 322 | 329 | 334 | 339 | 346 | 353 | 360 | 367 | 374 | 382 | 389 | 397 | 402 | 407 | 412 | 419 | 424 | 430 | 438 | 446 | 454 | 460 | 467 | 475 | 483 | 489 | 495 | 502 | 507 | 512 | 517 | 524 | 532 | 539 | 544 | 550 | 557 | 565 | 570 | 576 | 581 | 589 | 594 | 600 | 606 | 614 | 622 | 629 | 636 | 642 | 650 | 657 | 663 | 668 | 674
377 | 1.2976 | 8 | 28 | 56 | 89 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 2 | 4 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 15 | 22 | 29 | 36 | 44 | 50 | 55 | 62 | 70 | 75 | 82 | 88 | 93 | 99 | 107 | 114 | 122 | 129 | 134 | 139 | 147 | 152 | 158 | 166 | 172 | 179 | 186 | 194 | 199 | 205 | 211 | 216 | 224 | 232 | 237 | 242 | 249 | 256 | 262 | 269 | 274 | 279 | 287 | 294 | 299 | 305 | 311 | 316 | 324 | 332 | 340 | 348 | 354 | 359 | 367 | 373 | 380 | 385 | 393 | 401 | 407 | 415 | 421 | 426 | 432 | 437 | 443 | 450 | 458 | 465 | 473 | 479 | 485 | 492 | 499 | 504 | 512 | 518 | 525 | 531 | 536 | 541 | 546 | 554 | 560 | 567 | 573 | 578 | 586 | 594 | 599 | 604 | 611 | 618 | 626 | 633 | 640 | 646 | 654 | 659 | 665 | 670 | 676
378 | 1.2701 | 13 | 25 | 46 | 74 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 3 | 5 | 8 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 12 | 18 | 24 | 31 | 37 | 45 | 51 | 58 | 66 | 73 | 79 | 85 | 92 | 100 | 107 | 112 | 117 | 123 | 130 | 136 | 143 | 150 | 158 | 163 | 168 | 176 | 181 | 186 | 192 | 200 | 208 | 215 | 221 | 226 | 232 | 239 | 247 | 254 | 262 | 268 | 275 | 280 | 286 | 294 | 301 | 306 | 311 | 319 | 327 | 332 | 337 | 345 | 351 | 359 | 366 | 372 | 379 | 384 | 389 | 395 | 403 | 411 | 417 | 423 | 428 | 436 | 442 | 447 | 454 | 459 | 464 | 472 | 477 | 483 | 491 | 497 | 503 | 510 | 516 | 522 | 529 | 536 | 544 | 552 | 560 | 567 | 573 | 580 | 586 | 592 | 598 | 603 | 609 | 616 | 623 | 630 | 636 | 641 | 648 | 654 | 660 | 666 | 674
379 | 1.3693 | 14 | 28 | 55 | 86 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 141 | 3 | 5 | 9 | 13 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 13 | 18 | 23 | 31 | 36 | 42 | 49 | 57 | 64 | 72 | 80 | 87 | 93 | 98 | 106 | 111 | 117 | 122 | 128 | 134 | 140 | 146 | 151 | 156 | 161 | 167 | 175 | 181 | 186 | 192 | 199 | 205 | 211 | 219 | 225 | 233 | 241 | 247 | 252 | 257 | 263 | 269 | 274 | 281 | 289 | 296 | 301 | 306 | 313 | 319 | 327 | 333 | 339 | 346 | 354 | 360 | 365 | 370 | 377 | 385 | 393 | 398 | 405 | 412 | 420 | 426 | 431 | 438 | 443 | 448 | 456 | 463 | 468 | 476 | 481 | 486 | 494 | 502 | 508 | 515 | 521 | 527 | 533 | 541 | 546 | 554 | 559 | 566 | 572 | 579 | 584 | 591 | 596 | 602 | 609 | 616 | 621 | 629 | 637 | 643 | 650 | 657 | 664
380 | 1.0302 | 8 | 19 | 36 | 65 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 2 | 3 | 6 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 14 | 20 | 27 | 33 | 39 | 44 | 49 | 56 | 63 | 69 | 77 | 82 | 89 | 96 | 103 | 109 | 116 | 122 | 128 | 135 | 143 | 149 | 156 | 162 | 169 | 177 | 184 | 189 | 197 | 203 | 211 | 219 | 225 | 231 | 236 | 243 | 249 | 254 | 259 | 266 | 273 | 278 | 285 | 293 | 299 | 307 | 312 | 317 | 324 | 329 | 334 | 342 | 347 | 355 | 361 | 366 | 371 | 377 | 385 | 393 | 398 | 404 | 410 | 418 | 426 | 432 | 438 | 443 | 451 | 458 | 466 | 473 | 480 | 485 | 490 | 496 | 501 | 508 | 514 | 519 | 524 | 531 | 536 | 543 | 550 | 557 | 562 | 570 | 577 | 584 | 592 | 600 | 605 | 610 | 616 | 621 | 627 | 632 | 638 | 646 | 652 | 658 | 665
381 | 1.6199 | 13 | 33 | 61 | 96 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 3 | 7 | 11 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 10 | 16 | 21 | 27 | 32 | 39 | 45 | 52 | 57 | 62 | 67 | 74 | 82 | 90 | 95 | 100 | 108 | 116 | 121 | 126 | 131 | 139 | 145 | 151 | 157 | 165 | 171 | 178 | 184 | 191 | 196 | 201 | 209 | 217 | 222 | 230 | 238 | 244 | 250 | 255 | 263 | 268 | 275 | 283 | 289 | 296 | 301 | 306 | 313 | 321 | 326 | 333 | 340 | 346 | 354 | 362 | 368 | 374 | 380 | 386 | 393 | 398 | 403 | 411 | 416 | 423 | 429 | 436 | 441 | 447 | 452 | 457 | 464 | 470 | 476 | 484 | 492 | 497 | 502 | 507 | 513 | 520 | 526 | 531 | 539 | 544 | 552 | 557 | 564 | 572 | 580 | 587 | 592 | 600 | 608 | 614 | 621 | 627 | 634 | 641 | 646 | 653 | 660
382 | 1.7568 | 15 | 40 | 83 | 126 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 3 | 6 | 13 | 21 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 14 | 22 | 29 | 34 | 42 | 47 | 54 | 62 | 67 | 75 | 81 | 86 | 91 | 97 | 104 | 109 | 115 | 120 | 125 | 132 | 140 | 147 | 155 | 160 | 166 | 172 | 178 | 184 | 190 | 198 | 206 | 211 | 216 | 221 | 228 | 233 | 241 | 249 | 256 | 261 | 267 | 274 | 280 | 286 | 291 | 298 | 304 | 311 | 317 | 324 | 330 | 337 | 343 | 348 | 356 | 361 | 369 | 377 | 383 | 391 | 398 | 406 | 412 | 420 | 426 | 431 | 437 | 443 | 450 | 456 | 462 | 469 | 477 | 483 | 491 | 498 | 504 | 509 | 515 | 520 | 526 | 532 | 537 | 542 | 548 | 554 | 562 | 568 | 575 | 582 | 590 | 596 | 601 | 606 | 614 | 619 | 627 | 633 | 640 | 647 | 653 | 661 | 667
383 | 1.1213 | 8 | 23 | 41 | 73 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 2 | 4 | 7 | 12 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 13 | 18 | 26 | 31 | 36 | 42 | 50 | 58 | 66 | 71 | 78 | 84 | 89 | 96 | 102 | 108 | 114 | 121 | 129 | 137 | 143 | 148 | 155 | 163 | 171 | 177 | 185 | 193 | 201 | 209 | 214 | 220 | 227 | 233 | 238 | 246 | 252 | 260 | 268 | 274 | 279 | 287 | 295 | 303 | 310 | 318 | 326 | 332 | 337 | 344 | 352 | 358 | 364 | 372 | 378 | 386 | 391 | 396 | 401 | 406 | 414 | 420 | 425 | 430 | 437 | 443 | 448 | 455 | 462 | 468 | 474 | 482 | 487 | 493 | 499 | 507 | 514 | 521 | 529 | 534 | 540 | 548 | 553 | 561 | 569 | 577 | 584 | 592 | 597 | 605 | 613 | 619 | 625 | 631 | 639 | 644 | 649 | 657 | 662 | 670 | 677 | 684 | 691
384 | 1.9855 | 18 | 48 | 90 | 134 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 4 | 8 | 15 | 21 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 5 | 11 | 17 | 23 | 29 | 37 | 44 | 50 | 58 | 65 | 72 | 77 | 84 | 89 | 97 | 102 | 109 | 116 | 123 | 131 | 138 | 144 | 151 | 158 | 164 | 170 | 176 | 184 | 191 | 196 | 203 | 208 | 216 | 223 | 230 | 235 | 242 | 249 | 256 | 263 | 269 | 274 | 281 | 289 | 295 | 301 | 306 | 311 | 319 | 324 | 331 | 336 | 342 | 349 | 357 | 363 | 369 | 377 | 384 | 392 | 399 | 406 | 411 | 417 | 424 | 429 | 436 | 442 | 448 | 456 | 464 | 469 | 475 | 481 | 488 | 496 | 502 | 510 | 518 | 525 | 531 | 537 | 542 | 549 | 557 | 564 | 572 | 578 | 583 | 590 | 596 | 601 | 607 | 612 | 619 | 627 | 634 | 641 | 647 | 652 | 660 | 665 | 672 | 678
385 | 1.4191 | 8 | 20 | 50 | 89 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 2 | 3 | 8 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 14 | 22 | 30 | 37 | 43 | 49 | 54 | 60 | 65 | 71 | 79 | 85 | 92 | 99 | 105 | 110 | 117 | 122 | 130 | 138 | 143 | 149 | 156 | 162 | 167 | 174 | 179 | 186 | 192 | 197 | 205 | 211 | 219 | 227 | 234 | 242 | 247 | 252 | 259 | 266 | 272 | 280 | 286 | 293 | 301 | 306 | 312 | 317 | 323 | 331 | 339 | 344 | 350 | 356 | 363 | 368 | 375 | 383 | 391 | 396 | 403 | 409 | 414 | 419 | 426 | 433 | 440 | 447 | 455 | 460 | 468 | 473 | 480 | 487 | 494 | 500 | 505 | 512 | 517 | 523 | 528 | 534 | 539 | 547 | 554 | 561 | 568 | 576 | 584 | 589 | 596 | 603 | 610 | 616 | 622 | 627 | 633 | 639 | 646 | 653 | 658 | 663 | 670
386 | 1.1777 | 11 | 26 | 48 | 79 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 5 | 8 | 13 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 11 | 18 | 23 | 31 | 39 | 46 | 52 | 59 | 67 | 72 | 78 | 85 | 90 | 95 | 100 | 107 | 113 | 120 | 127 | 134 | 139 | 144 | 150 | 156 | 164 | 171 | 178 | 184 | 191 | 197 | 202 | 210 | 218 | 225 | 233 | 240 | 246 | 252 | 259 | 265 | 271 | 278 | 286 | 291 | 297 | 304 | 312 | 320 | 328 | 336 | 343 | 351 | 358 | 366 | 371 | 377 | 382 | 387 | 394 | 401 | 409 | 415 | 420 | 426 | 431 | 438 | 446 | 452 | 459 | 465 | 472 | 480 | 486 | 491 | 497 | 503 | 508 | 513 | 518 | 526 | 533 | 538 | 545 | 551 | 559 | 564 | 570 | 577 | 585 | 592 | 600 | 606 | 614 | 622 | 627 | 635 | 643 | 651 | 659 | 665 | 672 | 678 | 686
387 | 1.2975 | 11 | 27 | 47 | 75 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 5 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 11 | 19 | 25 | 32 | 39 | 45 | 50 | 56 | 61 | 68 | 74 | 82 | 88 | 93 | 99 | 106 | 112 | 119 | 127 | 132 | 140 | 148 | 155 | 160 | 166 | 172 | 177 | 184 | 192 | 197 | 203 | 209 | 214 | 222 | 229 | 236 | 241 | 249 | 255 | 261 | 268 | 274 | 282 | 289 | 294 | 299 | 305 | 312 | 319 | 325 | 331 | 337 | 343 | 348 | 353 | 360 | 366 | 372 | 377 | 385 | 390 | 397 | 403 | 408 | 414 | 419 | 425 | 430 | 435 | 440 | 445 | 453 | 461 | 466 | 472 | 480 | 485 | 490 | 495 | 502 | 507 | 512 | 519 | 525 | 533 | 538 | 546 | 553 | 559 | 565 | 572 | 580 | 588 | 593 | 601 | 609 | 615 | 622 | 629 | 637 | 643 | 650 | 656
388 | 1.2473 | 9 | 26 | 46 | 71 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 2 | 5 | 8 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 12 | 18 | 23 | 31 | 37 | 42 | 49 | 56 | 64 | 70 | 75 | 80 | 87 | 94 | 99 | 105 | 111 | 116 | 123 | 130 | 136 | 142 | 149 | 157 | 163 | 171 | 178 | 184 | 190 | 196 | 204 | 212 | 220 | 225 | 232 | 238 | 243 | 251 | 258 | 266 | 274 | 279 | 286 | 292 | 299 | 306 | 311 | 317 | 325 | 330 | 338 | 346 | 353 | 359 | 365 | 373 | 378 | 384 | 392 | 397 | 403 | 411 | 419 | 425 | 430 | 436 | 441 | 448 | 453 | 460 | 466 | 471 | 476 | 481 | 489 | 494 | 501 | 507 | 512 | 518 | 526 | 532 | 537 | 542 | 549 | 556 | 563 | 568 | 573 | 580 | 585 | 593 | 601 | 609 | 615 | 623 | 629 | 634 | 641 | 649 | 656 | 664 | 671
389 | 1.8849 | 17 | 34 | 70 | 127 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 3 | 6 | 10 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 6 | 13 | 18 | 25 | 33 | 41 | 49 | 56 | 64 | 70 | 78 | 86 | 93 | 100 | 107 | 113 | 118 | 125 | 130 | 136 | 144 | 152 | 157 | 163 | 171 | 176 | 184 | 191 | 196 | 204 | 210 | 215 | 222 | 229 | 237 | 244 | 250 | 258 | 264 | 272 | 280 | 287 | 293 | 300 | 307 | 312 | 320 | 327 | 334 | 342 | 347 | 355 | 360 | 368 | 373 | 378 | 384 | 391 | 398 | 405 | 412 | 419 | 427 | 434 | 441 | 449 | 457 | 463 | 470 | 478 | 483 | 488 | 494 | 499 | 507 | 513 | 521 | 527 | 535 | 542 | 548 | 555 | 562 | 570 | 575 | 581 | 586 | 593 | 600 | 607 | 615 | 623 | 631 | 636 | 641 | 648 | 653 | 661 | 666 | 671 | 676 | 682 | 689 | 696
390 | 1.4037 | 13 | 28 | 57 | 90 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 2 | 5 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 14 | 20 | 25 | 33 | 38 | 45 | 52 | 59 | 66 | 72 | 78 | 83 | 88 | 96 | 104 | 109 | 116 | 124 | 131 | 138 | 145 | 150 | 156 | 163 | 169 | 177 | 185 | 193 | 201 | 206 | 213 | 219 | 225 | 232 | 237 | 242 | 250 | 255 | 260 | 266 | 274 | 280 | 288 | 294 | 300 | 308 | 313 | 318 | 326 | 333 | 339 | 345 | 350 | 357 | 365 | 372 | 378 | 385 | 393 | 400 | 408 | 414 | 420 | 426 | 431 | 437 | 442 | 448 | 453 | 458 | 463 | 468 | 474 | 481 | 488 | 496 | 502 | 508 | 516 | 523 | 531 | 537 | 545 | 552 | 560 | 567 | 573 | 578 | 585 | 590 | 596 | 602 | 609 | 615 | 621 | 627 | 634 | 641 | 647 | 653 | 660 | 667 | 673
391 | 1.6515 | 15 | 35 | 69 | 119 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 3 | 6 | 11 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 5 | 13 | 21 | 28 | 34 | 42 | 47 | 54 | 59 | 64 | 69 | 74 | 82 | 88 | 94 | 99 | 107 | 115 | 121 | 127 | 135 | 143 | 148 | 155 | 163 | 170 | 178 | 186 | 192 | 197 | 204 | 210 | 217 | 225 | 230 | 237 | 244 | 249 | 257 | 265 | 271 | 278 | 284 | 291 | 297 | 303 | 310 | 318 | 326 | 334 | 340 | 347 | 353 | 358 | 366 | 371 | 379 | 384 | 389 | 395 | 400 | 408 | 413 | 421 | 428 | 436 | 443 | 448 | 456 | 462 | 467 | 475 | 483 | 488 | 493 | 501 | 508 | 515 | 522 | 530 | 536 | 544 | 550 | 555 | 560 | 568 | 574 | 579 | 586 | 592 | 599 | 606 | 614 | 620 | 625 | 632 | 640 | 645 | 653 | 660 | 668 | 675 | 680 | 686
392 | 1.5787 | 10 | 33 | 67 | 104 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 2 | 6 | 11 | 16 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 6 | 12 | 19 | 25 | 31 | 39 | 47 | 52 | 58 | 66 | 74 | 82 | 87 | 92 | 98 | 104 | 109 | 115 | 120 | 126 | 133 | 138 | 145 | 150 | 156 | 162 | 170 | 176 | 183 | 188 | 196 | 202 | 210 | 215 | 221 | 228 | 235 | 242 | 247 | 254 | 262 | 267 | 272 | 278 | 286 | 291 | 297 | 304 | 312 | 318 | 325 | 333 | 339 | 345 | 350 | 355 | 360 | 365 | 370 | 375 | 381 | 386 | 392 | 399 | 407 | 412 | 419 | 424 | 429 | 437 | 442 | 448 | 453 | 459 | 464 | 469 | 475 | 481 | 489 | 494 | 500 | 508 | 516 | 522 | 528 | 536 | 542 | 548 | 554 | 561 | 569 | 574 | 582 | 588 | 593 | 600 | 608 | 616 | 621 | 628 | 634 | 640 | 647 | 655
393 | 1.8154 | 19 | 36 | 69 | 113 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 166 | 3 | 6 | 11 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 16 | 22 | 29 | 34 | 39 | 44 | 51 | 58 | 66 | 74 | 80 | 88 | 93 | 98 | 105 | 110 | 117 | 123 | 128 | 136 | 141 | 148 | 156 | 162 | 167 | 172 | 179 | 184 | 189 | 195 | 203 | 209 | 214 | 219 | 227 | 234 | 242 | 249 | 256 | 264 | 269 | 276 | 284 | 290 | 296 | 304 | 311 | 317 | 325 | 330 | 336 | 344 | 352 | 357 | 363 | 370 | 376 | 384 | 391 | 399 | 404 | 410 | 416 | 423 | 431 | 438 | 446 | 452 | 460 | 466 | 471 | 477 | 483 | 490 | 497 | 504 | 511 | 516 | 523 | 528 | 534 | 541 | 548 | 556 | 562 | 569 | 577 | 585 | 591 | 596 | 603 | 611 | 617 | 625 | 633 | 639 | 647 | 653 | 660 | 665 | 671 | 677 | 685
394 | 1.6095 | 9 | 24 | 50 | 91 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 2 | 4 | 8 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 15 | 23 | 31 | 36 | 41 | 46 | 53 | 59 | 67 | 72 | 78 | 86 | 92 | 100 | 105 | 113 | 120 | 126 | 131 | 136 | 144 | 151 | 156 | 161 | 168 | 174 | 181 | 187 | 193 | 201 | 206 | 213 | 219 | 227 | 234 | 241 | 248 | 254 | 261 | 266 | 273 | 278 | 286 | 293 | 298 | 305 | 312 | 320 | 328 | 334 | 341 | 347 | 352 | 358 | 364 | 369 | 374 | 381 | 389 | 394 | 402 | 408 | 416 | 424 | 429 | 437 | 444 | 449 | 454 | 460 | 466 | 473 | 480 | 485 | 492 | 497 | 505 | 510 | 518 | 523 | 531 | 537 | 542 | 548 | 556 | 562 | 568 | 573 | 579 | 585 | 593 | 601 | 608 | 615 | 623 | 629 | 634 | 639 | 646 | 653 | 659 | 667 | 675
395 | 1.5565 | 13 | 37 | 64 | 99 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 2 | 6 | 10 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 7 | 15 | 23 | 28 | 33 | 39 | 47 | 53 | 58 | 64 | 72 | 79 | 87 | 95 | 100 | 105 | 112 | 120 | 125 | 131 | 136 | 144 | 150 | 155 | 161 | 167 | 173 | 179 | 186 | 192 | 199 | 207 | 212 | 218 | 224 | 231 | 238 | 246 | 254 | 260 | 265 | 270 | 276 | 281 | 287 | 294 | 301 | 307 | 315 | 322 | 328 | 335 | 343 | 348 | 356 | 364 | 371 | 378 | 383 | 390 | 395 | 403 | 411 | 419 | 426 | 434 | 439 | 444 | 449 | 456 | 463 | 469 | 477 | 485 | 491 | 497 | 505 | 513 | 521 | 527 | 532 | 538 | 545 | 551 | 558 | 564 | 571 | 579 | 584 | 592 | 597 | 604 | 611 | 617 | 622 | 630 | 635 | 641 | 648 | 654 | 662 | 668 | 674 | 680
396 | 1.6886 | 11 | 30 | 56 | 99 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 138 | 2 | 5 | 9 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 13 | 21 | 29 | 35 | 41 | 49 | 54 | 61 | 67 | 72 | 77 | 82 | 88 | 94 | 99 | 104 | 111 | 116 | 122 | 128 | 133 | 140 | 148 | 153 | 159 | 166 | 171 | 176 | 181 | 189 | 197 | 204 | 210 | 215 | 223 | 230 | 235 | 240 | 246 | 251 | 257 | 262 | 268 | 276 | 284 | 291 | 298 | 305 | 312 | 317 | 323 | 330 | 337 | 342 | 349 | 356 | 363 | 369 | 375 | 383 | 391 | 397 | 402 | 408 | 414 | 419 | 426 | 431 | 437 | 445 | 450 | 455 | 462 | 470 | 476 | 484 | 489 | 494 | 501 | 506 | 512 | 520 | 527 | 534 | 539 | 544 | 551 | 559 | 564 | 571 | 579 | 584 | 590 | 598 | 606 | 613 | 621 | 627 | 632 | 637 | 642 | 649 | 655
397 | 1.5849 | 8 | 23 | 52 | 94 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 2 | 4 | 9 | 15 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 14 | 21 | 27 | 34 | 39 | 45 | 50 | 55 | 60 | 68 | 75 | 81 | 87 | 94 | 99 | 107 | 115 | 121 | 129 | 137 | 144 | 152 | 160 | 168 | 175 | 180 | 185 | 192 | 198 | 206 | 211 | 218 | 226 | 231 | 239 | 247 | 253 | 259 | 264 | 269 | 277 | 283 | 291 | 296 | 304 | 312 | 319 | 327 | 332 | 338 | 345 | 353 | 360 | 367 | 375 | 380 | 385 | 390 | 398 | 404 | 409 | 416 | 422 | 430 | 435 | 443 | 451 | 456 | 461 | 468 | 473 | 478 | 486 | 493 | 501 | 506 | 511 | 516 | 521 | 528 | 536 | 542 | 548 | 555 | 560 | 566 | 572 | 580 | 586 | 593 | 599 | 605 | 613 | 620 | 626 | 631 | 638 | 645 | 653 | 661 | 668 | 673 | 680
398 | 1.1773 | 12 | 25 | 48 | 80 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 2 | 4 | 7 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 6 | 12 | 20 | 27 | 35 | 43 | 50 | 55 | 61 | 67 | 73 | 79 | 84 | 89 | 94 | 101 | 109 | 117 | 124 | 129 | 137 | 142 | 149 | 157 | 163 | 170 | 176 | 183 | 190 | 198 | 204 | 210 | 217 | 222 | 230 | 237 | 245 | 253 | 259 | 267 | 275 | 280 | 288 | 293 | 300 | 307 | 313 | 320 | 328 | 335 | 342 | 350 | 355 | 361 | 367 | 373 | 380 | 387 | 395 | 401 | 406 | 414 | 422 | 428 | 435 | 440 | 448 | 453 | 459 | 466 | 472 | 477 | 484 | 489 | 496 | 501 | 506 | 512 | 520 | 526 | 532 | 538 | 545 | 550 | 557 | 564 | 571 | 576 | 581 | 586 | 593 | 598 | 606 | 614 | 619 | 625 | 631 | 638 | 644 | 649 | 655 | 663 | 671 | 679
399 | 1.7244 | 13 | 34 | 69 | 107 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 2 | 6 | 11 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 16 | 21 | 27 | 33 | 39 | 46 | 52 | 59 | 65 | 73 | 81 | 89 | 95 | 100 | 108 | 115 | 120 | 126 | 132 | 137 | 144 | 152 | 160 | 167 | 172 | 178 | 186 | 194 | 199 | 204 | 209 | 216 | 223 | 230 | 237 | 243 | 248 | 256 | 264 | 271 | 279 | 285 | 292 | 297 | 303 | 308 | 314 | 320 | 327 | 333 | 341 | 347 | 353 | 358 | 365 | 373 | 380 | 387 | 393 | 400 | 408 | 413 | 419 | 427 | 432 | 438 | 446 | 452 | 458 | 465 | 473 | 480 | 486 | 493 | 500 | 506 | 513 | 521 | 528 | 535 | 543 | 549 | 555 | 563 | 569 | 574 | 580 | 585 | 592 | 598 | 603 | 609 | 616 | 624 | 631 | 639 | 644 | 650 | 655 | 660 | 666 | 673 | 680
400 | 1.1756 | 10 | 20 | 39 | 72 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 2 | 3 | 6 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 16 | 21 | 27 | 33 | 40 | 48 | 56 | 63 | 71 | 76 | 81 | 89 | 96 | 102 | 109 | 116 | 121 | 128 | 134 | 140 | 148 | 154 | 159 | 165 | 173 | 179 | 184 | 189 | 196 | 202 | 210 | 215 | 220 | 225 | 231 | 238 | 244 | 250 | 255 | 263 | 270 | 277 | 282 | 289 | 296 | 304 | 311 | 316 | 324 | 332 | 339 | 345 | 352 | 357 | 362 | 369 | 377 | 382 | 389 | 395 | 403 | 409 | 416 | 423 | 431 | 439 | 445 | 453 | 461 | 468 | 474 | 482 | 489 | 496 | 503 | 511 | 519 | 526 | 531 | 538 | 543 | 550 | 558 | 565 | 573 | 578 | 584 | 590 | 598 | 604 | 609 | 615 | 621 | 626 | 631 | 639 | 644 | 652 | 660 | 666 | 672 | 677 | 683
401 | 1.3184 | 10 | 25 | 58 | 89 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 2 | 4 | 8 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 15 | 20 | 28 | 36 | 44 | 50 | 58 | 64 | 71 | 79 | 85 | 92 | 100 | 106 | 112 | 119 | 124 | 131 | 137 | 145 | 150 | 156 | 162 | 167 | 172 | 178 | 186 | 193 | 198 | 205 | 210 | 215 | 221 | 226 | 231 | 238 | 246 | 251 | 256 | 263 | 268 | 274 | 279 | 286 | 294 | 299 | 305 | 310 | 316 | 321 | 329 | 336 | 342 | 350 | 355 | 362 | 368 | 373 | 380 | 385 | 392 | 398 | 406 | 412 | 419 | 425 | 431 | 437 | 442 | 447 | 454 | 459 | 464 | 469 | 475 | 483 | 490 | 496 | 504 | 511 | 518 | 523 | 530 | 538 | 545 | 553 | 559 | 565 | 572 | 579 | 587 | 592 | 599 | 606 | 611 | 619 | 626 | 631 | 636 | 644 | 649 | 655 | 660
402 | 1.1342 | 10 | 20 | 48 | 77 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 2 | 4 | 8 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 11 | 18 | 23 | 29 | 36 | 42 | 49 | 57 | 64 | 71 | 78 | 86 | 92 | 100 | 106 | 113 | 120 | 126 | 132 | 140 | 146 | 154 | 161 | 166 | 174 | 182 | 190 | 195 | 203 | 211 | 219 | 224 | 232 | 239 | 245 | 251 | 259 | 267 | 275 | 280 | 287 | 292 | 300 | 308 | 316 | 321 | 327 | 333 | 341 | 347 | 354 | 359 | 365 | 371 | 377 | 385 | 391 | 398 | 403 | 408 | 416 | 423 | 431 | 438 | 446 | 454 | 460 | 466 | 471 | 477 | 483 | 491 | 496 | 501 | 507 | 513 | 519 | 525 | 533 | 539 | 545 | 553 | 559 | 566 | 574 | 582 | 588 | 596 | 603 | 609 | 615 | 623 | 631 | 637 | 643 | 651 | 658 | 664 | 670 | 677 | 683 | 690 | 695
403 | 1.1269 | 11 | 23 | 48 | 72 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 4 | 8 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 13 | 20 | 26 | 33 | 39 | 47 | 55 | 60 | 68 | 73 | 78 | 86 | 93 | 101 | 107 | 113 | 118 | 125 | 132 | 138 | 144 | 151 | 156 | 164 | 171 | 177 | 185 | 191 | 198 | 206 | 211 | 216 | 224 | 230 | 235 | 243 | 250 | 257 | 262 | 268 | 276 | 283 | 290 | 295 | 301 | 306 | 313 | 320 | 327 | 333 | 341 | 348 | 356 | 362 | 367 | 374 | 379 | 386 | 391 | 399 | 404 | 411 | 416 | 424 | 429 | 437 | 443 | 448 | 455 | 461 | 468 | 475 | 481 | 486 | 494 | 499 | 504 | 510 | 516 | 523 | 531 | 536 | 541 | 547 | 552 | 560 | 567 | 574 | 579 | 586 | 594 | 602 | 607 | 612 | 617 | 624 | 631 | 638 | 643 | 650 | 658 | 666 | 673
404 | 1.5434 | 16 | 33 | 58 | 89 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 3 | 5 | 8 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 15 | 23 | 31 | 38 | 43 | 51 | 59 | 64 | 69 | 74 | 81 | 86 | 92 | 97 | 103 | 110 | 116 | 124 | 132 | 140 | 147 | 152 | 160 | 168 | 174 | 180 | 187 | 194 | 199 | 204 | 211 | 216 | 224 | 231 | 236 | 241 | 249 | 257 | 264 | 271 | 276 | 283 | 290 | 298 | 303 | 309 | 316 | 323 | 331 | 337 | 342 | 348 | 353 | 358 | 365 | 370 | 378 | 383 | 389 | 397 | 402 | 409 | 417 | 425 | 430 | 437 | 443 | 450 | 455 | 463 | 469 | 474 | 479 | 485 | 493 | 500 | 506 | 513 | 518 | 523 | 529 | 535 | 541 | 546 | 553 | 561 | 567 | 572 | 580 | 587 | 592 | 597 | 604 | 611 | 619 | 626 | 634 | 641 | 647 | 652 | 660 | 668 | 676
405 | 1.6919 | 12 | 38 | 67 | 117 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 2 | 6 | 11 | 18 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 7 | 12 | 18 | 26 | 31 | 38 | 45 | 51 | 58 | 64 | 71 | 79 | 85 | 90 | 98 | 106 | 113 | 120 | 126 | 133 | 138 | 146 | 154 | 162 | 170 | 176 | 184 | 189 | 195 | 202 | 208 | 215 | 223 | 230 | 237 | 242 | 248 | 255 | 262 | 267 | 273 | 279 | 287 | 294 | 301 | 306 | 313 | 318 | 326 | 334 | 339 | 344 | 350 | 356 | 362 | 368 | 375 | 380 | 387 | 394 | 401 | 407 | 414 | 420 | 426 | 431 | 437 | 443 | 451 | 457 | 464 | 470 | 477 | 483 | 491 | 498 | 503 | 510 | 518 | 524 | 530 | 538 | 546 | 554 | 562 | 568 | 573 | 580 | 586 | 591 | 596 | 601 | 606 | 613 | 621 | 627 | 633 | 638 | 644 | 649 | 655 | 661 | 669 | 677
406 | 1.7443 | 14 | 28 | 69 | 113 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 3 | 5 | 11 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 12 | 20 | 26 | 33 | 39 | 44 | 51 | 56 | 63 | 71 | 78 | 86 | 93 | 101 | 107 | 115 | 122 | 128 | 136 | 142 | 148 | 155 | 162 | 169 | 174 | 181 | 187 | 193 | 200 | 208 | 214 | 221 | 226 | 231 | 239 | 245 | 252 | 258 | 264 | 271 | 279 | 284 | 292 | 299 | 306 | 314 | 322 | 330 | 336 | 343 | 350 | 357 | 364 | 371 | 377 | 382 | 390 | 395 | 401 | 408 | 415 | 423 | 431 | 436 | 441 | 447 | 454 | 461 | 469 | 474 | 480 | 488 | 493 | 499 | 507 | 514 | 522 | 529 | 536 | 543 | 549 | 557 | 564 | 571 | 579 | 587 | 592 | 597 | 605 | 610 | 616 | 621 | 627 | 632 | 640 | 647 | 652 | 657 | 663 | 671 | 678 | 685 | 690
407 | 1.7813 | 17 | 32 | 68 | 117 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 3 | 5 | 11 | 18 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 7 | 13 | 19 | 26 | 33 | 40 | 45 | 51 | 58 | 65 | 73 | 78 | 86 | 94 | 101 | 106 | 113 | 120 | 127 | 132 | 138 | 143 | 148 | 154 | 162 | 170 | 175 | 180 | 186 | 192 | 200 | 205 | 213 | 221 | 229 | 237 | 245 | 250 | 255 | 261 | 267 | 274 | 281 | 289 | 294 | 300 | 306 | 312 | 320 | 325 | 331 | 339 | 346 | 354 | 361 | 367 | 374 | 380 | 385 | 392 | 397 | 405 | 411 | 419 | 427 | 432 | 438 | 445 | 453 | 460 | 467 | 475 | 483 | 489 | 497 | 502 | 509 | 514 | 519 | 525 | 532 | 538 | 543 | 549 | 554 | 559 | 566 | 573 | 578 | 585 | 590 | 595 | 601 | 607 | 612 | 619 | 626 | 632 | 637 | 644 | 652 | 660 | 666 | 673
408 | 1.4023 | 9 | 25 | 49 | 90 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 2 | 4 | 7 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 7 | 15 | 23 | 28 | 35 | 42 | 49 | 56 | 63 | 71 | 76 | 81 | 87 | 92 | 98 | 103 | 108 | 114 | 120 | 128 | 136 | 142 | 148 | 154 | 161 | 168 | 176 | 183 | 188 | 193 | 199 | 204 | 212 | 218 | 224 | 230 | 235 | 240 | 247 | 255 | 260 | 268 | 273 | 280 | 286 | 291 | 298 | 306 | 313 | 320 | 327 | 334 | 341 | 346 | 351 | 358 | 366 | 371 | 377 | 384 | 390 | 398 | 405 | 410 | 417 | 425 | 430 | 438 | 444 | 450 | 458 | 464 | 472 | 477 | 485 | 491 | 497 | 502 | 509 | 515 | 521 | 528 | 533 | 538 | 544 | 552 | 560 | 567 | 573 | 581 | 588 | 594 | 600 | 605 | 613 | 620 | 626 | 633 | 638 | 643 | 649 | 657 | 665 | 672
409 | 1.2367 | 8 | 22 | 48 | 82 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 2 | 4 | 8 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 15 | 20 | 26 | 33 | 40 | 45 | 51 | 56 | 63 | 69 | 74 | 80 | 86 | 91 | 97 | 102 | 109 | 116 | 124 | 131 | 139 | 145 | 150 | 157 | 164 | 172 | 179 | 185 | 193 | 198 | 203 | 211 | 218 | 224 | 231 | 236 | 241 | 247 | 254 | 261 | 266 | 273 | 278 | 283 | 289 | 295 | 301 | 309 | 315 | 321 | 326 | 331 | 339 | 347 | 354 | 361 | 367 | 374 | 379 | 387 | 394 | 401 | 406 | 413 | 419 | 426 | 432 | 437 | 443 | 451 | 457 | 464 | 471 | 476 | 482 | 488 | 496 | 503 | 509 | 517 | 523 | 529 | 536 | 543 | 549 | 556 | 564 | 571 | 577 | 582 | 588 | 594 | 602 | 609 | 617 | 625 | 632 | 639 | 644 | 649 | 656 | 661 | 668
410 | 1.4322 | 8 | 29 | 58 | 97 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 2 | 5 | 10 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 11 | 19 | 25 | 31 | 38 | 43 | 50 | 57 | 63 | 68 | 73 | 80 | 86 | 92 | 99 | 104 | 112 | 117 | 125 | 130 | 135 | 141 | 146 | 151 | 157 | 164 | 170 | 177 | 185 | 191 | 197 | 205 | 212 | 218 | 224 | 229 | 236 | 241 | 247 | 252 | 257 | 265 | 273 | 278 | 284 | 291 | 299 | 307 | 314 | 321 | 329 | 336 | 341 | 349 | 356 | 362 | 370 | 377 | 385 | 391 | 396 | 404 | 412 | 419 | 424 | 431 | 437 | 443 | 451 | 456 | 464 | 472 | 480 | 486 | 493 | 501 | 509 | 514 | 521 | 529 | 536 | 542 | 548 | 556 | 563 | 570 | 575 | 582 | 587 | 595 | 603 | 608 | 613 | 620 | 626 | 633 | 640 | 645 | 651 | 657 | 662 | 669 | 676
411 | 1.1481 | 6 | 18 | 38 | 71 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1 | 3 | 7 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 13 | 18 | 24 | 29 | 37 | 43 | 48 | 55 | 63 | 68 | 75 | 82 | 89 | 95 | 102 | 108 | 113 | 118 | 124 | 129 | 135 | 140 | 147 | 153 | 159 | 165 | 173 | 181 | 187 | 195 | 203 | 210 | 217 | 225 | 231 | 239 | 246 | 253 | 258 | 265 | 270 | 276 | 282 | 288 | 293 | 301 | 307 | 313 | 320 | 327 | 333 | 338 | 344 | 352 | 359 | 364 | 371 | 377 | 385 | 392 | 400 | 406 | 411 | 417 | 425 | 430 | 435 | 442 | 447 | 452 | 460 | 466 | 473 | 479 | 486 | 492 | 498 | 503 | 509 | 515 | 522 | 527 | 534 | 540 | 547 | 553 | 561 | 566 | 571 | 577 | 585 | 591 | 597 | 603 | 611 | 619 | 624 | 632 | 638 | 645 | 651 | 657 | 665
412 | 1.9047 | 18 | 45 | 85 | 124 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 3 | 7 | 13 | 19 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 12 | 18 | 26 | 33 | 39 | 46 | 52 | 60 | 68 | 74 | 80 | 87 | 93 | 101 | 108 | 114 | 122 | 130 | 136 | 142 | 149 | 155 | 161 | 169 | 175 | 181 | 189 | 195 | 203 | 211 | 218 | 226 | 231 | 237 | 245 | 253 | 258 | 266 | 271 | 278 | 285 | 291 | 296 | 301 | 306 | 312 | 320 | 327 | 334 | 340 | 346 | 354 | 359 | 364 | 369 | 374 | 379 | 384 | 389 | 395 | 401 | 406 | 413 | 418 | 424 | 432 | 438 | 446 | 454 | 459 | 467 | 475 | 482 | 490 | 497 | 505 | 512 | 518 | 524 | 531 | 538 | 543 | 551 | 556 | 564 | 571 | 579 | 585 | 593 | 599 | 604 | 609 | 615 | 623 | 630 | 637 | 643 | 651 | 658 | 663 | 668 | 673 | 681
413 | 1.9244 | 12 | 38 | 83 | 124 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 3 | 7 | 14 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 10 | 15 | 20 | 28 | 35 | 42 | 47 | 54 | 62 | 67 | 75 | 81 | 87 | 94 | 99 | 106 | 114 | 120 | 125 | 133 | 140 | 148 | 154 | 161 | 167 | 175 | 181 | 187 | 194 | 200 | 208 | 213 | 218 | 224 | 231 | 239 | 247 | 252 | 258 | 266 | 273 | 278 | 285 | 290 | 298 | 306 | 312 | 317 | 322 | 329 | 334 | 342 | 347 | 352 | 359 | 366 | 372 | 379 | 387 | 393 | 399 | 404 | 411 | 418 | 423 | 431 | 436 | 443 | 449 | 454 | 462 | 469 | 476 | 483 | 490 | 495 | 502 | 507 | 515 | 521 | 528 | 534 | 542 | 548 | 553 | 561 | 569 | 575 | 581 | 588 | 594 | 602 | 607 | 614 | 621 | 628 | 635 | 641 | 649 | 654 | 661 | 668 | 673
414 | 1.5913 | 10 | 31 | 65 | 104 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 2 | 5 | 10 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 6 | 14 | 21 | 28 | 35 | 43 | 49 | 56 | 62 | 70 | 77 | 84 | 91 | 96 | 103 | 108 | 116 | 122 | 130 | 138 | 145 | 151 | 157 | 162 | 169 | 176 | 181 | 188 | 194 | 201 | 209 | 214 | 220 | 227 | 233 | 240 | 248 | 255 | 262 | 270 | 276 | 281 | 288 | 293 | 300 | 308 | 314 | 321 | 328 | 334 | 339 | 344 | 349 | 354 | 361 | 367 | 375 | 383 | 388 | 395 | 400 | 408 | 416 | 423 | 429 | 437 | 443 | 448 | 455 | 462 | 467 | 474 | 480 | 485 | 490 | 496 | 503 | 508 | 515 | 520 | 526 | 534 | 541 | 547 | 553 | 558 | 566 | 574 | 581 | 586 | 593 | 599 | 607 | 614 | 620 | 628 | 636 | 643 | 649 | 657 | 665 | 670 | 676 | 682
415 | 1.8591 | 12 | 39 | 82 | 131 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 2 | 6 | 13 | 20 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 5 | 13 | 20 | 25 | 33 | 41 | 49 | 54 | 62 | 67 | 74 | 81 | 88 | 95 | 101 | 109 | 115 | 120 | 127 | 135 | 140 | 146 | 154 | 160 | 166 | 174 | 182 | 188 | 195 | 200 | 208 | 213 | 220 | 225 | 233 | 239 | 247 | 255 | 262 | 267 | 273 | 281 | 289 | 296 | 304 | 309 | 316 | 321 | 327 | 335 | 342 | 347 | 352 | 360 | 365 | 373 | 381 | 387 | 392 | 399 | 406 | 412 | 420 | 426 | 434 | 440 | 445 | 451 | 457 | 463 | 469 | 474 | 480 | 486 | 491 | 499 | 505 | 511 | 517 | 525 | 530 | 535 | 540 | 546 | 554 | 561 | 567 | 575 | 580 | 586 | 591 | 597 | 604 | 609 | 617 | 625 | 630 | 638 | 643 | 650 | 657 | 663 | 671 | 676
416 | 1.1303 | 11 | 27 | 48 | 80 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 2 | 5 | 8 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 12 | 18 | 23 | 30 | 37 | 45 | 52 | 60 | 67 | 74 | 81 | 88 | 96 | 101 | 108 | 116 | 124 | 130 | 137 | 143 | 151 | 159 | 167 | 173 | 181 | 189 | 196 | 203 | 210 | 215 | 221 | 229 | 234 | 240 | 245 | 252 | 257 | 263 | 271 | 277 | 283 | 291 | 299 | 307 | 314 | 320 | 327 | 332 | 338 | 344 | 350 | 355 | 363 | 368 | 374 | 380 | 385 | 391 | 399 | 404 | 409 | 417 | 423 | 429 | 434 | 442 | 447 | 454 | 460 | 466 | 471 | 478 | 486 | 493 | 498 | 504 | 512 | 517 | 524 | 532 | 540 | 547 | 555 | 563 | 571 | 577 | 584 | 590 | 597 | 605 | 610 | 615 | 620 | 625 | 633 | 638 | 644 | 649 | 655 | 661 | 666 | 673 | 678
417 | 1.8643 | 12 | 37 | 73 | 128 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 2 | 6 | 11 | 20 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 7 | 12 | 18 | 24 | 30 | 38 | 43 | 51 | 59 | 67 | 74 | 80 | 87 | 95 | 103 | 108 | 114 | 122 | 127 | 134 | 141 | 147 | 152 | 157 | 164 | 171 | 179 | 184 | 191 | 199 | 205 | 213 | 220 | 227 | 234 | 239 | 244 | 249 | 255 | 261 | 266 | 274 | 280 | 287 | 292 | 299 | 307 | 312 | 320 | 328 | 333 | 339 | 345 | 350 | 356 | 362 | 367 | 375 | 381 | 389 | 394 | 402 | 409 | 417 | 423 | 429 | 437 | 442 | 450 | 458 | 464 | 469 | 476 | 482 | 487 | 492 | 500 | 508 | 516 | 524 | 531 | 539 | 546 | 552 | 559 | 564 | 571 | 577 | 584 | 591 | 597 | 605 | 611 | 619 | 625 | 633 | 638 | 646 | 654 | 662 | 669 | 677 | 684 | 691
418 | 1.8146 | 15 | 35 | 68 | 112 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 3 | 6 | 11 | 18 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 6 | 12 | 17 | 24 | 32 | 38 | 43 | 50 | 58 | 66 | 71 | 76 | 84 | 89 | 94 | 101 | 108 | 114 | 122 | 128 | 133 | 140 | 147 | 152 | 159 | 166 | 172 | 177 | 184 | 189 | 194 | 200 | 205 | 210 | 215 | 222 | 230 | 236 | 241 | 246 | 253 | 261 | 269 | 275 | 281 | 287 | 295 | 302 | 309 | 314 | 322 | 329 | 337 | 343 | 351 | 357 | 362 | 367 | 373 | 381 | 388 | 395 | 402 | 407 | 415 | 423 | 431 | 439 | 444 | 450 | 456 | 464 | 471 | 478 | 484 | 489 | 497 | 503 | 510 | 517 | 522 | 527 | 533 | 539 | 545 | 551 | 556 | 561 | 567 | 574 | 580 | 587 | 594 | 600 | 605 | 612 | 620 | 625 | 630 | 635 | 641 | 647 | 652 | 658
419 | 1.2044 | 11 | 21 | 48 | 79 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 4 | 8 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 13 | 18 | 24 | 32 | 39 | 45 | 53 | 59 | 66 | 73 | 79 | 87 | 92 | 97 | 105 | 110 | 117 | 123 | 128 | 134 | 140 | 145 | 152 | 157 | 163 | 170 | 178 | 185 | 193 | 198 | 205 | 211 | 217 | 222 | 230 | 238 | 243 | 250 | 257 | 262 | 267 | 275 | 281 | 288 | 295 | 303 | 309 | 314 | 321 | 329 | 335 | 343 | 350 | 357 | 365 | 373 | 379 | 386 | 391 | 396 | 404 | 409 | 415 | 423 | 429 | 434 | 441 | 446 | 453 | 461 | 469 | 476 | 483 | 490 | 496 | 504 | 509 | 516 | 522 | 527 | 535 | 543 | 549 | 555 | 561 | 568 | 574 | 579 | 585 | 590 | 598 | 605 | 612 | 617 | 624 | 629 | 635 | 641 | 649 | 657 | 662 | 669 | 676
420 | 1.6294 | 17 | 35 | 66 | 109 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 3 | 6 | 10 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6 | 13 | 21 | 28 | 34 | 42 | 48 | 55 | 62 | 69 | 76 | 82 | 90 | 98 | 104 | 110 | 116 | 123 | 128 | 135 | 142 | 149 | 155 | 163 | 171 | 179 | 185 | 190 | 197 | 204 | 209 | 217 | 222 | 230 | 236 | 243 | 248 | 254 | 261 | 266 | 271 | 278 | 285 | 292 | 297 | 303 | 311 | 318 | 324 | 329 | 334 | 342 | 349 | 355 | 362 | 368 | 375 | 380 | 387 | 393 | 401 | 406 | 412 | 417 | 425 | 430 | 437 | 443 | 448 | 455 | 462 | 468 | 473 | 479 | 484 | 489 | 495 | 503 | 509 | 514 | 522 | 530 | 538 | 545 | 553 | 560 | 567 | 575 | 581 | 586 | 593 | 601 | 608 | 616 | 623 | 628 | 636 | 643 | 649 | 657 | 664 | 670 | 675 | 680
421 | 1.8273 | 11 | 32 | 60 | 101 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 2 | 5 | 9 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 15 | 22 | 27 | 35 | 41 | 46 | 54 | 62 | 68 | 76 | 82 | 89 | 97 | 102 | 107 | 114 | 122 | 129 | 135 | 143 | 148 | 153 | 160 | 167 | 173 | 178 | 185 | 190 | 196 | 203 | 211 | 216 | 222 | 228 | 235 | 240 | 247 | 255 | 260 | 268 | 274 | 279 | 286 | 293 | 300 | 308 | 314 | 322 | 327 | 332 | 340 | 347 | 354 | 360 | 368 | 376 | 383 | 389 | 394 | 400 | 406 | 414 | 420 | 428 | 433 | 441 | 448 | 454 | 459 | 465 | 473 | 481 | 489 | 496 | 501 | 507 | 513 | 521 | 526 | 534 | 542 | 547 | 554 | 562 | 567 | 573 | 578 | 584 | 590 | 598 | 605 | 610 | 618 | 626 | 632 | 640 | 647 | 653 | 660 | 667 | 673 | 680 | 685
422 | 1.5058 | 11 | 31 | 57 | 88 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 2 | 5 | 9 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 14 | 21 | 29 | 35 | 42 | 49 | 56 | 64 | 69 | 76 | 82 | 88 | 94 | 102 | 110 | 118 | 126 | 134 | 140 | 146 | 151 | 156 | 163 | 168 | 176 | 183 | 188 | 194 | 202 | 207 | 214 | 220 | 226 | 234 | 241 | 247 | 255 | 260 | 268 | 276 | 281 | 286 | 293 | 299 | 305 | 313 | 318 | 325 | 332 | 340 | 348 | 355 | 362 | 370 | 377 | 383 | 390 | 398 | 405 | 413 | 421 | 427 | 435 | 441 | 446 | 454 | 459 | 465 | 472 | 480 | 488 | 496 | 501 | 508 | 513 | 518 | 524 | 529 | 535 | 542 | 547 | 552 | 558 | 563 | 570 | 576 | 583 | 590 | 597 | 603 | 608 | 614 | 620 | 625 | 631 | 636 | 642 | 647 | 652 | 658 | 665 | 670 | 678
423 | 1.2798 | 12 | 32 | 63 | 97 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 2 | 5 | 10 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 14 | 21 | 27 | 32 | 37 | 43 | 49 | 55 | 63 | 71 | 78 | 85 | 93 | 100 | 107 | 113 | 120 | 126 | 134 | 140 | 146 | 152 | 158 | 165 | 170 | 177 | 183 | 188 | 194 | 200 | 208 | 216 | 223 | 228 | 233 | 239 | 246 | 251 | 258 | 266 | 273 | 281 | 287 | 292 | 298 | 305 | 313 | 321 | 326 | 334 | 340 | 347 | 353 | 360 | 365 | 370 | 378 | 386 | 391 | 396 | 402 | 409 | 416 | 424 | 431 | 437 | 444 | 451 | 458 | 463 | 468 | 473 | 479 | 487 | 492 | 498 | 504 | 511 | 518 | 523 | 529 | 535 | 543 | 550 | 555 | 560 | 566 | 573 | 581 | 588 | 594 | 602 | 610 | 616 | 624 | 631 | 637 | 642 | 649 | 656 | 661 | 667 | 674
424 | 1.1734 | 12 | 22 | 41 | 76 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 2 | 4 | 7 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 14 | 19 | 25 | 31 | 37 | 45 | 51 | 59 | 64 | 69 | 74 | 79 | 84 | 90 | 97 | 104 | 109 | 116 | 124 | 132 | 139 | 146 | 151 | 156 | 161 | 169 | 174 | 182 | 188 | 193 | 200 | 207 | 214 | 219 | 226 | 234 | 242 | 250 | 256 | 263 | 271 | 278 | 283 | 288 | 294 | 299 | 306 | 311 | 319 | 324 | 329 | 336 | 342 | 347 | 353 | 358 | 363 | 370 | 378 | 385 | 393 | 398 | 404 | 409 | 414 | 421 | 426 | 432 | 439 | 444 | 450 | 457 | 463 | 470 | 478 | 485 | 490 | 495 | 502 | 509 | 514 | 522 | 527 | 533 | 538 | 543 | 548 | 554 | 561 | 567 | 573 | 580 | 587 | 595 | 600 | 608 | 614 | 620 | 628 | 635 | 642 | 650 | 656
425 | 1.3373 | 11 | 22 | 49 | 88 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 2 | 4 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 5 | 11 | 17 | 23 | 30 | 36 | 41 | 46 | 52 | 58 | 63 | 71 | 77 | 82 | 90 | 97 | 102 | 109 | 117 | 125 | 131 | 136 | 143 | 149 | 156 | 164 | 172 | 180 | 188 | 195 | 203 | 208 | 213 | 219 | 227 | 234 | 242 | 247 | 254 | 262 | 270 | 275 | 280 | 286 | 291 | 296 | 303 | 309 | 317 | 323 | 330 | 335 | 343 | 350 | 356 | 364 | 372 | 378 | 385 | 391 | 397 | 404 | 412 | 420 | 426 | 432 | 440 | 446 | 452 | 460 | 465 | 470 | 478 | 486 | 494 | 500 | 508 | 515 | 520 | 525 | 532 | 538 | 543 | 551 | 558 | 566 | 571 | 576 | 581 | 587 | 593 | 599 | 606 | 614 | 621 | 626 | 631 | 638 | 645 | 650 | 657 | 663 | 669 | 675
426 | 1.6729 | 17 | 41 | 82 | 123 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 3 | 7 | 13 | 19 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 7 | 12 | 20 | 25 | 31 | 39 | 46 | 51 | 59 | 67 | 75 | 80 | 86 | 92 | 98 | 106 | 111 | 118 | 123 | 128 | 136 | 143 | 151 | 156 | 162 | 168 | 174 | 180 | 185 | 193 | 199 | 206 | 211 | 218 | 223 | 230 | 237 | 244 | 251 | 259 | 267 | 275 | 282 | 290 | 298 | 305 | 313 | 319 | 325 | 331 | 336 | 344 | 352 | 360 | 366 | 372 | 377 | 384 | 392 | 397 | 404 | 412 | 419 | 426 | 433 | 441 | 449 | 456 | 464 | 470 | 475 | 482 | 489 | 494 | 502 | 509 | 514 | 519 | 527 | 532 | 540 | 545 | 553 | 558 | 566 | 574 | 582 | 587 | 592 | 597 | 605 | 612 | 619 | 624 | 630 | 635 | 642 | 649 | 654 | 661 | 668 | 673 | 679 | 685
427 | 1.7294 | 13 | 39 | 65 | 109 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 2 | 6 | 10 | 17 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 6 | 14 | 21 | 29 | 35 | 43 | 48 | 53 | 60 | 67 | 72 | 78 | 83 | 89 | 95 | 103 | 109 | 114 | 121 | 129 | 136 | 144 | 152 | 158 | 164 | 172 | 178 | 186 | 194 | 199 | 204 | 210 | 215 | 220 | 226 | 231 | 239 | 247 | 254 | 261 | 266 | 271 | 277 | 282 | 289 | 296 | 302 | 309 | 317 | 323 | 330 | 338 | 346 | 351 | 358 | 366 | 371 | 377 | 384 | 389 | 394 | 399 | 406 | 414 | 419 | 427 | 432 | 438 | 445 | 453 | 458 | 463 | 468 | 475 | 482 | 489 | 495 | 502 | 509 | 515 | 523 | 531 | 536 | 542 | 549 | 556 | 561 | 567 | 573 | 578 | 585 | 590 | 595 | 603 | 608 | 613 | 618 | 623 | 630 | 636 | 642 | 650 | 657 | 662
428 | 1.4054 | 8 | 23 | 46 | 84 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 1 | 4 | 7 | 12 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 8 | 14 | 20 | 28 | 35 | 43 | 51 | 58 | 64 | 71 | 78 | 86 | 92 | 98 | 105 | 113 | 120 | 126 | 132 | 140 | 148 | 155 | 161 | 167 | 175 | 182 | 189 | 197 | 203 | 209 | 215 | 222 | 229 | 235 | 243 | 248 | 254 | 261 | 269 | 274 | 282 | 288 | 295 | 300 | 306 | 311 | 317 | 323 | 328 | 334 | 341 | 346 | 354 | 359 | 366 | 371 | 376 | 382 | 389 | 396 | 404 | 410 | 417 | 423 | 428 | 434 | 442 | 447 | 453 | 458 | 465 | 470 | 476 | 481 | 488 | 496 | 503 | 509 | 514 | 519 | 524 | 529 | 534 | 541 | 546 | 552 | 557 | 565 | 573 | 581 | 589 | 596 | 604 | 611 | 619 | 625 | 633 | 641 | 647 | 652 | 658 | 664 | 670 | 675
429 | 1.9503 | 20 | 42 | 78 | 125 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 4 | 7 | 12 | 19 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 5 | 10 | 16 | 24 | 31 | 39 | 45 | 53 | 59 | 65 | 71 | 79 | 85 | 92 | 97 | 104 | 110 | 118 | 125 | 132 | 138 | 145 | 150 | 156 | 162 | 169 | 177 | 182 | 187 | 194 | 202 | 207 | 215 | 221 | 227 | 233 | 241 | 246 | 252 | 259 | 267 | 272 | 279 | 286 | 292 | 300 | 307 | 312 | 320 | 327 | 335 | 340 | 345 | 352 | 360 | 365 | 371 | 378 | 384 | 389 | 397 | 402 | 409 | 416 | 421 | 429 | 435 | 441 | 448 | 455 | 463 | 468 | 473 | 480 | 488 | 496 | 503 | 511 | 518 | 523 | 530 | 538 | 543 | 549 | 555 | 560 | 567 | 575 | 582 | 590 | 595 | 601 | 609 | 616 | 623 | 631 | 637 | 642 | 650 | 658 | 663 | 670 | 678 | 684
430 | 1.2921 | 8 | 24 | 54 | 93 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 2 | 4 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 12 | 19 | 27 | 34 | 40 | 48 | 53 | 58 | 66 | 72 | 80 | 88 | 95 | 100 | 107 | 112 | 118 | 126 | 133 | 141 | 146 | 151 | 159 | 167 | 172 | 177 | 183 | 189 | 197 | 204 | 211 | 217 | 225 | 230 | 238 | 244 | 249 | 255 | 260 | 265 | 271 | 278 | 285 | 292 | 297 | 302 | 307 | 312 | 320 | 327 | 333 | 340 | 345 | 353 | 358 | 364 | 369 | 377 | 385 | 392 | 397 | 403 | 410 | 417 | 424 | 431 | 439 | 444 | 450 | 458 | 463 | 468 | 476 | 483 | 491 | 496 | 501 | 508 | 516 | 524 | 529 | 537 | 542 | 550 | 555 | 561 | 566 | 573 | 579 | 586 | 594 | 600 | 605 | 612 | 618 | 623 | 629 | 634 | 641 | 648 | 655 | 662 | 669
431 | 1.0523 | 7 | 21 | 45 | 73 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 1 | 3 | 7 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 15 | 22 | 30 | 37 | 44 | 50 | 58 | 63 | 70 | 77 | 85 | 90 | 95 | 101 | 108 | 116 | 122 | 127 | 132 | 137 | 142 | 147 | 153 | 159 | 167 | 172 | 177 | 185 | 193 | 201 | 208 | 216 | 221 | 227 | 232 | 240 | 246 | 252 | 258 | 264 | 270 | 275 | 282 | 289 | 294 | 302 | 310 | 315 | 320 | 326 | 334 | 339 | 344 | 350 | 358 | 365 | 371 | 379 | 387 | 394 | 399 | 406 | 413 | 418 | 425 | 432 | 439 | 447 | 452 | 457 | 462 | 470 | 478 | 483 | 489 | 495 | 502 | 510 | 518 | 523 | 530 | 535 | 540 | 547 | 555 | 563 | 570 | 576 | 583 | 590 | 595 | 601 | 606 | 611 | 618 | 626 | 634 | 641 | 648 | 654 | 660 | 668 | 674
432 | 1.3879 | 9 | 25 | 49 | 88 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 4 | 8 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 12 | 19 | 25 | 33 | 40 | 47 | 55 | 62 | 70 | 75 | 83 | 90 | 98 | 103 | 111 | 117 | 125 | 131 | 139 | 147 | 155 | 161 | 168 | 176 | 182 | 190 | 195 | 203 | 210 | 218 | 224 | 230 | 238 | 243 | 248 | 254 | 260 | 265 | 271 | 279 | 287 | 292 | 300 | 305 | 312 | 317 | 325 | 331 | 339 | 346 | 352 | 359 | 365 | 372 | 378 | 386 | 391 | 399 | 406 | 411 | 418 | 423 | 430 | 437 | 444 | 451 | 459 | 466 | 473 | 479 | 484 | 490 | 497 | 504 | 510 | 515 | 521 | 526 | 532 | 540 | 547 | 552 | 559 | 564 | 569 | 575 | 581 | 586 | 593 | 600 | 605 | 611 | 617 | 625 | 630 | 636 | 642 | 648 | 656 | 662 | 669 | 676 | 681
433 | 1.2041 | 7 | 24 | 49 | 82 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 1 | 4 | 8 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 12 | 20 | 26 | 33 | 39 | 47 | 55 | 61 | 68 | 75 | 83 | 89 | 94 | 101 | 109 | 114 | 121 | 129 | 135 | 143 | 151 | 159 | 164 | 170 | 176 | 181 | 188 | 193 | 199 | 204 | 211 | 219 | 224 | 231 | 237 | 242 | 250 | 258 | 265 | 272 | 278 | 283 | 288 | 295 | 300 | 307 | 313 | 320 | 325 | 333 | 341 | 349 | 354 | 361 | 367 | 374 | 379 | 387 | 394 | 401 | 408 | 416 | 421 | 426 | 432 | 437 | 443 | 449 | 454 | 461 | 467 | 475 | 483 | 488 | 494 | 500 | 506 | 513 | 518 | 524 | 532 | 540 | 547 | 554 | 561 | 567 | 574 | 579 | 585 | 593 | 599 | 607 | 614 | 621 | 629 | 636 | 644 | 650 | 655 | 661 | 669 | 674 | 679
434 | 1.4779 | 14 | 28 | 64 | 106 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 3 | 5 | 10 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 13 | 19 | 26 | 32 | 39 | 44 | 52 | 57 | 65 | 70 | 77 | 85 | 91 | 98 | 105 | 112 | 120 | 126 | 131 | 138 | 144 | 151 | 159 | 166 | 171 | 177 | 182 | 190 | 198 | 206 | 212 | 220 | 227 | 235 | 241 | 246 | 252 | 259 | 266 | 272 | 280 | 286 | 293 | 299 | 304 | 311 | 318 | 324 | 329 | 337 | 344 | 349 | 355 | 361 | 366 | 374 | 381 | 389 | 395 | 401 | 409 | 415 | 423 | 430 | 436 | 444 | 452 | 460 | 468 | 474 | 482 | 488 | 496 | 502 | 510 | 515 | 520 | 526 | 533 | 541 | 546 | 553 | 560 | 566 | 574 | 581 | 589 | 595 | 602 | 609 | 614 | 622 | 627 | 634 | 641 | 647 | 652 | 659 | 666 | 671 | 676 | 683 | 691
435 | 1.9953 | 16 | 36 | 86 | 142 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 3 | 6 | 13 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 7 | 15 | 20 | 28 | 35 | 43 | 51 | 58 | 64 | 70 | 78 | 85 | 92 | 98 | 105 | 111 | 118 | 124 | 131 | 139 | 147 | 155 | 162 | 167 | 173 | 178 | 185 | 191 | 199 | 207 | 213 | 220 | 227 | 235 | 242 | 250 | 258 | 265 | 272 | 278 | 283 | 289 | 297 | 303 | 308 | 314 | 320 | 325 | 333 | 338 | 343 | 350 | 356 | 362 | 369 | 376 | 384 | 392 | 400 | 408 | 416 | 422 | 429 | 437 | 442 | 447 | 452 | 458 | 463 | 468 | 474 | 481 | 489 | 496 | 502 | 508 | 515 | 520 | 525 | 533 | 539 | 544 | 550 | 558 | 563 | 570 | 578 | 584 | 592 | 597 | 604 | 610 | 616 | 621 | 628 | 636 | 641 | 648 | 656 | 663 | 668 | 676 | 683 | 691
436 | 1.9762 | 18 | 40 | 84 | 130 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 3 | 7 | 14 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 7 | 13 | 19 | 24 | 29 | 36 | 44 | 51 | 58 | 63 | 69 | 77 | 83 | 90 | 98 | 105 | 113 | 118 | 123 | 130 | 136 | 144 | 152 | 157 | 162 | 167 | 173 | 179 | 187 | 194 | 200 | 207 | 212 | 218 | 226 | 234 | 239 | 245 | 250 | 255 | 260 | 268 | 274 | 281 | 286 | 291 | 298 | 303 | 309 | 316 | 321 | 327 | 334 | 339 | 345 | 350 | 357 | 364 | 369 | 377 | 383 | 389 | 394 | 399 | 406 | 414 | 422 | 427 | 434 | 442 | 449 | 454 | 461 | 468 | 473 | 478 | 486 | 491 | 496 | 501 | 507 | 515 | 521 | 527 | 532 | 540 | 547 | 552 | 558 | 563 | 571 | 576 | 584 | 592 | 598 | 605 | 610 | 616 | 621 | 626 | 634 | 642 | 647 | 653
437 | 1.9811 | 12 | 42 | 78 | 126 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 2 | 7 | 13 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 7 | 15 | 21 | 27 | 33 | 40 | 45 | 51 | 56 | 64 | 69 | 75 | 82 | 87 | 93 | 98 | 106 | 112 | 120 | 126 | 132 | 138 | 145 | 150 | 156 | 161 | 166 | 172 | 177 | 185 | 192 | 199 | 206 | 212 | 218 | 224 | 232 | 239 | 245 | 251 | 258 | 266 | 273 | 281 | 286 | 291 | 296 | 304 | 309 | 314 | 320 | 328 | 335 | 341 | 348 | 355 | 363 | 368 | 376 | 383 | 389 | 397 | 403 | 409 | 416 | 421 | 429 | 436 | 444 | 450 | 456 | 464 | 470 | 475 | 482 | 490 | 498 | 505 | 510 | 516 | 522 | 530 | 537 | 544 | 549 | 556 | 561 | 568 | 576 | 583 | 589 | 596 | 603 | 609 | 615 | 620 | 625 | 633 | 641 | 646 | 653 | 660 | 667 | 672
438 | 1.6712 | 16 | 37 | 79 | 128 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 3 | 7 | 13 | 21 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 11 | 18 | 23 | 29 | 36 | 43 | 48 | 53 | 61 | 68 | 73 | 81 | 86 | 91 | 98 | 104 | 109 | 115 | 122 | 128 | 133 | 139 | 144 | 149 | 154 | 162 | 170 | 175 | 181 | 188 | 196 | 201 | 206 | 212 | 220 | 225 | 233 | 241 | 248 | 254 | 260 | 265 | 272 | 279 | 285 | 290 | 295 | 302 | 307 | 315 | 322 | 328 | 336 | 341 | 347 | 353 | 358 | 366 | 372 | 377 | 382 | 387 | 395 | 403 | 411 | 419 | 426 | 432 | 440 | 447 | 454 | 459 | 464 | 472 | 477 | 483 | 490 | 498 | 504 | 510 | 518 | 523 | 528 | 535 | 540 | 547 | 553 | 561 | 566 | 573 | 580 | 585 | 590 | 598 | 604 | 610 | 618 | 625 | 633 | 640 | 645 | 652 | 659
439 | 1.0857 | 10 | 19 | 39 | 66 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 3 | 6 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 15 | 21 | 28 | 34 | 41 | 47 | 54 | 60 | 67 | 73 | 80 | 87 | 94 | 100 | 107 | 112 | 118 | 126 | 131 | 137 | 144 | 152 | 158 | 164 | 171 | 177 | 183 | 188 | 195 | 203 | 210 | 217 | 223 | 230 | 236 | 244 | 250 | 255 | 260 | 267 | 273 | 281 | 286 | 293 | 300 | 305 | 313 | 320 | 326 | 331 | 338 | 345 | 352 | 357 | 363 | 371 | 377 | 382 | 390 | 397 | 403 | 409 | 415 | 421 | 428 | 434 | 441 | 447 | 452 | 457 | 462 | 469 | 477 | 485 | 492 | 498 | 504 | 511 | 517 | 523 | 531 | 539 | 545 | 550 | 557 | 564 | 572 | 580 | 586 | 593 | 601 | 606 | 613 | 621 | 627 | 635 | 642 | 650 | 657 | 664 | 672 | 680 | 686
440 | 1.2262 | 8 | 27 | 48 | 77 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 2 | 5 | 8 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 7 | 12 | 20 | 25 | 30 | 35 | 41 | 49 | 56 | 62 | 69 | 76 | 82 | 90 | 97 | 103 | 111 | 119 | 125 | 131 | 138 | 144 | 151 | 158 | 163 | 169 | 174 | 181 | 189 | 195 | 203 | 208 | 213 | 218 | 224 | 230 | 238 | 244 | 252 | 258 | 265 | 271 | 278 | 283 | 288 | 293 | 300 | 308 | 313 | 319 | 324 | 331 | 339 | 345 | 350 | 356 | 361 | 368 | 375 | 380 | 388 | 393 | 399 | 405 | 411 | 417 | 422 | 428 | 433 | 438 | 444 | 452 | 457 | 465 | 470 | 476 | 483 | 489 | 495 | 503 | 509 | 514 | 521 | 528 | 534 | 540 | 545 | 552 | 558 | 566 | 571 | 578 | 584 | 589 | 594 | 600 | 607 | 615 | 620 | 625 | 631 | 637 | 642 | 648
441 | 1.1509 | 10 | 21 | 48 | 77 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 2 | 4 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 12 | 18 | 24 | 32 | 37 | 43 | 49 | 55 | 60 | 67 | 72 | 80 | 85 | 90 | 95 | 101 | 108 | 115 | 120 | 125 | 132 | 140 | 145 | 151 | 159 | 166 | 171 | 178 | 184 | 190 | 198 | 204 | 209 | 217 | 224 | 231 | 239 | 245 | 251 | 256 | 262 | 269 | 276 | 281 | 289 | 295 | 300 | 307 | 313 | 319 | 324 | 330 | 338 | 345 | 352 | 359 | 364 | 372 | 380 | 386 | 391 | 399 | 407 | 415 | 421 | 426 | 431 | 438 | 445 | 451 | 456 | 462 | 469 | 475 | 482 | 489 | 497 | 502 | 508 | 516 | 521 | 528 | 533 | 538 | 545 | 553 | 561 | 568 | 573 | 581 | 587 | 592 | 599 | 604 | 612 | 618 | 626 | 632 | 639 | 645 | 651 | 657 | 662
442 | 1.3238 | 14 | 28 | 59 | 87 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 2 | 4 | 9 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 15 | 22 | 30 | 38 | 43 | 48 | 53 | 59 | 66 | 73 | 80 | 85 | 92 | 99 | 105 | 111 | 116 | 123 | 128 | 134 | 139 | 144 | 152 | 159 | 165 | 170 | 177 | 185 | 193 | 199 | 205 | 211 | 217 | 222 | 230 | 236 | 242 | 247 | 253 | 260 | 268 | 276 | 282 | 289 | 297 | 302 | 307 | 314 | 322 | 329 | 337 | 342 | 347 | 355 | 360 | 368 | 373 | 381 | 388 | 396 | 403 | 410 | 417 | 423 | 430 | 436 | 442 | 449 | 456 | 463 | 471 | 479 | 487 | 493 | 501 | 509 | 516 | 521 | 527 | 533 | 539 | 546 | 552 | 559 | 565 | 572 | 579 | 586 | 593 | 601 | 608 | 614 | 619 | 626 | 631 | 637 | 642 | 647 | 653 | 658 | 664 | 672 | 679
443 | 1.8953 | 14 | 41 | 83 | 125 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 169 | 2 | 6 | 12 | 19 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 6 | 14 | 21 | 29 | 37 | 42 | 50 | 57 | 65 | 73 | 78 | 84 | 90 | 96 | 104 | 109 | 114 | 120 | 126 | 131 | 137 | 143 | 149 | 155 | 160 | 168 | 173 | 178 | 184 | 191 | 197 | 202 | 208 | 216 | 221 | 228 | 233 | 241 | 248 | 254 | 262 | 267 | 272 | 277 | 284 | 290 | 295 | 301 | 308 | 316 | 323 | 330 | 337 | 342 | 348 | 353 | 358 | 365 | 373 | 378 | 386 | 391 | 399 | 406 | 413 | 420 | 428 | 434 | 442 | 447 | 453 | 459 | 467 | 473 | 478 | 483 | 490 | 496 | 501 | 506 | 513 | 520 | 526 | 534 | 540 | 548 | 556 | 562 | 569 | 574 | 581 | 586 | 591 | 596 | 603 | 610 | 616 | 622 | 629 | 635 | 641 | 648 | 655 | 663
444 | 1.5384 | 10 | 27 | 51 | 91 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 2 | 4 | 8 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 14 | 22 | 30 | 37 | 42 | 48 | 53 | 59 | 65 | 73 | 78 | 84 | 91 | 96 | 104 | 109 | 114 | 121 | 127 | 132 | 139 | 146 | 151 | 159 | 164 | 170 | 177 | 185 | 193 | 201 | 206 | 212 | 218 | 225 | 233 | 238 | 244 | 249 | 256 | 264 | 270 | 277 | 284 | 292 | 297 | 305 | 310 | 317 | 322 | 328 | 333 | 340 | 345 | 353 | 360 | 366 | 373 | 378 | 386 | 393 | 400 | 405 | 413 | 418 | 426 | 432 | 440 | 445 | 450 | 457 | 463 | 468 | 475 | 483 | 489 | 495 | 500 | 505 | 511 | 519 | 526 | 534 | 541 | 546 | 553 | 561 | 566 | 574 | 580 | 587 | 595 | 603 | 611 | 617 | 623 | 629 | 634 | 640 | 647 | 652 | 658 | 666 | 674
445 | 1.0195 | 11 | 27 | 45 | 67 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 2 | 4 | 7 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 14 | 21 | 28 | 36 | 41 | 48 | 54 | 62 | 67 | 74 | 82 | 87 | 93 | 101 | 106 | 111 | 118 | 125 | 130 | 138 | 146 | 152 | 160 | 168 | 175 | 182 | 188 | 194 | 202 | 209 | 217 | 224 | 229 | 237 | 244 | 251 | 256 | 261 | 266 | 272 | 280 | 288 | 296 | 303 | 310 | 318 | 326 | 333 | 341 | 348 | 354 | 362 | 367 | 374 | 380 | 388 | 393 | 400 | 405 | 412 | 419 | 424 | 429 | 436 | 441 | 449 | 454 | 462 | 467 | 475 | 481 | 489 | 496 | 501 | 506 | 512 | 519 | 525 | 533 | 539 | 545 | 550 | 557 | 563 | 569 | 575 | 582 | 587 | 594 | 602 | 607 | 613 | 621 | 626 | 633 | 638 | 644 | 650 | 657 | 662 | 670 | 675 | 683
446 | 1.3288 | 7 | 19 | 50 | 90 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 1 | 3 | 7 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 14 | 22 | 30 | 35 | 42 | 50 | 55 | 63 | 69 | 77 | 83 | 88 | 95 | 101 | 108 | 114 | 122 | 130 | 135 | 140 | 145 | 151 | 157 | 165 | 171 | 177 | 185 | 190 | 198 | 205 | 210 | 215 | 221 | 229 | 236 | 241 | 246 | 254 | 262 | 270 | 275 | 281 | 289 | 297 | 305 | 310 | 316 | 323 | 330 | 335 | 343 | 351 | 359 | 366 | 371 | 377 | 383 | 390 | 397 | 405 | 410 | 416 | 423 | 428 | 433 | 441 | 446 | 454 | 461 | 467 | 475 | 480 | 485 | 490 | 495 | 501 | 509 | 515 | 521 | 528 | 536 | 543 | 549 | 554 | 559 | 566 | 574 | 581 | 588 | 596 | 601 | 608 | 613 | 619 | 624 | 632 | 640 | 647 | 654 | 661 | 666 | 674 | 681
447 | 1.2016 | 7 | 17 | 37 | 69 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 1 | 3 | 6 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 15 | 20 | 27 | 35 | 41 | 46 | 51 | 56 | 62 | 70 | 75 | 83 | 89 | 97 | 104 | 110 | 116 | 123 | 130 | 136 | 143 | 151 | 159 | 167 | 174 | 182 | 190 | 196 | 201 | 206 | 213 | 218 | 224 | 231 | 236 | 243 | 250 | 256 | 262 | 269 | 276 | 284 | 290 | 297 | 302 | 309 | 315 | 322 | 329 | 337 | 343 | 349 | 354 | 361 | 366 | 372 | 380 | 388 | 396 | 401 | 406 | 414 | 421 | 429 | 437 | 443 | 449 | 455 | 460 | 466 | 471 | 477 | 483 | 490 | 496 | 503 | 509 | 514 | 522 | 528 | 535 | 543 | 551 | 557 | 565 | 570 | 576 | 584 | 592 | 597 | 602 | 608 | 613 | 621 | 628 | 634 | 642 | 649 | 656 | 664 | 672 | 679 | 684
448 | 1.8982 | 14 | 41 | 79 | 123 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 3 | 6 | 12 | 19 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 7 | 13 | 21 | 28 | 35 | 43 | 50 | 55 | 62 | 67 | 75 | 83 | 91 | 96 | 102 | 107 | 114 | 122 | 127 | 132 | 140 | 147 | 155 | 162 | 170 | 177 | 183 | 189 | 195 | 201 | 209 | 216 | 223 | 229 | 236 | 244 | 251 | 257 | 264 | 270 | 278 | 283 | 290 | 295 | 300 | 306 | 314 | 321 | 327 | 332 | 338 | 345 | 353 | 358 | 365 | 373 | 378 | 383 | 388 | 394 | 400 | 406 | 413 | 421 | 427 | 433 | 438 | 446 | 452 | 459 | 465 | 470 | 477 | 482 | 490 | 496 | 501 | 509 | 514 | 519 | 527 | 534 | 540 | 546 | 551 | 557 | 563 | 570 | 577 | 584 | 590 | 596 | 604 | 610 | 617 | 622 | 630 | 636 | 643 | 651 | 656 | 664 | 669 | 674
449 | 1.6371 | 14 | 33 | 58 | 99 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 3 | 6 | 10 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 6 | 12 | 19 | 27 | 32 | 38 | 43 | 51 | 57 | 63 | 68 | 75 | 81 | 89 | 96 | 102 | 108 | 114 | 121 | 127 | 132 | 139 | 144 | 152 | 158 | 163 | 168 | 175 | 182 | 189 | 194 | 201 | 208 | 215 | 221 | 228 | 235 | 243 | 248 | 255 | 263 | 271 | 279 | 287 | 294 | 301 | 307 | 314 | 321 | 329 | 337 | 343 | 349 | 357 | 365 | 373 | 381 | 387 | 395 | 402 | 408 | 413 | 418 | 424 | 432 | 440 | 446 | 451 | 456 | 462 | 468 | 474 | 479 | 484 | 492 | 497 | 503 | 509 | 517 | 522 | 529 | 535 | 543 | 550 | 558 | 565 | 573 | 580 | 586 | 592 | 599 | 607 | 613 | 620 | 628 | 634 | 642 | 647 | 655 | 663 | 671 | 678 | 683 | 690
450 | 1.8904 | 14 | 39 | 85 | 127 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 3 | 6 | 13 | 19 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 5 | 13 | 21 | 29 | 34 | 39 | 47 | 54 | 59 | 67 | 75 | 83 | 88 | 94 | 101 | 109 | 115 | 122 | 127 | 135 | 142 | 147 | 155 | 161 | 168 | 173 | 180 | 185 | 192 | 199 | 204 | 210 | 216 | 224 | 232 | 239 | 246 | 252 | 259 | 266 | 273 | 278 | 283 | 291 | 298 | 303 | 311 | 319 | 327 | 332 | 338 | 346 | 354 | 360 | 366 | 372 | 379 | 385 | 391 | 399 | 404 | 409 | 416 | 423 | 430 | 437 | 443 | 451 | 456 | 461 | 468 | 473 | 481 | 486 | 492 | 498 | 506 | 514 | 521 | 527 | 535 | 540 | 545 | 552 | 559 | 566 | 574 | 582 | 590 | 598 | 605 | 611 | 616 | 622 | 629 | 636 | 641 | 649 | 654 | 660 | 666 | 672 | 679 | 684
451 | 1.5254 | 16 | 32 | 60 | 102 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 3 | 5 | 9 | 16 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 15 | 23 | 31 | 36 | 43 | 49 | 54 | 60 | 67 | 72 | 77 | 85 | 91 | 96 | 102 | 109 | 114 | 120 | 128 | 134 | 139 | 144 | 149 | 155 | 162 | 170 | 178 | 183 | 189 | 195 | 203 | 211 | 218 | 226 | 234 | 242 | 247 | 254 | 262 | 267 | 273 | 280 | 287 | 294 | 302 | 309 | 315 | 322 | 327 | 333 | 340 | 348 | 355 | 360 | 366 | 372 | 378 | 384 | 390 | 395 | 400 | 408 | 414 | 421 | 427 | 433 | 441 | 447 | 455 | 460 | 468 | 475 | 483 | 488 | 494 | 500 | 506 | 511 | 516 | 524 | 529 | 535 | 541 | 549 | 555 | 563 | 568 | 575 | 581 | 588 | 593 | 598 | 605 | 613 | 619 | 625 | 633 | 640 | 648 | 656 | 663 | 670 | 675
452 | 1.6572 | 12 | 37 | 64 | 104 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 2 | 6 | 10 | 16 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 12 | 19 | 27 | 33 | 39 | 45 | 52 | 59 | 66 | 73 | 80 | 88 | 93 | 99 | 106 | 114 | 120 | 128 | 136 | 144 | 150 | 156 | 161 | 167 | 175 | 182 | 187 | 195 | 201 | 208 | 216 | 222 | 229 | 235 | 242 | 249 | 256 | 262 | 268 | 274 | 279 | 286 | 292 | 300 | 305 | 311 | 316 | 323 | 329 | 336 | 344 | 352 | 359 | 367 | 373 | 379 | 385 | 392 | 397 | 402 | 408 | 414 | 420 | 425 | 433 | 441 | 447 | 455 | 462 | 467 | 474 | 480 | 486 | 493 | 501 | 508 | 514 | 522 | 530 | 536 | 541 | 546 | 554 | 559 | 567 | 573 | 580 | 585 | 592 | 598 | 604 | 609 | 617 | 624 | 630 | 637 | 643 | 650 | 657 | 663 | 670 | 675 | 680
453 | 1.1523 | 6 | 24 | 50 | 75 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 1 | 4 | 7 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 14 | 22 | 29 | 35 | 43 | 50 | 55 | 63 | 68 | 74 | 81 | 89 | 95 | 102 | 108 | 114 | 121 | 127 | 134 | 140 | 147 | 154 | 159 | 164 | 172 | 180 | 185 | 190 | 196 | 204 | 212 | 217 | 224 | 229 | 234 | 241 | 249 | 255 | 263 | 269 | 276 | 281 | 288 | 296 | 303 | 311 | 317 | 323 | 328 | 334 | 339 | 345 | 353 | 360 | 366 | 372 | 377 | 382 | 387 | 395 | 402 | 408 | 413 | 418 | 423 | 431 | 438 | 446 | 453 | 461 | 466 | 474 | 482 | 488 | 494 | 500 | 505 | 512 | 520 | 528 | 536 | 541 | 549 | 557 | 565 | 571 | 579 | 587 | 595 | 602 | 609 | 617 | 624 | 629 | 634 | 639 | 645 | 651 | 656 | 661 | 668 | 673 | 680
454 | 1.7048 | 11 | 25 | 58 | 103 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 139 | 2 | 4 | 10 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 13 | 18 | 25 | 30 | 36 | 43 | 51 | 57 | 65 | 71 | 79 | 87 | 94 | 99 | 107 | 115 | 120 | 126 | 134 | 139 | 145 | 152 | 158 | 163 | 168 | 173 | 181 | 188 | 194 | 199 | 207 | 212 | 217 | 223 | 230 | 237 | 244 | 249 | 256 | 264 | 270 | 276 | 283 | 289 | 294 | 299 | 307 | 314 | 320 | 328 | 335 | 343 | 350 | 356 | 363 | 370 | 378 | 386 | 392 | 399 | 405 | 413 | 418 | 425 | 430 | 436 | 441 | 447 | 453 | 458 | 466 | 472 | 479 | 484 | 490 | 496 | 502 | 509 | 514 | 520 | 528 | 536 | 541 | 547 | 554 | 559 | 566 | 572 | 577 | 582 | 587 | 592 | 597 | 603 | 610 | 618 | 623 | 631 | 638 | 644 | 650 | 656 | 662
455 | 1.1447 | 10 | 27 | 52 | 87 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 2 | 5 | 9 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 11 | 16 | 21 | 27 | 35 | 42 | 48 | 55 | 63 | 71 | 78 | 86 | 91 | 96 | 102 | 110 | 116 | 122 | 127 | 135 | 140 | 147 | 152 | 159 | 167 | 174 | 181 | 189 | 194 | 200 | 207 | 214 | 219 | 224 | 230 | 236 | 243 | 251 | 256 | 263 | 270 | 276 | 284 | 289 | 296 | 303 | 308 | 315 | 321 | 328 | 336 | 342 | 348 | 356 | 362 | 368 | 375 | 382 | 387 | 395 | 400 | 407 | 413 | 419 | 427 | 434 | 440 | 447 | 455 | 462 | 469 | 474 | 480 | 488 | 494 | 499 | 504 | 509 | 516 | 521 | 529 | 535 | 540 | 546 | 552 | 560 | 568 | 575 | 581 | 586 | 594 | 602 | 610 | 615 | 622 | 629 | 636 | 642 | 649 | 657 | 663 | 669 | 675
456 | 1.2043 | 9 | 26 | 53 | 82 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 2 | 4 | 9 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 14 | 21 | 27 | 32 | 37 | 43 | 48 | 53 | 58 | 66 | 71 | 79 | 86 | 93 | 101 | 106 | 114 | 120 | 126 | 132 | 139 | 145 | 153 | 159 | 166 | 172 | 178 | 183 | 188 | 195 | 202 | 208 | 216 | 222 | 230 | 237 | 244 | 250 | 255 | 260 | 265 | 270 | 276 | 281 | 287 | 294 | 299 | 307 | 313 | 321 | 329 | 337 | 343 | 348 | 356 | 363 | 370 | 377 | 384 | 392 | 398 | 403 | 409 | 414 | 422 | 427 | 433 | 441 | 448 | 455 | 461 | 467 | 474 | 479 | 486 | 492 | 497 | 505 | 511 | 518 | 525 | 533 | 539 | 544 | 549 | 557 | 562 | 568 | 574 | 582 | 590 | 596 | 603 | 610 | 617 | 624 | 629 | 637 | 644 | 652 | 660 | 668 | 673
457 | 1.9231 | 10 | 37 | 84 | 133 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 199 | 2 | 6 | 12 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 8 | 14 | 19 | 25 | 30 | 38 | 45 | 52 | 60 | 68 | 76 | 84 | 90 | 98 | 104 | 112 | 119 | 127 | 133 | 138 | 143 | 150 | 158 | 166 | 173 | 180 | 188 | 196 | 203 | 211 | 217 | 223 | 229 | 237 | 245 | 253 | 258 | 266 | 272 | 279 | 284 | 292 | 298 | 306 | 313 | 321 | 327 | 333 | 338 | 346 | 352 | 360 | 368 | 376 | 383 | 391 | 399 | 405 | 410 | 417 | 424 | 430 | 436 | 444 | 451 | 457 | 462 | 469 | 475 | 483 | 491 | 498 | 505 | 511 | 518 | 525 | 533 | 540 | 547 | 554 | 561 | 569 | 576 | 584 | 590 | 598 | 606 | 614 | 621 | 629 | 636 | 642 | 649 | 657 | 665 | 673 | 678 | 686 | 691 | 698 | 706 | 711 | 718 | 724
458 | 1.5874 | 13 | 36 | 63 | 100 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 2 | 6 | 12 | 17 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 13 | 18 | 24 | 31 | 36 | 42 | 47 | 52 | 57 | 62 | 70 | 76 | 81 | 88 | 95 | 100 | 105 | 111 | 118 | 124 | 132 | 139 | 145 | 152 | 160 | 168 | 175 | 182 | 187 | 194 | 200 | 207 | 213 | 220 | 227 | 235 | 241 | 248 | 254 | 260 | 265 | 272 | 278 | 283 | 288 | 293 | 298 | 306 | 314 | 319 | 327 | 335 | 340 | 345 | 350 | 356 | 364 | 371 | 376 | 384 | 392 | 400 | 407 | 413 | 420 | 427 | 434 | 440 | 446 | 453 | 461 | 469 | 474 | 480 | 485 | 492 | 499 | 504 | 510 | 516 | 523 | 528 | 536 | 544 | 549 | 555 | 562 | 568 | 574 | 579 | 584 | 590 | 598 | 606 | 611 | 616 | 624 | 629 | 634 | 641 | 647 | 654 | 662
459 | 1.6264 | 12 | 26 | 56 | 94 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 2 | 4 | 9 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 6 | 13 | 20 | 28 | 33 | 41 | 47 | 53 | 59 | 64 | 69 | 76 | 83 | 91 | 96 | 103 | 111 | 116 | 122 | 129 | 136 | 143 | 148 | 156 | 163 | 169 | 176 | 182 | 189 | 196 | 203 | 211 | 216 | 222 | 229 | 234 | 241 | 247 | 253 | 260 | 267 | 273 | 281 | 286 | 293 | 299 | 304 | 312 | 320 | 325 | 331 | 338 | 345 | 350 | 356 | 362 | 369 | 376 | 384 | 390 | 396 | 404 | 412 | 420 | 425 | 432 | 438 | 444 | 452 | 460 | 468 | 473 | 479 | 485 | 492 | 497 | 502 | 509 | 514 | 521 | 527 | 534 | 541 | 548 | 555 | 562 | 569 | 574 | 579 | 585 | 593 | 600 | 605 | 610 | 616 | 622 | 627 | 632 | 639 | 645 | 651 | 658 | 663 | 671
460 | 1.3309 | 14 | 34 | 68 | 102 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 2 | 6 | 11 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 14 | 21 | 27 | 32 | 37 | 45 | 50 | 57 | 64 | 72 | 78 | 85 | 93 | 98 | 106 | 114 | 121 | 128 | 133 | 138 | 144 | 151 | 159 | 164 | 172 | 177 | 184 | 189 | 194 | 200 | 207 | 215 | 220 | 226 | 232 | 237 | 245 | 253 | 261 | 267 | 275 | 280 | 288 | 295 | 300 | 306 | 313 | 321 | 326 | 331 | 338 | 345 | 352 | 357 | 362 | 368 | 375 | 383 | 389 | 396 | 403 | 408 | 415 | 420 | 428 | 435 | 440 | 445 | 453 | 458 | 466 | 474 | 482 | 489 | 494 | 501 | 507 | 512 | 518 | 524 | 530 | 536 | 541 | 549 | 555 | 562 | 567 | 572 | 579 | 585 | 590 | 595 | 600 | 606 | 614 | 620 | 627 | 634 | 640 | 647 | 653 | 660 | 668
461 | 1.3274 | 14 | 26 | 49 | 83 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 3 | 4 | 7 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 8 | 13 | 19 | 27 | 35 | 42 | 49 | 54 | 59 | 64 | 69 | 75 | 80 | 87 | 93 | 100 | 107 | 115 | 121 | 127 | 133 | 140 | 145 | 151 | 159 | 165 | 170 | 178 | 186 | 191 | 198 | 206 | 213 | 220 | 228 | 233 | 239 | 246 | 251 | 257 | 262 | 270 | 278 | 283 | 289 | 294 | 302 | 308 | 316 | 323 | 331 | 336 | 341 | 346 | 353 | 359 | 366 | 373 | 381 | 387 | 395 | 402 | 410 | 417 | 425 | 430 | 435 | 440 | 445 | 453 | 458 | 463 | 471 | 478 | 483 | 488 | 494 | 500 | 507 | 512 | 519 | 527 | 535 | 541 | 546 | 551 | 558 | 563 | 568 | 573 | 578 | 585 | 591 | 597 | 605 | 613 | 620 | 625 | 630 | 635 | 641 | 649 | 657 | 664
462 | 1.4906 | 9 | 24 | 59 | 89 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 2 | 4 | 9 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 5 | 13 | 20 | 26 | 32 | 40 | 45 | 53 | 61 | 69 | 77 | 84 | 89 | 97 | 105 | 111 | 117 | 124 | 130 | 138 | 144 | 152 | 157 | 163 | 171 | 177 | 185 | 193 | 199 | 206 | 212 | 219 | 226 | 232 | 237 | 244 | 249 | 255 | 262 | 269 | 274 | 280 | 287 | 295 | 300 | 306 | 314 | 322 | 328 | 335 | 342 | 348 | 356 | 362 | 368 | 374 | 382 | 388 | 395 | 400 | 406 | 414 | 422 | 427 | 435 | 440 | 447 | 454 | 461 | 467 | 472 | 480 | 488 | 496 | 502 | 510 | 518 | 525 | 530 | 536 | 541 | 546 | 551 | 557 | 562 | 569 | 577 | 583 | 589 | 596 | 602 | 608 | 615 | 622 | 629 | 634 | 641 | 648 | 653 | 658 | 665 | 673 | 680 | 686
463 | 1.4311 | 8 | 30 | 56 | 92 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 2 | 5 | 10 | 15 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 7 | 13 | 19 | 24 | 31 | 38 | 44 | 49 | 55 | 60 | 67 | 75 | 80 | 85 | 93 | 100 | 108 | 113 | 119 | 126 | 132 | 138 | 143 | 150 | 157 | 163 | 169 | 176 | 181 | 188 | 196 | 201 | 209 | 217 | 222 | 229 | 234 | 239 | 247 | 255 | 263 | 268 | 275 | 281 | 286 | 291 | 297 | 305 | 310 | 315 | 323 | 331 | 339 | 344 | 349 | 356 | 361 | 369 | 375 | 382 | 389 | 397 | 404 | 409 | 417 | 423 | 430 | 437 | 443 | 449 | 456 | 464 | 472 | 479 | 486 | 491 | 499 | 504 | 510 | 516 | 523 | 530 | 537 | 542 | 550 | 558 | 564 | 571 | 578 | 585 | 592 | 598 | 605 | 610 | 616 | 624 | 631 | 639 | 647 | 655 | 663 | 671 | 676 | 684
464 | 1.891 | 18 | 43 | 83 | 140 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 4 | 7 | 14 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 5 | 10 | 17 | 22 | 30 | 38 | 46 | 51 | 56 | 61 | 68 | 76 | 82 | 90 | 97 | 102 | 110 | 118 | 123 | 128 | 135 | 142 | 148 | 156 | 161 | 168 | 175 | 183 | 188 | 196 | 203 | 209 | 214 | 219 | 225 | 230 | 236 | 244 | 250 | 256 | 263 | 271 | 277 | 284 | 291 | 299 | 307 | 314 | 322 | 329 | 335 | 343 | 348 | 356 | 361 | 368 | 373 | 380 | 387 | 393 | 401 | 408 | 413 | 419 | 427 | 433 | 440 | 446 | 451 | 458 | 463 | 471 | 479 | 484 | 490 | 498 | 505 | 510 | 515 | 521 | 526 | 532 | 538 | 544 | 550 | 555 | 561 | 566 | 574 | 581 | 589 | 595 | 603 | 608 | 613 | 621 | 628 | 634 | 640 | 647 | 653 | 659 | 664 | 669
465 | 1.4165 | 8 | 28 | 51 | 81 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 2 | 5 | 9 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 13 | 19 | 25 | 30 | 37 | 45 | 50 | 55 | 62 | 67 | 72 | 80 | 88 | 93 | 98 | 104 | 111 | 117 | 124 | 129 | 137 | 144 | 152 | 157 | 164 | 170 | 178 | 185 | 190 | 196 | 204 | 212 | 218 | 223 | 228 | 233 | 238 | 244 | 249 | 256 | 261 | 267 | 275 | 281 | 286 | 294 | 300 | 308 | 315 | 321 | 327 | 333 | 338 | 343 | 348 | 353 | 358 | 365 | 373 | 379 | 387 | 394 | 400 | 408 | 415 | 420 | 425 | 430 | 435 | 440 | 446 | 452 | 459 | 467 | 472 | 480 | 485 | 490 | 496 | 501 | 507 | 512 | 517 | 524 | 532 | 537 | 545 | 553 | 560 | 566 | 572 | 577 | 584 | 591 | 596 | 602 | 610 | 616 | 622 | 629 | 634 | 641 | 646
466 | 1.0893 | 8 | 22 | 49 | 77 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 2 | 4 | 7 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 13 | 21 | 29 | 35 | 43 | 50 | 55 | 62 | 70 | 75 | 80 | 86 | 93 | 98 | 105 | 111 | 116 | 121 | 128 | 134 | 139 | 144 | 149 | 156 | 162 | 170 | 177 | 183 | 189 | 194 | 201 | 208 | 213 | 220 | 226 | 232 | 238 | 244 | 250 | 257 | 263 | 268 | 275 | 282 | 288 | 293 | 298 | 306 | 313 | 321 | 328 | 334 | 342 | 349 | 355 | 360 | 367 | 375 | 381 | 387 | 392 | 399 | 405 | 410 | 415 | 420 | 427 | 433 | 440 | 448 | 454 | 459 | 466 | 472 | 477 | 482 | 489 | 496 | 501 | 507 | 515 | 520 | 528 | 535 | 543 | 549 | 557 | 562 | 568 | 575 | 580 | 585 | 592 | 598 | 603 | 610 | 615 | 621 | 629 | 635 | 643 | 650 | 658
467 | 1.4264 | 8 | 28 | 57 | 95 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 2 | 4 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 6 | 14 | 22 | 30 | 35 | 40 | 47 | 53 | 58 | 63 | 71 | 78 | 85 | 91 | 99 | 105 | 110 | 117 | 122 | 129 | 137 | 144 | 152 | 159 | 167 | 172 | 180 | 185 | 190 | 195 | 200 | 208 | 216 | 224 | 229 | 235 | 242 | 248 | 253 | 260 | 266 | 271 | 278 | 284 | 290 | 298 | 306 | 313 | 320 | 326 | 334 | 341 | 349 | 356 | 362 | 367 | 374 | 382 | 387 | 392 | 397 | 402 | 409 | 416 | 422 | 427 | 435 | 440 | 448 | 455 | 463 | 470 | 478 | 486 | 492 | 499 | 505 | 511 | 519 | 527 | 534 | 541 | 548 | 555 | 562 | 570 | 578 | 586 | 593 | 600 | 607 | 612 | 617 | 622 | 629 | 636 | 642 | 648 | 655 | 663 | 670 | 677 | 684 | 692
468 | 1.9076 | 18 | 38 | 79 | 127 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 3 | 6 | 13 | 21 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 5 | 13 | 21 | 27 | 32 | 39 | 45 | 50 | 58 | 64 | 69 | 74 | 81 | 86 | 93 | 99 | 104 | 110 | 116 | 122 | 127 | 132 | 138 | 145 | 152 | 159 | 165 | 170 | 176 | 181 | 187 | 195 | 201 | 208 | 213 | 221 | 228 | 235 | 240 | 246 | 252 | 260 | 265 | 270 | 275 | 283 | 289 | 295 | 303 | 311 | 316 | 324 | 329 | 334 | 342 | 348 | 353 | 360 | 366 | 371 | 379 | 385 | 393 | 399 | 406 | 412 | 417 | 423 | 429 | 437 | 445 | 451 | 456 | 461 | 467 | 473 | 478 | 485 | 490 | 498 | 503 | 508 | 513 | 521 | 529 | 535 | 543 | 548 | 554 | 559 | 564 | 569 | 576 | 583 | 590 | 596 | 604 | 610 | 615 | 623 | 629 | 635 | 643 | 649
469 | 1.4286 | 13 | 25 | 51 | 94 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 2 | 4 | 9 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 14 | 19 | 26 | 33 | 40 | 45 | 50 | 56 | 63 | 68 | 73 | 79 | 86 | 92 | 100 | 108 | 113 | 121 | 127 | 134 | 140 | 145 | 152 | 160 | 165 | 172 | 179 | 184 | 189 | 196 | 201 | 206 | 214 | 219 | 226 | 232 | 239 | 245 | 250 | 255 | 262 | 269 | 275 | 283 | 289 | 297 | 304 | 309 | 314 | 321 | 329 | 334 | 339 | 344 | 350 | 355 | 360 | 368 | 374 | 379 | 386 | 393 | 400 | 407 | 414 | 422 | 429 | 436 | 444 | 449 | 456 | 464 | 471 | 476 | 481 | 488 | 493 | 501 | 509 | 514 | 520 | 526 | 531 | 537 | 542 | 549 | 555 | 562 | 568 | 573 | 579 | 585 | 591 | 599 | 604 | 609 | 616 | 624 | 629 | 634 | 639 | 646 | 651
470 | 1.7497 | 13 | 29 | 71 | 120 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 2 | 5 | 12 | 19 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 6 | 13 | 20 | 28 | 33 | 39 | 46 | 51 | 57 | 62 | 70 | 78 | 84 | 90 | 98 | 104 | 109 | 117 | 124 | 129 | 134 | 139 | 146 | 154 | 161 | 168 | 175 | 183 | 190 | 197 | 202 | 210 | 215 | 222 | 229 | 235 | 240 | 245 | 253 | 261 | 268 | 273 | 281 | 288 | 293 | 299 | 307 | 313 | 321 | 326 | 332 | 337 | 343 | 350 | 356 | 361 | 368 | 373 | 381 | 389 | 394 | 402 | 408 | 414 | 422 | 429 | 435 | 442 | 447 | 454 | 462 | 469 | 475 | 480 | 486 | 491 | 499 | 505 | 513 | 519 | 527 | 535 | 541 | 547 | 552 | 557 | 562 | 567 | 574 | 580 | 587 | 595 | 603 | 610 | 616 | 623 | 630 | 636 | 643 | 651 | 658 | 665 | 673 | 680
471 | 1.1515 | 6 | 21 | 39 | 64 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 1 | 3 | 6 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 14 | 22 | 29 | 35 | 40 | 47 | 55 | 60 | 66 | 72 | 78 | 86 | 92 | 100 | 108 | 114 | 120 | 126 | 134 | 140 | 145 | 153 | 158 | 165 | 172 | 177 | 183 | 190 | 196 | 203 | 208 | 215 | 220 | 227 | 233 | 240 | 245 | 252 | 260 | 266 | 271 | 278 | 285 | 293 | 298 | 303 | 310 | 316 | 323 | 329 | 335 | 342 | 350 | 357 | 362 | 368 | 373 | 379 | 387 | 393 | 399 | 407 | 415 | 421 | 429 | 437 | 444 | 451 | 458 | 463 | 468 | 475 | 482 | 490 | 496 | 501 | 506 | 512 | 518 | 525 | 533 | 540 | 546 | 551 | 557 | 563 | 571 | 578 | 586 | 594 | 601 | 607 | 612 | 618 | 626 | 632 | 639 | 644 | 651 | 658 | 665 | 670 | 677
472 | 1.8342 | 17 | 41 | 82 | 138 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 3 | 7 | 13 | 22 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 8 | 13 | 19 | 25 | 32 | 37 | 45 | 50 | 58 | 63 | 69 | 74 | 82 | 88 | 96 | 101 | 107 | 112 | 119 | 126 | 134 | 139 | 147 | 153 | 159 | 165 | 172 | 180 | 187 | 194 | 202 | 209 | 215 | 220 | 225 | 231 | 237 | 242 | 249 | 254 | 262 | 268 | 274 | 280 | 287 | 295 | 300 | 306 | 311 | 319 | 326 | 332 | 340 | 346 | 353 | 358 | 366 | 372 | 379 | 384 | 389 | 395 | 400 | 406 | 413 | 420 | 427 | 432 | 438 | 444 | 450 | 455 | 462 | 467 | 473 | 478 | 485 | 493 | 501 | 509 | 514 | 521 | 527 | 532 | 540 | 546 | 553 | 561 | 568 | 574 | 579 | 584 | 591 | 598 | 603 | 610 | 615 | 622 | 630 | 638 | 645 | 652 | 657 | 663
473 | 1.6169 | 9 | 22 | 56 | 99 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 161 | 2 | 4 | 9 | 16 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 6 | 13 | 19 | 24 | 32 | 39 | 47 | 53 | 58 | 63 | 69 | 74 | 82 | 88 | 94 | 102 | 108 | 116 | 122 | 128 | 135 | 142 | 148 | 153 | 161 | 166 | 174 | 179 | 186 | 194 | 201 | 209 | 214 | 221 | 229 | 235 | 241 | 248 | 253 | 259 | 267 | 273 | 281 | 287 | 295 | 303 | 310 | 318 | 324 | 330 | 335 | 340 | 347 | 352 | 360 | 368 | 375 | 382 | 388 | 393 | 401 | 408 | 415 | 422 | 430 | 438 | 446 | 452 | 459 | 465 | 472 | 479 | 485 | 493 | 499 | 506 | 511 | 516 | 522 | 529 | 536 | 544 | 552 | 557 | 563 | 568 | 574 | 580 | 588 | 596 | 602 | 610 | 617 | 624 | 629 | 635 | 643 | 648 | 654 | 659 | 665 | 670 | 675 | 683
474 | 1.2804 | 13 | 29 | 56 | 82 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 2 | 5 | 9 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 7 | 14 | 20 | 26 | 32 | 38 | 46 | 54 | 59 | 66 | 72 | 79 | 87 | 95 | 101 | 108 | 115 | 120 | 127 | 134 | 141 | 149 | 156 | 163 | 169 | 176 | 181 | 188 | 193 | 198 | 203 | 209 | 214 | 222 | 230 | 236 | 242 | 249 | 255 | 261 | 268 | 273 | 278 | 283 | 290 | 298 | 303 | 308 | 316 | 322 | 328 | 334 | 339 | 345 | 353 | 361 | 367 | 374 | 380 | 388 | 396 | 402 | 410 | 417 | 423 | 431 | 436 | 443 | 450 | 456 | 464 | 470 | 478 | 485 | 492 | 497 | 504 | 509 | 514 | 519 | 526 | 532 | 540 | 547 | 555 | 561 | 566 | 573 | 578 | 585 | 591 | 598 | 606 | 613 | 618 | 626 | 632 | 638 | 643 | 649 | 655 | 662 | 669 | 676
475 | 1.6459 | 15 | 29 | 56 | 103 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 3 | 5 | 9 | 17 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 8 | 14 | 21 | 28 | 33 | 38 | 43 | 49 | 56 | 62 | 70 | 76 | 82 | 89 | 94 | 100 | 108 | 116 | 122 | 130 | 136 | 144 | 151 | 157 | 162 | 170 | 178 | 183 | 190 | 195 | 200 | 208 | 215 | 222 | 229 | 234 | 242 | 248 | 256 | 261 | 269 | 277 | 283 | 291 | 299 | 304 | 310 | 315 | 321 | 327 | 335 | 341 | 346 | 354 | 362 | 367 | 375 | 380 | 385 | 393 | 398 | 405 | 411 | 417 | 422 | 427 | 434 | 442 | 448 | 454 | 460 | 467 | 472 | 477 | 483 | 489 | 497 | 503 | 510 | 517 | 522 | 529 | 536 | 541 | 548 | 556 | 564 | 570 | 578 | 585 | 593 | 600 | 605 | 612 | 617 | 625 | 630 | 635 | 642 | 650 | 656 | 661 | 669 | 674
476 | 1.5004 | 14 | 30 | 59 | 102 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 3 | 5 | 9 | 15 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 5 | 12 | 18 | 26 | 32 | 37 | 45 | 53 | 61 | 68 | 74 | 81 | 88 | 96 | 104 | 110 | 116 | 121 | 126 | 132 | 138 | 145 | 150 | 157 | 165 | 173 | 178 | 186 | 192 | 199 | 207 | 214 | 222 | 227 | 233 | 239 | 244 | 252 | 258 | 263 | 268 | 274 | 280 | 287 | 294 | 301 | 306 | 313 | 320 | 325 | 331 | 336 | 343 | 351 | 357 | 362 | 368 | 374 | 379 | 387 | 392 | 400 | 408 | 414 | 421 | 428 | 435 | 443 | 448 | 456 | 464 | 471 | 477 | 484 | 492 | 499 | 505 | 510 | 516 | 523 | 528 | 536 | 544 | 551 | 559 | 566 | 572 | 579 | 586 | 591 | 598 | 605 | 613 | 618 | 626 | 632 | 638 | 643 | 651 | 659 | 665 | 671 | 677 | 685
477 | 1.5063 | 13 | 36 | 59 | 90 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 3 | 6 | 10 | 15 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 11 | 16 | 22 | 30 | 37 | 42 | 50 | 57 | 64 | 72 | 77 | 82 | 87 | 95 | 102 | 109 | 115 | 121 | 126 | 134 | 139 | 147 | 152 | 159 | 166 | 173 | 179 | 184 | 192 | 197 | 202 | 207 | 215 | 223 | 230 | 238 | 245 | 250 | 255 | 262 | 269 | 277 | 283 | 288 | 296 | 302 | 310 | 315 | 323 | 331 | 337 | 342 | 349 | 355 | 363 | 369 | 376 | 384 | 389 | 395 | 403 | 410 | 416 | 421 | 429 | 436 | 443 | 449 | 456 | 463 | 469 | 475 | 481 | 487 | 495 | 502 | 508 | 516 | 524 | 532 | 538 | 546 | 551 | 559 | 566 | 573 | 578 | 584 | 590 | 595 | 603 | 611 | 616 | 624 | 629 | 634 | 642 | 648 | 655 | 663 | 670 | 677 | 685
478 | 1.0402 | 8 | 24 | 46 | 78 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 2 | 4 | 8 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 6 | 13 | 18 | 26 | 33 | 38 | 43 | 49 | 55 | 62 | 67 | 72 | 77 | 82 | 88 | 95 | 101 | 107 | 115 | 122 | 130 | 137 | 142 | 150 | 158 | 166 | 171 | 179 | 184 | 192 | 197 | 202 | 209 | 215 | 222 | 228 | 236 | 241 | 248 | 254 | 261 | 269 | 277 | 282 | 287 | 293 | 299 | 306 | 311 | 319 | 326 | 334 | 340 | 345 | 352 | 357 | 362 | 369 | 376 | 381 | 388 | 395 | 400 | 405 | 411 | 419 | 424 | 429 | 437 | 443 | 451 | 459 | 465 | 473 | 480 | 487 | 493 | 501 | 507 | 513 | 518 | 526 | 533 | 540 | 545 | 552 | 560 | 566 | 572 | 578 | 585 | 591 | 599 | 606 | 611 | 618 | 624 | 629 | 637 | 645 | 652 | 660 | 665 | 670
479 | 1.8777 | 17 | 42 | 89 | 131 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 3 | 7 | 15 | 22 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 6 | 12 | 19 | 25 | 30 | 36 | 42 | 49 | 54 | 61 | 67 | 73 | 81 | 86 | 91 | 96 | 103 | 109 | 114 | 122 | 129 | 134 | 142 | 150 | 155 | 160 | 166 | 173 | 180 | 188 | 194 | 201 | 209 | 216 | 224 | 229 | 235 | 243 | 249 | 254 | 261 | 266 | 271 | 278 | 286 | 293 | 298 | 303 | 310 | 315 | 323 | 331 | 339 | 344 | 352 | 357 | 364 | 371 | 377 | 385 | 392 | 398 | 404 | 410 | 418 | 426 | 432 | 440 | 447 | 453 | 461 | 466 | 473 | 481 | 489 | 497 | 504 | 511 | 518 | 523 | 528 | 533 | 541 | 548 | 556 | 564 | 570 | 575 | 580 | 588 | 596 | 601 | 608 | 615 | 622 | 628 | 634 | 641 | 648 | 656 | 664 | 671 | 679 | 687
480 | 1.5042 | 13 | 27 | 58 | 89 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 2 | 4 | 10 | 14 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 6 | 13 | 19 | 27 | 33 | 41 | 46 | 51 | 57 | 64 | 71 | 79 | 84 | 90 | 98 | 106 | 111 | 119 | 127 | 132 | 139 | 146 | 152 | 160 | 166 | 174 | 182 | 190 | 195 | 200 | 207 | 212 | 219 | 225 | 231 | 238 | 243 | 250 | 257 | 264 | 269 | 274 | 281 | 289 | 296 | 303 | 311 | 318 | 324 | 330 | 335 | 340 | 346 | 351 | 356 | 363 | 371 | 378 | 386 | 391 | 399 | 406 | 411 | 416 | 421 | 427 | 433 | 438 | 444 | 451 | 456 | 463 | 469 | 474 | 482 | 488 | 494 | 502 | 510 | 518 | 524 | 529 | 534 | 540 | 547 | 555 | 563 | 570 | 578 | 584 | 591 | 598 | 603 | 609 | 615 | 623 | 631 | 637 | 642 | 647 | 653 | 659 | 665 | 673
481 | 1.8827 | 10 | 26 | 60 | 100 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 121 | 2 | 4 | 9 | 15 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 16 | 22 | 27 | 35 | 43 | 49 | 55 | 63 | 68 | 76 | 84 | 89 | 94 | 102 | 107 | 113 | 121 | 126 | 133 | 141 | 148 | 153 | 160 | 165 | 171 | 178 | 186 | 193 | 199 | 206 | 212 | 217 | 223 | 229 | 237 | 245 | 253 | 261 | 266 | 274 | 282 | 287 | 294 | 302 | 310 | 316 | 323 | 331 | 339 | 345 | 353 | 358 | 364 | 372 | 377 | 384 | 391 | 396 | 403 | 411 | 417 | 425 | 432 | 438 | 444 | 452 | 460 | 468 | 475 | 480 | 487 | 495 | 503 | 511 | 517 | 522 | 528 | 535 | 541 | 548 | 553 | 561 | 568 | 574 | 581 | 587 | 592 | 600 | 608 | 614 | 620 | 626 | 632 | 640 | 648 | 655 | 662 | 668 | 674 | 681 | 687 | 692 | 698
482 | 1.6772 | 16 | 32 | 58 | 105 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 3 | 5 | 9 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 8 | 15 | 20 | 25 | 33 | 40 | 46 | 51 | 58 | 65 | 71 | 78 | 85 | 90 | 97 | 105 | 112 | 118 | 124 | 129 | 135 | 142 | 150 | 157 | 164 | 171 | 177 | 184 | 192 | 198 | 204 | 211 | 217 | 222 | 229 | 237 | 244 | 250 | 255 | 261 | 268 | 273 | 281 | 288 | 295 | 303 | 309 | 314 | 320 | 328 | 336 | 344 | 351 | 358 | 366 | 373 | 381 | 388 | 394 | 399 | 407 | 413 | 419 | 424 | 432 | 437 | 442 | 449 | 456 | 464 | 472 | 478 | 483 | 488 | 496 | 504 | 509 | 516 | 521 | 529 | 536 | 541 | 547 | 552 | 558 | 564 | 571 | 579 | 585 | 591 | 598 | 606 | 613 | 620 | 625 | 631 | 639 | 647 | 654 | 659 | 664 | 669 | 674 | 679
483 | 1.5862 | 13 | 33 | 64 | 101 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 2 | 5 | 10 | 15 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 7 | 15 | 23 | 31 | 38 | 44 | 50 | 56 | 63 | 70 | 78 | 85 | 90 | 97 | 103 | 109 | 116 | 121 | 126 | 134 | 139 | 144 | 150 | 158 | 164 | 172 | 179 | 185 | 192 | 200 | 206 | 212 | 220 | 225 | 230 | 235 | 240 | 247 | 252 | 259 | 264 | 270 | 276 | 282 | 288 | 295 | 302 | 308 | 313 | 319 | 324 | 330 | 337 | 342 | 347 | 354 | 359 | 364 | 370 | 376 | 381 | 388 | 394 | 401 | 409 | 414 | 420 | 426 | 431 | 438 | 446 | 452 | 457 | 465 | 472 | 477 | 484 | 491 | 497 | 505 | 511 | 519 | 526 | 533 | 538 | 545 | 550 | 557 | 563 | 571 | 577 | 585 | 591 | 597 | 603 | 610 | 618 | 624 | 631 | 639 | 645 | 652 | 659 | 665
484 | 1.2224 | 8 | 24 | 45 | 72 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 1 | 4 | 7 | 11 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 8 | 15 | 22 | 27 | 33 | 39 | 47 | 54 | 62 | 70 | 76 | 81 | 87 | 93 | 98 | 103 | 111 | 118 | 123 | 129 | 137 | 145 | 151 | 158 | 164 | 169 | 177 | 182 | 189 | 194 | 201 | 209 | 214 | 220 | 227 | 234 | 239 | 245 | 251 | 258 | 263 | 270 | 275 | 282 | 290 | 295 | 303 | 308 | 315 | 322 | 327 | 334 | 340 | 347 | 353 | 359 | 367 | 373 | 381 | 389 | 394 | 400 | 406 | 414 | 422 | 430 | 437 | 443 | 448 | 453 | 461 | 469 | 476 | 482 | 487 | 495 | 500 | 506 | 512 | 520 | 525 | 531 | 538 | 546 | 554 | 562 | 567 | 573 | 581 | 587 | 592 | 598 | 604 | 612 | 617 | 623 | 631 | 636 | 641 | 648 | 654 | 660 | 667 | 672
485 | 1.5699 | 16 | 37 | 77 | 125 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 3 | 6 | 12 | 20 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 8 | 15 | 20 | 27 | 32 | 37 | 44 | 49 | 55 | 63 | 71 | 78 | 85 | 90 | 97 | 104 | 112 | 117 | 123 | 131 | 139 | 147 | 154 | 161 | 168 | 174 | 181 | 188 | 193 | 200 | 208 | 216 | 224 | 229 | 235 | 240 | 248 | 255 | 263 | 271 | 279 | 286 | 291 | 299 | 304 | 310 | 318 | 326 | 332 | 339 | 346 | 351 | 356 | 361 | 367 | 372 | 379 | 387 | 395 | 400 | 406 | 414 | 420 | 427 | 433 | 440 | 446 | 453 | 460 | 466 | 474 | 482 | 488 | 495 | 502 | 509 | 516 | 521 | 526 | 534 | 542 | 550 | 557 | 563 | 571 | 578 | 584 | 591 | 596 | 603 | 609 | 617 | 625 | 632 | 639 | 647 | 652 | 657 | 663 | 668 | 673 | 681 | 686 | 693
486 | 1.6965 | 9 | 25 | 61 | 106 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 5 | 10 | 17 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 10 | 16 | 24 | 31 | 37 | 43 | 51 | 58 | 63 | 71 | 77 | 83 | 89 | 97 | 105 | 110 | 117 | 123 | 129 | 134 | 142 | 148 | 154 | 159 | 166 | 174 | 180 | 186 | 191 | 197 | 203 | 208 | 215 | 221 | 226 | 233 | 238 | 243 | 248 | 253 | 261 | 266 | 274 | 279 | 286 | 294 | 301 | 308 | 314 | 319 | 324 | 332 | 340 | 347 | 352 | 360 | 365 | 373 | 380 | 385 | 393 | 400 | 408 | 416 | 424 | 432 | 439 | 445 | 453 | 460 | 468 | 476 | 482 | 488 | 496 | 503 | 509 | 514 | 520 | 526 | 534 | 542 | 547 | 552 | 560 | 568 | 576 | 581 | 589 | 594 | 602 | 607 | 615 | 623 | 629 | 635 | 642 | 647 | 653 | 660 | 668 | 674 | 679
487 | 1.875 | 14 | 31 | 76 | 123 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 2 | 6 | 13 | 20 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 6 | 14 | 19 | 24 | 30 | 37 | 44 | 49 | 57 | 63 | 69 | 75 | 83 | 88 | 96 | 102 | 107 | 113 | 118 | 125 | 130 | 138 | 143 | 148 | 153 | 159 | 165 | 172 | 178 | 183 | 191 | 197 | 204 | 210 | 218 | 226 | 232 | 239 | 247 | 252 | 258 | 266 | 273 | 281 | 289 | 294 | 299 | 306 | 314 | 321 | 328 | 335 | 342 | 347 | 352 | 360 | 367 | 375 | 382 | 390 | 398 | 405 | 412 | 420 | 427 | 433 | 439 | 444 | 451 | 456 | 462 | 467 | 472 | 478 | 485 | 492 | 499 | 507 | 515 | 520 | 526 | 533 | 538 | 544 | 549 | 557 | 562 | 569 | 577 | 585 | 591 | 597 | 604 | 611 | 619 | 626 | 634 | 640 | 646 | 652 | 659 | 667 | 673 | 679
488 | 1.8728 | 10 | 33 | 71 | 124 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 154 | 2 | 5 | 11 | 19 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 7 | 14 | 20 | 27 | 35 | 43 | 49 | 57 | 63 | 70 | 75 | 82 | 88 | 94 | 102 | 110 | 116 | 123 | 130 | 138 | 143 | 148 | 153 | 159 | 164 | 169 | 174 | 181 | 189 | 195 | 203 | 208 | 214 | 221 | 229 | 237 | 242 | 248 | 254 | 261 | 269 | 275 | 283 | 291 | 296 | 301 | 308 | 314 | 322 | 328 | 333 | 341 | 348 | 353 | 361 | 366 | 374 | 379 | 384 | 390 | 395 | 403 | 409 | 417 | 423 | 430 | 436 | 444 | 451 | 456 | 462 | 468 | 475 | 480 | 485 | 490 | 495 | 501 | 507 | 514 | 522 | 528 | 533 | 541 | 547 | 552 | 560 | 566 | 571 | 579 | 587 | 593 | 598 | 605 | 610 | 617 | 623 | 628 | 636 | 643 | 649 | 654 | 662 | 667
489 | 1.891 | 10 | 28 | 76 | 131 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 2 | 5 | 12 | 21 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 5 | 13 | 19 | 26 | 34 | 42 | 50 | 57 | 63 | 70 | 75 | 82 | 89 | 95 | 101 | 107 | 113 | 118 | 124 | 129 | 136 | 143 | 148 | 155 | 162 | 170 | 175 | 181 | 186 | 193 | 200 | 207 | 212 | 217 | 222 | 227 | 232 | 240 | 245 | 251 | 258 | 264 | 269 | 276 | 282 | 287 | 295 | 302 | 309 | 316 | 323 | 331 | 337 | 343 | 349 | 355 | 361 | 369 | 376 | 384 | 392 | 400 | 407 | 412 | 420 | 427 | 435 | 443 | 450 | 456 | 464 | 469 | 477 | 482 | 490 | 496 | 502 | 510 | 516 | 521 | 527 | 532 | 539 | 547 | 552 | 560 | 566 | 572 | 579 | 585 | 592 | 600 | 608 | 614 | 621 | 627 | 633 | 638 | 645 | 653 | 661 | 667 | 672 | 679
490 | 1.6528 | 17 | 41 | 73 | 115 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 3 | 7 | 13 | 19 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 5 | 11 | 18 | 24 | 31 | 37 | 43 | 51 | 56 | 61 | 67 | 72 | 80 | 86 | 93 | 101 | 107 | 114 | 120 | 126 | 134 | 140 | 145 | 151 | 156 | 163 | 168 | 173 | 179 | 187 | 194 | 199 | 205 | 211 | 217 | 224 | 231 | 236 | 241 | 247 | 255 | 261 | 269 | 274 | 282 | 287 | 294 | 299 | 306 | 314 | 319 | 326 | 334 | 342 | 347 | 355 | 362 | 367 | 374 | 380 | 387 | 392 | 400 | 408 | 416 | 422 | 428 | 434 | 442 | 449 | 455 | 463 | 471 | 478 | 485 | 490 | 496 | 504 | 511 | 516 | 521 | 526 | 534 | 539 | 544 | 552 | 557 | 564 | 570 | 578 | 585 | 590 | 596 | 604 | 610 | 617 | 623 | 631 | 636 | 644 | 652 | 658 | 664 | 670
491 | 1.8273 | 10 | 27 | 57 | 105 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 2 | 5 | 10 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 7 | 13 | 19 | 26 | 32 | 37 | 42 | 48 | 56 | 61 | 66 | 72 | 79 | 85 | 92 | 98 | 104 | 111 | 119 | 127 | 135 | 141 | 146 | 152 | 160 | 167 | 174 | 182 | 187 | 192 | 198 | 205 | 211 | 219 | 224 | 229 | 235 | 241 | 248 | 253 | 260 | 265 | 272 | 279 | 285 | 293 | 299 | 305 | 313 | 320 | 326 | 332 | 340 | 348 | 356 | 361 | 369 | 374 | 382 | 388 | 394 | 399 | 404 | 412 | 418 | 423 | 431 | 436 | 441 | 449 | 457 | 463 | 471 | 476 | 482 | 488 | 496 | 504 | 509 | 517 | 525 | 533 | 541 | 547 | 553 | 560 | 566 | 571 | 579 | 584 | 589 | 595 | 602 | 607 | 613 | 620 | 628 | 635 | 642 | 649 | 657 | 662 | 667 | 673
492 | 1.2555 | 13 | 25 | 47 | 83 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 3 | 5 | 8 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 7 | 12 | 18 | 23 | 30 | 38 | 43 | 51 | 56 | 62 | 69 | 76 | 83 | 90 | 96 | 103 | 110 | 115 | 120 | 128 | 135 | 142 | 148 | 156 | 162 | 168 | 175 | 182 | 189 | 194 | 200 | 208 | 213 | 220 | 226 | 232 | 237 | 244 | 249 | 257 | 263 | 269 | 276 | 284 | 292 | 297 | 303 | 311 | 318 | 326 | 333 | 338 | 345 | 351 | 358 | 363 | 368 | 373 | 379 | 386 | 394 | 401 | 407 | 412 | 418 | 424 | 431 | 438 | 444 | 451 | 457 | 462 | 468 | 473 | 479 | 487 | 493 | 501 | 508 | 514 | 519 | 525 | 532 | 537 | 542 | 547 | 555 | 560 | 568 | 574 | 579 | 587 | 593 | 599 | 605 | 610 | 617 | 625 | 630 | 638 | 646 | 654 | 662 | 669
493 | 1.6071 | 10 | 23 | 49 | 88 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 2 | 4 | 8 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 5 | 12 | 18 | 25 | 32 | 40 | 48 | 56 | 62 | 67 | 74 | 80 | 86 | 91 | 97 | 102 | 110 | 117 | 123 | 129 | 135 | 143 | 151 | 158 | 163 | 170 | 176 | 182 | 188 | 194 | 201 | 207 | 214 | 220 | 228 | 235 | 242 | 250 | 257 | 265 | 273 | 281 | 286 | 294 | 301 | 308 | 316 | 322 | 328 | 333 | 339 | 345 | 352 | 358 | 364 | 369 | 377 | 385 | 392 | 400 | 407 | 413 | 419 | 424 | 431 | 438 | 444 | 452 | 458 | 465 | 470 | 476 | 483 | 488 | 495 | 501 | 507 | 512 | 520 | 527 | 532 | 538 | 543 | 549 | 557 | 565 | 572 | 577 | 583 | 588 | 595 | 603 | 610 | 617 | 625 | 633 | 640 | 648 | 656 | 662 | 668 | 674 | 680 | 686
494 | 1.7362 | 18 | 45 | 72 | 125 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 3 | 8 | 12 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 7 | 13 | 18 | 24 | 30 | 37 | 42 | 50 | 55 | 62 | 69 | 74 | 81 | 88 | 93 | 100 | 106 | 112 | 119 | 127 | 132 | 140 | 148 | 156 | 164 | 172 | 179 | 184 | 192 | 198 | 203 | 210 | 217 | 225 | 232 | 239 | 247 | 252 | 257 | 265 | 271 | 277 | 284 | 291 | 299 | 306 | 312 | 320 | 328 | 334 | 342 | 349 | 355 | 360 | 368 | 374 | 379 | 385 | 390 | 395 | 403 | 411 | 416 | 422 | 430 | 437 | 444 | 449 | 457 | 463 | 469 | 476 | 484 | 492 | 499 | 505 | 511 | 516 | 524 | 531 | 539 | 546 | 551 | 556 | 563 | 568 | 575 | 583 | 589 | 594 | 599 | 606 | 612 | 618 | 625 | 633 | 640 | 646 | 654 | 659 | 665 | 673 | 678 | 684
495 | 1.3561 | 10 | 27 | 61 | 99 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 142 | 2 | 5 | 10 | 16 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 7 | 14 | 21 | 26 | 32 | 40 | 48 | 53 | 58 | 64 | 72 | 78 | 86 | 93 | 98 | 103 | 111 | 116 | 123 | 131 | 138 | 143 | 151 | 158 | 165 | 173 | 181 | 188 | 196 | 204 | 211 | 219 | 225 | 232 | 237 | 242 | 248 | 255 | 261 | 267 | 273 | 280 | 287 | 294 | 301 | 306 | 312 | 320 | 326 | 332 | 340 | 347 | 353 | 358 | 363 | 368 | 374 | 379 | 385 | 391 | 399 | 404 | 412 | 418 | 424 | 430 | 436 | 442 | 450 | 458 | 464 | 472 | 479 | 484 | 492 | 499 | 505 | 510 | 517 | 525 | 533 | 538 | 545 | 551 | 557 | 564 | 572 | 579 | 585 | 590 | 595 | 600 | 608 | 616 | 622 | 629 | 635 | 643 | 649 | 654 | 659 | 664 | 669 | 674
496 | 1.1292 | 8 | 19 | 45 | 78 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 2 | 3 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 14 | 20 | 25 | 31 | 37 | 43 | 49 | 56 | 62 | 69 | 74 | 80 | 85 | 90 | 96 | 101 | 107 | 115 | 122 | 128 | 135 | 142 | 147 | 152 | 160 | 166 | 171 | 177 | 185 | 191 | 196 | 201 | 208 | 213 | 218 | 226 | 232 | 239 | 245 | 250 | 257 | 262 | 269 | 277 | 284 | 289 | 295 | 301 | 308 | 315 | 320 | 325 | 330 | 336 | 344 | 350 | 355 | 360 | 367 | 373 | 380 | 386 | 392 | 397 | 405 | 412 | 417 | 425 | 431 | 437 | 443 | 450 | 455 | 460 | 466 | 474 | 482 | 488 | 495 | 503 | 510 | 516 | 522 | 529 | 536 | 544 | 550 | 557 | 562 | 567 | 572 | 578 | 585 | 593 | 599 | 604 | 609 | 616 | 623 | 631 | 638 | 646 | 654
497 | 1.7829 | 17 | 34 | 67 | 116 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 3 | 6 | 10 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 6 | 12 | 20 | 27 | 32 | 39 | 47 | 55 | 63 | 69 | 75 | 83 | 89 | 94 | 102 | 109 | 115 | 122 | 128 | 136 | 142 | 150 | 158 | 165 | 171 | 178 | 184 | 191 | 197 | 202 | 207 | 212 | 217 | 223 | 228 | 235 | 243 | 249 | 256 | 261 | 269 | 276 | 281 | 287 | 294 | 302 | 307 | 315 | 323 | 331 | 336 | 344 | 349 | 355 | 363 | 368 | 374 | 379 | 385 | 392 | 399 | 405 | 412 | 417 | 422 | 429 | 435 | 443 | 448 | 453 | 459 | 464 | 469 | 474 | 480 | 488 | 496 | 501 | 506 | 512 | 519 | 524 | 530 | 536 | 541 | 546 | 554 | 561 | 567 | 573 | 581 | 586 | 594 | 600 | 605 | 610 | 616 | 624 | 631 | 638 | 645 | 652 | 658 | 664
498 | 1.8286 | 11 | 32 | 62 | 114 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 2 | 6 | 10 | 18 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 11 | 17 | 25 | 31 | 39 | 47 | 53 | 58 | 63 | 71 | 77 | 85 | 92 | 98 | 103 | 109 | 114 | 121 | 128 | 136 | 142 | 148 | 155 | 160 | 165 | 171 | 179 | 187 | 195 | 202 | 208 | 215 | 222 | 228 | 234 | 239 | 245 | 251 | 256 | 264 | 269 | 275 | 283 | 291 | 298 | 306 | 314 | 319 | 325 | 333 | 339 | 345 | 350 | 356 | 363 | 368 | 376 | 382 | 387 | 392 | 399 | 404 | 412 | 418 | 426 | 434 | 441 | 449 | 454 | 459 | 465 | 470 | 477 | 483 | 488 | 493 | 501 | 508 | 513 | 519 | 526 | 534 | 541 | 546 | 551 | 558 | 565 | 573 | 581 | 589 | 596 | 602 | 610 | 615 | 623 | 628 | 636 | 641 | 647 | 654 | 662 | 670 | 678
499 | 1.5586 | 10 | 28 | 61 | 108 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 2 | 4 | 9 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 8 | 16 | 24 | 31 | 36 | 43 | 50 | 57 | 63 | 69 | 77 | 84 | 90 | 96 | 102 | 107 | 112 | 119 | 124 | 130 | 135 | 143 | 148 | 156 | 163 | 168 | 175 | 183 | 189 | 194 | 200 | 207 | 213 | 221 | 229 | 234 | 240 | 248 | 253 | 259 | 264 | 271 | 279 | 286 | 294 | 302 | 309 | 316 | 323 | 328 | 336 | 344 | 350 | 355 | 361 | 368 | 376 | 381 | 387 | 395 | 400 | 406 | 412 | 420 | 425 | 431 | 437 | 444 | 452 | 459 | 466 | 473 | 481 | 489 | 497 | 503 | 511 | 519 | 526 | 532 | 539 | 544 | 552 | 560 | 567 | 575 | 580 | 587 | 593 | 600 | 605 | 611 | 616 | 622 | 628 | 633 | 639 | 644 | 650 | 657 | 662 | 670 | 677 | 682
500 | 1.0669 | 8 | 22 | 40 | 64 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 2 | 4 | 6 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 5 | 13 | 20 | 26 | 32 | 40 | 48 | 53 | 60 | 68 | 76 | 83 | 90 | 97 | 102 | 110 | 117 | 123 | 131 | 139 | 145 | 152 | 157 | 164 | 169 | 175 | 183 | 189 | 196 | 201 | 209 | 214 | 221 | 227 | 234 | 242 | 247 | 252 | 257 | 264 | 271 | 277 | 283 | 289 | 297 | 302 | 307 | 314 | 320 | 326 | 332 | 338 | 345 | 351 | 358 | 364 | 369 | 376 | 381 | 387 | 395 | 402 | 408 | 415 | 422 | 427 | 434 | 442 | 448 | 453 | 458 | 464 | 469 | 476 | 481 | 486 | 493 | 500 | 507 | 515 | 520 | 528 | 534 | 542 | 549 | 554 | 559 | 564 | 572 | 578 | 584 | 590 | 596 | 602 | 610 | 618 | 626 | 631 | 636 | 643 | 649 | 657 | 663 | 671
501 | 1.8897 | 14 | 32 | 67 | 124 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 2 | 5 | 10 | 17 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 8 | 16 | 24 | 31 | 36 | 44 | 52 | 58 | 66 | 74 | 81 | 87 | 95 | 103 | 111 | 117 | 125 | 130 | 135 | 141 | 146 | 153 | 159 | 165 | 170 | 177 | 184 | 190 | 197 | 204 | 212 | 218 | 224 | 230 | 236 | 244 | 252 | 258 | 263 | 270 | 276 | 284 | 292 | 299 | 304 | 312 | 317 | 322 | 327 | 332 | 338 | 346 | 353 | 358 | 366 | 371 | 379 | 386 | 394 | 401 | 409 | 417 | 422 | 427 | 432 | 440 | 446 | 453 | 460 | 465 | 472 | 479 | 486 | 492 | 499 | 504 | 511 | 516 | 521 | 526 | 532 | 538 | 545 | 552 | 558 | 563 | 571 | 576 | 583 | 589 | 595 | 602 | 609 | 617 | 625 | 630 | 636 | 643 | 648 | 656 | 661 | 667 | 675 | 682